## Sheet7
17.5 | 12.5 | 1.4
1.4
1.75
0.8
Tambahkan chart ft/day (total) dari membagi $/day dibagi $/ft

## Charts
Note on U25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Munifah and @Ryandito Mahendradani hasilnya dari remapping. Aku restart laptop dulu ya. Monggo direview. Sejauh ini tidak ada pattern untuk $/ft vs $k/day. Walaupun tidak sejomplang kemarin

## Sheet6
Bagaimana menjawab pertanyaan "bayar mahal tapi lancar"?

## DashBoard.Tab.Template
Asset | Asset_Label | Campaign | Camp_Label | Well | Well_Label | No of Wells Drilled | Campaign Cost USD mn | Well Cost USD mn | Drilling Shared Cost USD mn | Support Cost USD | Surface Facilities Cost USD | Campaign Cost per Well USD | Actual Total Depth ft MD | Drilling Duration days
Darajat | Darajat | DRJ - 2019 | DRJ - 2019 | DRJ-44OH | DRJ-44OH | 5 | 42.0034 | 4.2156 | 0.89604 | 0.46409 | 1.6158 | 7.1915 | 0 | 0
Darajat | Darajat | DRJ - 2019 | DRJ - 2019 | DRJ-45OH | DRJ-45OH | 5 | 42.0034 | 6.5561 | 0.89604 | 0.46409 | 1.6158 | 9.532 | 0 | 0
Darajat | Darajat | DRJ - 2019 | DRJ - 2019 | DRJ-46OH | DRJ-46OH | 5 | 42.0034 | 5.9692 | 0.89604 | 0.46409 | 1.6158 | 8.9451 | 0 | 0
Darajat | Darajat | DRJ - 2019 | DRJ - 2019 | DRJ-47OH | DRJ-47OH | 5 | 42.0034 | 4.8038 | 0.89604 | 0.46409 | 1.6158 | 7.7797 | 0 | 0
Darajat | Darajat | DRJ - 2019 | DRJ - 2019 | DRJ-48 | DRJ-48 | 5 | 42.0034 | 5.5791 | 0.89604 | 0.46409 | 1.6158 | 8.555 | 5399.5 | 21.4792
Darajat | Darajat | DRJ - 2022 | DRJ - 2022 | DRJ-38RD | DRJ-38RD | 5 | 30.6695 | 3.9122 | 0.91248 | 0.38913 | 0.73877 | 5.9526 | 6748 | 30
Darajat | Darajat | DRJ - 2022 | DRJ - 2022 | DRJ-49OH | DRJ-49OH | 5 | 30.6695 | 4.7829 | 0.91248 | 0.38913 | 0.73877 | 6.8233 | 0 | 0
Darajat | Darajat | DRJ - 2022 | DRJ - 2022 | DRJ-50OH | DRJ-50OH | 5 | 30.6695 | 4.0668 | 0.91248 | 0.38913 | 0.73877 | 6.1072 | 0 | 0
Darajat | Darajat | DRJ - 2022 | DRJ - 2022 | DRJ-51OH | DRJ-51OH | 5 | 30.6695 | 4.1985 | 0.91248 | 0.38913 | 0.73877 | 6.2389 | 0 | 0
Darajat | Darajat | DRJ - 2022 | DRJ - 2022 | DRJ-52OH | DRJ-52OH | 5 | 30.6695 | 3.5072 | 0.91248 | 0.38913 | 0.73877 | 5.5476 | 0 | 0
Darajat | Darajat | DRJ - 2024 | DRJ - 2024 | DRJ-53 | DRJ-53 | 5 | 37.3671 | 3.6096 | 1.034 | 0.38862 | 1.1212 | 6.1534 | 6500 | 22.7708
Darajat | Darajat | DRJ - 2024 | DRJ - 2024 | DRJ-54 | DRJ-54 | 5 | 37.3671 | 5.1896 | 1.034 | 0.38862 | 1.1212 | 7.7334 | 6014 | 29.6875
Darajat | Darajat | DRJ - 2024 | DRJ - 2024 | DRJ-55 | DRJ-55 | 5 | 37.3671 | 4.3599 | 1.034 | 0.38862 | 1.1212 | 6.9038 | 6000 | 18.2292
Darajat | Darajat | DRJ - 2024 | DRJ - 2024 | DRJ-56 | DRJ-56 | 5 | 37.3671 | 6.926 | 1.034 | 0.38862 | 1.1212 | 9.4698 | 6500 | 50.3125
Darajat | Darajat | DRJ - 2024 | DRJ - 2024 | DRJ-57 | DRJ-57 | 5 | 37.3671 | 4.563 | 1.034 | 0.38862 | 1.1212 | 7.1068 | 6000 | 18.8542
Salak | Salak | SLK - 2021 | SLK - 2021 | AWI 16-08 | AWI 16-08 | 5 | 28.0512 | 5.46 | 1.1168 | 0.27674 | 0.73941 | 7.593 | 0 | 0
Salak | Salak | SLK - 2021 | SLK - 2021 | AWI 16-09 | AWI 16-09 | 5 | 28.0512 | 3.0589 | 1.1168 | 0.27674 | 0.73941 | 5.1919 | 0 | 0
Salak | Salak | SLK - 2021 | SLK - 2021 | Awi 21-05 | Awi 21-05 | 5 | 28.0512 | 3.1118 | 1.1168 | 0.27674 | 0.73941 | 5.2448 | 0 | 0
Salak | Salak | SLK - 2021 | SLK - 2021 | Awi 21-06 | Awi 21-06 | 5 | 28.0512 | 2.1497 | 1.1168 | 0.27674 | 0.73941 | 4.2827 | 0 | 0
Salak | Salak | SLK - 2021 | SLK - 2021 | AWI 9-10 | AWI 9-10 | 5 | 28.0512 | 3.6059 | 1.1168 | 0.27674 | 0.73941 | 5.7388 | 8919 | 22
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 21-7 | AWI 21-7 | 9 | 38.5223 | 3.1838 | 0.60168 | 0.22585 | 0.51348 | 4.5248 | 5060 | 16.4167
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 21-8 | AWI 21-8 | 9 | 38.5223 | 3.1873 | 0.60168 | 0.22585 | 0.51348 | 4.5283 | 4055 | 13.9167
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 23-1 | AWI 23-1 | 9 | 38.5223 | 4.8799 | 0.60168 | 0.22585 | 0.51348 | 6.2209 | 9000 | 13.6979
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 23-2 | AWI 23-2 | 9 | 38.5223 | 4.3257 | 0.60168 | 0.22585 | 0.51348 | 5.6667 | 8050 | 20
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 2-6 | AWI 2-6 | 9 | 38.5223 | 2.3294 | 0.60168 | 0.22585 | 0.51348 | 3.6705 | 5484 | 11.0417
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 2-7 ML | AWI 2-7 ML | 9 | 38.5223 | 4.7207 | 0.60168 | 0.22585 | 0.51348 | 6.0617 | 5497 | 26
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 3-9 | AWI 3-9 | 9 | 38.5223 | 3.6699 | 0.60168 | 0.22585 | 0.51348 | 5.0109 | 5500 | 12.5833
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 9-10 RD | AWI 9-10 RD | 9 | 38.5223 | 0.045128 | 0.60168 | 0.22585 | 0.51348 | 1.3861 | 0 | 0
Salak | Salak | SLK - 2025 | SLK - 2025 | AWI 9-11 | AWI 9-11 | 9 | 38.5223 | 0.1113 | 0.60168 | 0.22585 | 0.51348 | 1.4523 | 9000 | 11.3333
Wayang Windu | Wayang Windu | WW - 2018 | WW - 2018 | MBA-6 | MBA-6 | 4 | 26.987 | 4.4991 | 0.26514 | 0.065259 | 0.21655 | 5.0461 | 5732 | 27.25
Wayang Windu | Wayang Windu | WW - 2018 | WW - 2018 | MBA-7 | MBA-7 | 4 | 26.987 | 4.4231 | 0.26514 | 0.065259 | 0.21655 | 4.97 | 4965 | 24.8958
Wayang Windu | Wayang Windu | WW - 2018 | WW - 2018 | MBD-7 | MBD-7 | 4 | 26.987 | 6.6963 | 0.26514 | 0.065259 | 0.21655 | 7.2432 | 4997 | 38.7708
Wayang Windu | Wayang Windu | WW - 2018 | WW - 2018 | MBD-8 | MBD-8 | 4 | 26.987 | 9.1807 | 0.26514 | 0.065259 | 0.21655 | 9.7276 | 4140 | 50.6042
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | MBD-8WO | MBD-8WO | 6 | 27.075 | 2.8165 | 0.77751 | 0.13804 | 0.43606 | 4.1681 | 0 | 0
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | MBE-6 | MBE-6 | 6 | 27.075 | 2.5398 | 0.77751 | 0.13804 | 0.43606 | 3.8914 | 4500 | 15.2292
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | MBE-7 | MBE-7 | 6 | 27.075 | 3.4822 | 0.77751 | 0.13804 | 0.43606 | 4.8338 | 7065 | 24.1042
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | MBI-1 | MBI-1 | 6 | 27.075 | 1.9177 | 0.77751 | 0.13804 | 0.43606 | 3.2693 | 4325 | 10.9167
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | WWA-8 | WWA-8 | 6 | 27.075 | 5.306 | 0.77751 | 0.13804 | 0.43606 | 6.6576 | 5263 | 45.2292
Wayang Windu | Wayang Windu | WW - 2021 | WW - 2021 | WWA-9 | WWA-9 | 6 | 27.075 | 2.9031 | 0.77751 | 0.13804 | 0.43606 | 4.2547 | 7158 | 14.8542

## Pivot.Master
Place Holder | [5 empty] | Campaign Well Cost | [5 empty] | # of wells drilled | [5 empty] | $mn/well | [5 empty] | $/ft | [5 empty] | $k/day | [5 empty] | Cumulative Depth | [5 empty] | Cumulative Days | [5 empty] | Complete $/ft and $k/day |  |  |  |  | Complete $/ft and $k/day as Campaign | [6 empty] | Campaign Well Cost | [7 empty] | Well Name (WellView Version)
[58 empty] | Normalized to DRJ - 2019 | [9 empty] | AWI 10-4
Asset_Label | Camp_Label | Well | $/ft | $000/day | $mn/well | Sum of Campaign Cost per Well USD |  |  | Asset |  |  | Average of No of Wells Drilled |  |  | Asset |  |  | $mn/well |  |  | Asset |  |  | $/ft |  |  | Asset |  |  | $000/day |  |  | Asset |  |  | Cumulative Depth ft |  |  | Asset |  |  | Cumulative days |  |  | Asset |  |  | Asset_Label | Campaign | Well | $/ft | $000/day | Asset_Label | Campaign | Well | $/ft | $000/day | $/ft Norm | $000/day Norm | Asset_Label | Campaign | Well | Avg. Well Cost per Well $mn/well | Avg. Drill Shared Cost per Well $mn/well | Avg. Support Cost per well $mn/well | Avg. Surface Facility per well $mn/well | Total | AWI 16-8
Darajat | DRJ - 2019 | DRJ-44OH |  |  | 1.4383 | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Asset_Label | Campaign | Well | Darajat | Salak | Wayang Windu | Darajat | DRJ - 2019 | DRJ-48 | 1650.5928 | 398.294 | Darajat | DRJ - 2019 |  | 8104.0679 | 1955.5407 | -9.9183 | 1.9129 | Darajat | DRJ - 2019 |  | 5.4248 | 0.89604 | 0.46409 | 1.6158 | 8.4007 | AWI 16-9
Darajat | DRJ - 2019 | DRJ-45OH |  |  | 1.9064 | Darajat | DRJ - 2019 |  | 42.0034 |  |  | Darajat | DRJ - 2019 |  | 5 |  |  | Darajat | DRJ - 2019 |  | 8.4007 |  |  | Darajat | DRJ - 2019 |  | 8104.0679 |  |  | Darajat | DRJ - 2019 |  | 1955.5407 |  |  | Darajat | DRJ - 2019 |  | 5183 |  |  | Darajat | DRJ - 2019 |  | 21.4792 |  |  | Darajat | DRJ - 2022 | DRJ-38RD | 882.1274 | 198.4199 | Darajat | DRJ - 2022 |  | 4544.98 | 1022.3175 | -5.5624 | 1 | Darajat | DRJ - 2022 |  | 4.0935 | 0.91248 | 0.38913 | 0.73877 | 6.1339 | AWI 21-5
Darajat | DRJ - 2019 | DRJ-46OH |  |  | 1.789 | Darajat | DRJ - 2022 |  | 30.6695 |  |  | Darajat | DRJ - 2022 |  | 5 |  |  | Darajat | DRJ - 2022 |  | 6.1339 |  |  | Darajat | DRJ - 2022 |  | 4544.98 |  |  | Darajat | DRJ - 2022 |  | 1022.3175 |  |  | Darajat | DRJ - 2022 |  | 6748 |  |  | Darajat | DRJ - 2022 |  | 30 |  |  | Darajat | DRJ - 2024 | DRJ-53 | 946.6748 | 270.231 | Darajat | DRJ - 2024 |  | 1204.8465 | 267.1862 | -1.4746 | 0.26135 | Darajat | DRJ - 2024 |  | 4.9296 | 1.034 | 0.38862 | 1.1212 | 7.4734 | AWI 21-6
Darajat | DRJ - 2019 | DRJ-47OH |  |  | 1.5559 | Darajat | DRJ - 2024 |  | 37.3671 |  |  | Darajat | DRJ - 2024 |  | 5 |  |  | Darajat | DRJ - 2024 |  | 7.4734 |  |  | Darajat | DRJ - 2024 |  | 1204.8465 |  |  | Darajat | DRJ - 2024 |  | 267.1862 |  |  | Darajat | DRJ - 2024 |  | 31014 |  |  | Darajat | DRJ - 2024 |  | 139.8542 |  |  | Darajat | DRJ - 2024 | DRJ-54 | 1285.8941 | 260.4924 | Salak | SLK - 2021 |  | 3145.1113 | 1275.0567 | -3.8492 | 1.2472 | Salak | SLK - 2021 |  | 3.4773 | 1.1168 | 0.27674 | 0.73941 | 5.6102 | AWI 21-7
Darajat | DRJ - 2019 | DRJ-48 | 1650.5928 | 398.294 | 1.711 | Salak | SLK - 2021 |  |  | 28.0512 |  | Salak | SLK - 2021 |  |  | 5 |  | Salak | SLK - 2021 |  |  | 5.6102 |  | Salak | SLK - 2021 |  |  | 3145.1113 |  | Salak | SLK - 2021 |  |  | 1275.0567 |  | Salak | SLK - 2021 |  |  | 8919 |  | Salak | SLK - 2021 |  |  | 22 |  | Darajat | DRJ - 2024 | DRJ-55 | 1150.6259 | 378.7203 | Salak | SLK - 2025 |  | 817.0858 | 308.2043 | -1 | 0.30148 | Salak | SLK - 2025 |  | 2.9393 | 0.60168 | 0.22585 | 0.51348 | 4.2803 | AWI 21-8
Darajat | DRJ - 2022 | DRJ-38RD | 882.1274 | 198.4199 | 1.1905 | Salak | SLK - 2025 |  |  | 38.5223 |  | Salak | SLK - 2025 |  |  | 9 |  | Salak | SLK - 2025 |  |  | 4.2803 |  | Salak | SLK - 2025 |  |  | 817.0858 |  | Salak | SLK - 2025 |  |  | 308.2043 |  | Salak | SLK - 2025 |  |  | 47146 |  | Salak | SLK - 2025 |  |  | 124.9896 |  | Darajat | DRJ - 2024 | DRJ-56 | 1456.8909 | 188.2194 | Wayang Windu | WW - 2018 |  | 1573.8613 | 190.6928 | -1.9262 | 0.18653 | Wayang Windu | WW - 2018 |  | 6.1998 | 0.26514 | 0.065259 | 0.21655 | 6.7467 | AWI 23-1
Darajat | DRJ - 2022 | DRJ-49OH |  |  | 1.3647 | Wayang Windu | WW - 2018 |  |  |  | 26.987 | Wayang Windu | WW - 2018 |  |  |  | 4 | Wayang Windu | WW - 2018 |  |  |  | 6.7467 | Wayang Windu | WW - 2018 |  |  |  | 1573.8613 | Wayang Windu | WW - 2018 |  |  |  | 190.6928 | Wayang Windu |  |  |  |  | 43546 | Wayang Windu | WW - 2018 |  |  |  | 141.5208 | Darajat | DRJ - 2024 | DRJ-57 | 1184.4684 | 376.9358 | Wayang Windu | WW - 2021 |  | 1025.607 | 245.3927 | -1.2552 | 0.24004 | Wayang Windu | WW - 2021 |  | 3.1609 | 0.77751 | 0.13804 | 0.43606 | 4.5125 | AWI 23-2
Darajat | DRJ - 2022 | DRJ-50OH |  |  | 1.2214 | Wayang Windu | WW - 2021 |  |  |  | 27.075 | Wayang Windu | WW - 2021 |  |  |  | 6 | Wayang Windu | WW - 2021 |  |  |  | 4.5125 | Wayang Windu | WW - 2021 |  |  |  | 1025.607 | Wayang Windu | WW - 2021 |  |  |  | 245.3927 | [6 empty] | Wayang Windu | WW - 2021 |  |  |  | 110.3333 | Salak | SLK - 2021 | AWI 9-10 | 643.4409 | 260.8568 | [15 empty] | AWI 2-6
Darajat | DRJ - 2022 | DRJ-51OH |  |  | 1.2478 | [42 empty] | Salak | SLK - 2025 | AWI 21-7 | 894.2315 | 275.623 | For Label $ft/norm |  |  |  |  | Denominator | [9 empty] | AWI 2-7 ML
Darajat | DRJ - 2022 | DRJ-52OH |  |  | 1.1095 | [42 empty] | Salak | SLK - 2025 | AWI 21-8 | 1116.7281 | 325.3892 | 9.9183 |  |  |  |  | $/ft | 817.0858 | [8 empty] | AWI 3-9
Darajat | DRJ - 2024 | DRJ-53 | 946.6748 | 270.231 | 1.2307 | [42 empty] | Salak | SLK - 2025 | AWI 23-1 | 691.2163 | 454.1528 | 5.5624 |  |  |  |  | $/day | 1022.3175 | [8 empty] | AWI 8-3
Darajat | DRJ - 2024 | DRJ-54 | 1285.8941 | 260.4924 | 1.5467 | [42 empty] | Salak | SLK - 2025 | AWI 23-2 | 703.9438 | 283.3374 | 1.4746 | [14 empty] | AWI 9-10
Darajat | DRJ - 2024 | DRJ-55 | 1150.6259 | 378.7203 | 1.3808 | [42 empty] | Salak | SLK - 2025 | AWI 2-6 | 669.3026 | 332.4186 | 3.8492 | [14 empty] | AWI 9-11
Darajat | DRJ - 2024 | DRJ-56 | 1456.8909 | 188.2194 | 1.894 | [42 empty] | Salak | SLK - 2025 | AWI 2-7 ML | 1102.7339 | 233.1434 | 1 | [14 empty] | DRJ-16
Darajat | DRJ - 2024 | DRJ-57 | 1184.4684 | 376.9358 | 1.4214 | [42 empty] | Salak | SLK - 2025 | AWI 3-9 | 911.0656 | 398.2141 | 1.9262 | [14 empty] | DRJ-37
Salak | SLK - 2021 | AWI 16-08 |  |  | 1.5186 | [42 empty] | Salak | SLK - 2025 | AWI 9-11 | 322.7351 | 128.1448 | 1.2552 | [14 empty] | DRJ-38
Salak | SLK - 2021 | AWI 16-09 |  |  | 1.0384 | [42 empty] | Wayang Windu | WW - 2018 | MBA-6 | 880.3348 | 185.1772 | [15 empty] | DRJ-38RD
Salak | SLK - 2021 | Awi 21-05 |  |  | 1.049 | [42 empty] | Wayang Windu | WW - 2018 | MBA-7 | 1001.0138 | 199.6332 | [15 empty] | DRJ-44
Salak | SLK - 2021 | Awi 21-06 |  |  | 0.85655 | [42 empty] | Wayang Windu | WW - 2018 | MBD-7 | 3135.6012 | 186.8218 | [15 empty] | DRJ-45
Salak | SLK - 2021 | AWI 9-10 | 643.4409 | 260.8568 | 1.1478 | [42 empty] | Wayang Windu | WW - 2018 | MBD-8 | 2349.6736 | 192.2302 | [15 empty] | DRJ-46
Salak | SLK - 2025 | AWI 21-7 | 894.2315 | 275.623 | 0.50276 | [42 empty] | Wayang Windu | WW - 2021 | MBE-6 | 864.7664 | 255.526 | [15 empty] | DRJ-47
Salak | SLK - 2025 | AWI 21-8 | 1116.7281 | 325.3892 | 0.50315 | [42 empty] | Wayang Windu | WW - 2021 | MBE-7 | 684.1948 | 200.5395 | [15 empty] | DRJ-48
Salak | SLK - 2025 | AWI 23-1 | 691.2163 | 454.1528 | 0.69122 | [42 empty] | Wayang Windu | WW - 2021 | MBI-1 | 755.9035 | 299.4763 | [15 empty] | DRJ-49
Salak | SLK - 2025 | AWI 23-2 | 703.9438 | 283.3374 | 0.62964 | [42 empty] | Wayang Windu | WW - 2021 | WWA-8 | 1264.9769 | 147.1965 | [15 empty] | DRJ-50
Salak | SLK - 2025 | AWI 2-6 | 669.3026 | 332.4186 | 0.40783 | [42 empty] | Wayang Windu | WW - 2021 | WWA-9 | 811.0449 | 286.4342 | [15 empty] | DRJ-51
Salak | SLK - 2025 | AWI 2-7 ML | 1102.7339 | 233.1434 | 0.67353 | [62 empty] | DRJ-52
Salak | SLK - 2025 | AWI 3-9 | 911.0656 | 398.2141 | 0.55676 | [62 empty] | DRJ-53
Salak | SLK - 2025 | AWI 9-10 RD |  |  | 0.15401 | [62 empty] | DRJ-54
Salak | SLK - 2025 | AWI 9-11 | 322.7351 | 128.1448 | 0.16137 | [62 empty] | DRJ-55
Wayang Windu | WW - 2018 | MBA-6 | 880.3348 | 185.1772 | 1.2615 | [62 empty] | DRJ-56
Wayang Windu | WW - 2018 | MBA-7 | 1001.0138 | 199.6332 | 1.2425 | [62 empty] | DRJ-57
Wayang Windu | WW - 2018 | MBD-7 | 3135.6012 | 186.8218 | 1.8108 | [62 empty] | HMD-A01
Wayang Windu | WW - 2018 | MBD-8 | 2349.6736 | 192.2302 | 2.4319 | [62 empty] | HMD-A02
Wayang Windu | WW - 2021 | MBD-8WO |  |  | 0.69469 | [62 empty] | MBA-6
Wayang Windu | WW - 2021 | MBE-6 | 864.7664 | 255.526 | 0.64857 | [62 empty] | MBA-7
Wayang Windu | WW - 2021 | MBE-7 | 684.1948 | 200.5395 | 0.80564 | [62 empty] | MBD-7
Wayang Windu | WW - 2021 | MBI-1 | 755.9035 | 299.4763 | 0.54488 | [62 empty] | MBD-8
Wayang Windu | WW - 2021 | WWA-8 | 1264.9769 | 147.1965 | 1.1096 | [62 empty] | MBE-6
Wayang Windu | WW - 2021 | WWA-9 | 811.0449 | 286.4342 | 0.70912 | [62 empty] | MBE-7
Grand Total |  |  | 1618.1402 | 390.8583 | 38.6109 | [62 empty] | MBI-1
WWA-8
WWA-9

## Piv.Struct.Cost
Sum of Actual Cost USD |  |  | Level 2 |  |  |  | Campaign | Well | Level 2 | Level 3 | Level 4 | Level 5 | Sum of Actual Cost USD
Asset | Campaign | Well | Contingency | Drilling Cost | Support Cost | Surface Facilities Cost | WW - 2018 | General | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | 4904.05
Darajat | DRJ - 2019 | DRJ-44OH |  | 4215619.74 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Material - LL | Casing | 0
Darajat | DRJ - 2019 | DRJ-45OH |  | 6556112 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | 0
Darajat | DRJ - 2019 | DRJ-46OH |  | 5969151.75 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | 0
Darajat | DRJ - 2019 | DRJ-47OH |  | 4803794.98 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | -228196.52
Darajat | DRJ - 2019 | DRJ-48 |  | 5579101.81 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | 0
Darajat | DRJ - 2019 | General |  | 4480219.5 | 2320438.57 | 8078945.81 | WW - 2018 | General | Drilling Cost | Well Cost | Services | Casing Installation | 0
Darajat | DRJ - 2022 | DRJ-38RD |  | 3912215.74 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | 0
Darajat | DRJ - 2022 | DRJ-49OH |  | 4782876.2 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Contract Rig | -557.92
Darajat | DRJ - 2022 | DRJ-50OH |  | 4066803.2 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | 0
Darajat | DRJ - 2022 | DRJ-51OH |  | 4198483.24 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | -116.55
Darajat | DRJ - 2022 | DRJ-52OH |  | 3507245.67 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Equipment Rental | 0
Darajat | DRJ - 2022 | General |  | 4562380.61 | 1945666.61 | 3693853.63 | WW - 2018 | General | Drilling Cost | Well Cost | Services | Land Transportation | -5927.89
Darajat | DRJ - 2024 | DRJ-53 |  | 3609573.61 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Mud Logging Service | -15683.35
Darajat | DRJ - 2024 | DRJ-54 |  | 5189554.63 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | 0
Darajat | DRJ - 2024 | DRJ-55 |  | 4359943.09 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | 0
Darajat | DRJ - 2024 | DRJ-56 |  | 6925978.21 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Other Transportation | 0
Darajat | DRJ - 2024 | DRJ-57 |  | 4562998.05 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Others | 1251014.26
Darajat | DRJ - 2024 | General |  | 5170158.38 | 1943104.28 | 5605799.39 | WW - 2018 | General | Drilling Cost | Well Cost | Services | Service Lines & Communication | 0
Salak | SLK - 2021 | AWI 16-08 |  | 5460023.53 |  |  | WW - 2018 | General | Drilling Cost | Well Cost | Services | Supervision | 0
Salak | SLK - 2021 | AWI 16-09 |  | 3058905.85 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | 12864.21
Salak | SLK - 2021 | Awi 21-05 |  | 3111812.78 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Material - LL | Casing | 395838.88
Salak | SLK - 2021 | Awi 21-06 |  | 2149748.71 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | 457313.66
Salak | SLK - 2021 | AWI 9-10 |  | 3605873.02 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | 133859.92
Salak | SLK - 2021 | General |  | 5584108.04 | 1383701.07 | 3697074.74 | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | 76817.64
Salak | SLK - 2025 | AWI 21-7 |  | 3183804.75 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | 103071.13
Salak | SLK - 2025 | AWI 21-8 |  | 3187325.84 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | -12705
Salak | SLK - 2025 | AWI 23-1 |  | 4879940.39 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Casing Installation | 75718.2
Salak | SLK - 2025 | AWI 23-2 |  | 4325740.79 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | 439716.99
Salak | SLK - 2025 | AWI 2-6 |  | 2329448.86 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Contract Rig | 1543621.9
Salak | SLK - 2025 | AWI 2-7 ML |  | 4720721.52 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | 334786.2
Salak | SLK - 2025 | AWI 3-9 |  | 3669854.19 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | 71177
Salak | SLK - 2025 | AWI 9-10 RD |  | 45127.74 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Equipment Rental | -141778.44
Salak | SLK - 2025 | AWI 9-11 |  | 111301.31 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Land Transportation | 117550.47
Salak | SLK - 2025 | General | 0 | 5415111.16 | 2032624.54 | 4621324.48 | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Mud Logging Service | 68207.7
Wayang Windu | WW - 2018 | General |  | 1060552.05 | 261037.06 | 866204.72 | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | 417750.09
Wayang Windu | WW - 2018 | MBA-6 |  | 4499130.51 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Other Transportation | 200544.73
Wayang Windu | WW - 2018 | MBA-7 |  | 4423085.22 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Others | 17890.25
Wayang Windu | WW - 2018 | MBD-7 |  | 6696290.24 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Service Lines & Communication | 1752.74
Wayang Windu | WW - 2018 | MBD-8 |  | 9180700.1 |  |  | WW - 2018 | MBA-6 | Drilling Cost | Well Cost | Services | Supervision | 185132.24
Wayang Windu | WW - 2021 | General |  | 4665082.42 | 774205.96 | 772274.8 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Material - LL | Casing | 325171.97
Wayang Windu | WW - 2021 | MBD-8WO |  | 2816506.28 | 5802.67 | 181230.63 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | 217969.05
Wayang Windu | WW - 2021 | MBE-6 |  | 2539839.79 | 17944.21 | 364171.44 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | 73907.16
Wayang Windu | WW - 2021 | MBE-7 |  | 3482227.67 | 21184.52 | 390996.51 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | 129993.89
Wayang Windu | WW - 2021 | MBI-1 |  | 1917673.74 | 3034.21 | 297255.68 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | 88611
Wayang Windu | WW - 2021 | WWA-8 |  | 5305964.61 | 3034.21 | 237021.95 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Casing Installation | 76816.73
Wayang Windu | WW - 2021 | WWA-9 |  | 2903132.66 | 3034.21 | 373380.02 | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | 402650.92
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Contract Rig | 1455536.41
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | 341813.33
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | 66339.49
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Equipment Rental | 329171.23
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Land Transportation | 76205.36
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Mud Logging Service | 61220.32
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | 688367.79
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | 0
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Other Transportation | 7081.19
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Service Lines & Communication | 1785.73
[7 empty] | WW - 2018 | MBA-7 | Drilling Cost | Well Cost | Services | Supervision | 80443.65
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Material - LL | Casing | 299595.79
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | 397730.2
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | 57089.09
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | 131706.28
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | 84413
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Casing Installation | 55441.94
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | 450613.83
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Contract Rig | 1675768.33
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | 416441.82
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | 94771.95
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Equipment Rental | 829062.51
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Land Transportation | 150677.1
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Mud Logging Service | 88856.75
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | 1827224.33
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | 0
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Other Transportation | 7103.95
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Service Lines & Communication | 2140.73
[7 empty] | WW - 2018 | MBD-7 | Drilling Cost | Well Cost | Services | Supervision | 127652.64
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Material - LL | Casing | 304089.61
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | 432393.83
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | 64532.62
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | 152464.29
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | 76948.75
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Casing Installation | 75380.46
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | 644909.26
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Contract Rig | 2358033.98
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | 1977239.44
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | 93867.15
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Equipment Rental | 626075.37
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Land Transportation | 185244.79
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Mud Logging Service | 104010.01
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | 1762720.88
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | 154684.52
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Other Transportation | 14360.42
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Service Lines & Communication | 2421.73
[7 empty] | WW - 2018 | MBD-8 | Drilling Cost | Well Cost | Services | Supervision | 151322.99

## Structured.Cost
# | Asset | Campaign | Level 2 | Level 3 | Level 4 | Level 5 | Well | Actual Cost USD
1 | Wayang Windu | WW - 2018 | Drilling Cost | LIH | LIH | LIH | General | -105457.27
2 | Wayang Windu | WW - 2018 | Drilling Cost | Logging Cost | Logging Cost | Logging Cost | General | 160573.24
3 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | General | 0
4 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-6 | 11935.55
5 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-7 | 325171.97
6 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-7 | 299595.79
7 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-8 | 304089.61
8 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | -149146.03
9 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBA-6 | 133859.92
10 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBA-7 | 217969.05
11 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-7 | 397730.2
12 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-8 | 432393.83
13 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | General | 0
14 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-6 | -321.15
15 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-7 | 73907.16
16 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBD-7 | 57089.09
17 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBD-8 | 64532.62
18 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | General | -228196.52
19 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBA-6 | 103071.13
20 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBA-7 | 129993.89
21 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBD-7 | 131706.28
22 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBD-8 | 152464.29
23 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | General | 0
24 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-6 | -45705
25 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-7 | 88611
26 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-7 | 84413
27 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-8 | 76948.75
28 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | General | -10421.91
29 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-6 | 2844.22
30 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-7 | 76816.73
31 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-7 | 55441.94
32 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-8 | 75380.46
33 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | -174558.94
34 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-6 | -26298.11
35 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-7 | 402650.92
36 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-7 | 450613.83
37 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-8 | 644909.26
38 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | General | -1867545.5
39 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-6 | 566893.34
40 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-7 | 1455536.41
41 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-7 | 1675768.33
42 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-8 | 2358033.98
43 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | General | 0
44 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-6 | -141925.8
45 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-7 | 341813.33
46 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-7 | 416441.82
47 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-8 | 1977239.44
48 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | -16482.32
49 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-6 | 39109.49
50 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-7 | 66339.49
51 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-7 | 94771.95
52 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-8 | 93867.15
53 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | General | 0
54 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBA-6 | -141778.44
55 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBA-7 | 329171.23
56 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBD-7 | 829062.51
57 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBD-8 | 626075.37
58 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | General | -38611.47
59 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-6 | 10230.16
60 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-7 | 76205.36
61 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-7 | 150677.1
62 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-8 | 185244.79
63 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | -32083.35
64 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-6 | -5105.34
65 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-7 | 61220.32
66 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-7 | 88856.75
67 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-8 | 104010.01
68 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | General | 0
69 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-6 | -668928.96
70 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-7 | 688367.79
71 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-7 | 1827224.33
72 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-8 | 1762720.88
73 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | General | 0
74 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBA-7 | 0
75 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBD-7 | 0
76 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBD-8 | 154684.52
77 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | General | -16983.19
78 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 11550.1
79 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-7 | 7081.19
80 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-7 | 7103.95
81 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-8 | 14360.42
82 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | -3010.93
83 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-6 | -247.26
84 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-7 | 1785.73
85 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-7 | 2140.73
86 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-8 | 2421.73
87 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | General | -111731.14
88 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-6 | 116332.5
89 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-7 | 80443.65
90 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBD-7 | 127652.64
91 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBD-8 | 151322.99
92 | Wayang Windu | WW - 2018 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 112.34
93 | Wayang Windu | WW - 2018 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 71133.41
94 | Wayang Windu | WW - 2018 | Support Cost | Permitting (IPPKH/IPJLPB) | Hardware Supply | Permitting | General | 0
95 | Wayang Windu | WW - 2018 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 72283.43
96 | Wayang Windu | WW - 2018 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 117507.88
97 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 0
98 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Tie-in | Procurement | Installation, Hook Up & Pre-Commisioning | General | 552424.06
99 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 313780.66
100 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-6 | 383903.33
101 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-6 | 77138.79
102 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-6 | 2000
103 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | MBA-6 | 12864.21
104 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-6 | 976728.56
105 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-6 | 1086679.05
106 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-6 | 33000
107 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBA-6 | 457313.66
108 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-6 | 476712
109 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-6 | 72873.98
110 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-6 | 466015.1
111 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-6 | 73313.04
112 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-6 | 68799.74
113 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-6 | 107320.31
114 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 5871.45
115 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 183123.18
116 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-6 | 32067.51
117 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | MBA-6 | 10359.49
118 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | MBA-6 | 7530.76
119 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 476192.46
120 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | 3010.93
121 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | General | 4904.05
122 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | General | 1866987.58
123 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | General | 10421.91
124 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | 174558.94
125 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | 16400
126 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | General | 111731.14
127 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | General | 32683.58
128 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | General | 16983.19
129 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | 149146.03
130 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 69.37
131 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | 16365.77
132 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 175153.08
133 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 580963.37
134 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 18635.98
136 | Darajat | DRJ - 2019 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 3136274.38 |  | D
137 | Darajat | DRJ - 2019 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1337803.55 | 4474077.93 | D
138 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-44OH | 367853.72
139 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-45OH | 571988.4
140 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-46OH | 532507.52
141 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-47OH | 454605.79
142 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-48 | 359868.91
143 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-44OH | 370208.79
144 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-45OH | 862920.21
145 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-46OH | 567110.31
146 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-47OH | 428314.23
147 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-48 | 332831.74
148 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-44OH | 318467.05
149 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-45OH | 580748.72
150 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-46OH | 368892.76
151 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-47OH | 298311.87
152 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-48 | 281753.9
153 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-44OH | 42261.87
154 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-45OH | 46684.52
155 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-46OH | 44139.04
156 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-47OH | 43094.75
157 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-48 | 43465.68
158 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-44OH | 135360
159 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-45OH | 321941.79
160 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-46OH | 168825.17
161 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-47OH | 105736.8
162 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-48 | 128882.5
163 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-44OH | 53399.65
164 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-45OH | 147905.11
165 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-46OH | 22398.73
166 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-47OH | 43200.12
167 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-48 | 111988.49
168 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-44OH | 395083.1
169 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-45OH | 929785.71
170 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-46OH | 808531.89
171 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-47OH | 567957.4
172 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-48 | 418783.86
173 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-44OH | 1319224
174 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-45OH | 2233613.7
175 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-46OH | 1308448.96
176 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-47OH | 1045526.44
177 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-48 | 728159.42
178 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-44OH | 358007.9
179 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-46OH | 624076.94
180 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-47OH | 756550.79
181 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-48 | 1096259.06
182 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-44OH | 41904.02
183 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-45OH | 128749.16
184 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-46OH | 75023.2
185 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-47OH | 57579.6
186 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-48 | 29319.96
187 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-44OH | 93305.44
188 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-45OH | 225633.72
189 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-46OH | 130265.36
190 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-47OH | 100633.48
191 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-48 | 170960.95
192 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-44OH | 35453.82
193 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-45OH | 84843.99
194 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-46OH | 50328.8
195 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-47OH | 37982.98
196 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-48 | 30672.16
197 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-44OH | 401556.19
198 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-46OH | 824197.43
199 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-47OH | 626372.53
200 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-48 | 1445756.12
201 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-48 | 109856.93
202 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-44OH | 171589.2
203 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-45OH | 204629.65
204 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-46OH | 326157.76
205 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-47OH | 135804.1
206 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-48 | 193295.66
207 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | General | 6141.57
208 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-44OH | 1142
209 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-46OH | 1582
210 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-47OH | 1156
211 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-48 | 3575
212 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-44OH | 110802.99
213 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-45OH | 216667.32
214 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-46OH | 116665.88
215 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-47OH | 100968.1
216 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-48 | 93671.47
217 | Darajat | DRJ - 2019 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 1009443.94
218 | Darajat | DRJ - 2019 | Support Cost | PGPA & Security | PGPA | PGPA | General | 602913.71
219 | Darajat | DRJ - 2019 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 232821.26
220 | Darajat | DRJ - 2019 | Support Cost | Well Testing | Well Testing | Well Testing | General | 333273.87
221 | Darajat | DRJ - 2019 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 141985.79
222 | Darajat | DRJ - 2019 | Surface Facilities Cost | Conductor Casing Installation & Material | Services | Service | General | 570474.38
223 | Darajat | DRJ - 2019 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 1183965.08
224 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 2589388.68
225 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 3295100.56
226 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 440017.11
227 | Wayang Windu | WW - 2021 | Drilling Cost | Explosive | Explosive | Explosive | General | 129531.42
228 | Wayang Windu | WW - 2021 | Drilling Cost | LIH | LIH | LIH | General | 330865.54
229 | Wayang Windu | WW - 2021 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 3981170.51 |  | WW
230 | Wayang Windu | WW - 2021 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 201214.07 | 4182384.58 | WW
231 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-8WO | 72987.9
232 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBE-6 | 409317.86
233 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBE-7 | 593931.6
234 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBI-1 | 368289.74
235 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | WWA-8 | 513871.54
236 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | WWA-9 | 585870.55
237 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBD-8WO | 533496.04
238 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBE-6 | 231136.99
239 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBE-7 | 344832.62
240 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBI-1 | 179334.32
241 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | WWA-8 | 762026.33
242 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | WWA-9 | 270273.02
243 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-8WO | 200286.6
244 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBE-6 | 169951.07
245 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBE-7 | 91084.43
246 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBI-1 | 88905.15
247 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | WWA-8 | 226206.2
248 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | WWA-9 | 218216.73
249 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBE-6 | 80177.45
250 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBE-7 | 64124.49
251 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBI-1 | 66560.99
252 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | WWA-8 | 56105.44
253 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | WWA-9 | 52653.32
254 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-8WO | 15385.86
255 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBE-6 | 71817.63
256 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBE-7 | 110547.29
257 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBI-1 | 90817.65
258 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | WWA-8 | 171407.29
259 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | WWA-9 | 110547.28
260 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-8WO | 55337.05
261 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBE-6 | 55253.68
262 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBE-7 | 100305.64
263 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBI-1 | 55580.6
264 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | WWA-8 | 53894.8
265 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | WWA-9 | 72409.5
266 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-8WO | 187723.47
267 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBE-6 | 276242.39
268 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBE-7 | 400466.91
269 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBI-1 | 236423.66
270 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | WWA-8 | 532362.28
271 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | WWA-9 | 305944.7
272 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-8WO | 880156.96
273 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBE-6 | 436456.53
274 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBE-7 | 680370.68
275 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBI-1 | 348332.76
276 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | WWA-8 | 1229036.48
277 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | WWA-9 | 518644.75
278 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-8WO | 315268.62
279 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBE-6 | 239924.36
280 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBE-7 | 324820.26
281 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBI-1 | 208122.09
282 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | WWA-8 | 706179.17
283 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | WWA-9 | 265095.09
284 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-8WO | 12392.45
285 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBE-6 | 6832.05
286 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBE-7 | 10737.34
287 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBI-1 | 5366
288 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | WWA-8 | 18858.51
289 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | WWA-9 | 7931.09
290 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-8WO | 68781.39
291 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBE-6 | 46472.28
292 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBE-7 | 54339.75
293 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBI-1 | 23515.42
294 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | WWA-8 | 114753.8
295 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | WWA-9 | 56610.35
296 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-8WO | 24494.27
297 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBE-6 | 11480
298 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBE-7 | 548.81
299 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBI-1 | 15831.29
300 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | WWA-8 | 59638.95
301 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | WWA-9 | 24464.01
302 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-8WO | 277995.3
303 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBE-6 | 277107.12
304 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBE-7 | 404978.12
305 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBI-1 | 71653.58
306 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | WWA-8 | 493805.9
307 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | WWA-9 | 179630.72
308 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBE-6 | 29400
309 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBE-7 | 41823.45
310 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | General | 22300.88
311 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-8WO | 3095.42
312 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBE-6 | 4562.38
313 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBE-7 | 4428.19
314 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBD-8WO | 84302.59
315 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBE-6 | 145881.28
316 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBE-7 | 178521.37
317 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBI-1 | 112596.93
318 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | WWA-8 | 241638.46
319 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | WWA-9 | 180531.16
320 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-8WO | 941
321 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBE-6 | 1115
322 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBE-7 | 3429.54
323 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBI-1 | 363
324 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | WWA-8 | 900
325 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | WWA-9 | 615
326 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBD-8WO | 83861.36
327 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBE-6 | 46711.72
328 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBE-7 | 72937.18
329 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBI-1 | 45980.56
330 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | WWA-8 | 125279.46
331 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | WWA-9 | 53695.39
332 | Wayang Windu | WW - 2021 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 129437.17
333 | Wayang Windu | WW - 2021 | Support Cost | IT & Communication | Drilling Facilities Support | Hardware Supply | General | 15984.04
334 | Wayang Windu | WW - 2021 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 18015.03
335 | Wayang Windu | WW - 2021 | Support Cost | PGPA & Security | PGPA | PGPA | General | 4156.68
336 | Wayang Windu | WW - 2021 | Support Cost | PGPA & Security | Security | Security | General | 65091.26
337 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 36778.03
338 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBD-8WO | 5802.67
339 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBE-6 | 17944.21
340 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBE-7 | 21184.52
341 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBI-1 | 3034.21
342 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | WWA-8 | 3034.21
343 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | WWA-9 | 3034.21
344 | Wayang Windu | WW - 2021 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 135591.23
345 | Wayang Windu | WW - 2021 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 8336.88
346 | Wayang Windu | WW - 2021 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 16051.55
347 | Wayang Windu | WW - 2021 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 271686
348 | Wayang Windu | WW - 2021 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 73078.09
349 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | MBE-6 | 113533.87
350 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | MBE-7 | 131575.61
351 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | WWA-8 | 103755.9
352 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | WWA-9 | 101119.67
353 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 339765.29
354 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBD-8WO | 43316.39
355 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBE-6 | 40570.57
356 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBE-7 | 32466.06
357 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBI-1 | 24941.43
358 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | WWA-8 | 11509.15
359 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | WWA-9 | 24870.39
360 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 160032.47
361 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBD-8WO | 127823.74
362 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBE-6 | 150242.22
363 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBE-7 | 163175.01
364 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBI-1 | 151195.77
365 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | WWA-8 | 30995.67
366 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | WWA-9 | 145307.49
367 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 4339.44
368 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | WWA-8 | 6424.63
369 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | WWA-9 | 6424.61
370 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 208653.62
371 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBD-8WO | 10090.5
372 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBE-6 | 47330.47
373 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBE-7 | 52316.65
374 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBI-1 | 101977.03
375 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | WWA-8 | 72676.01
376 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | WWA-9 | 83379.7
377 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 59483.98
378 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBE-6 | 12494.31
379 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBE-7 | 11463.18
380 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBI-1 | 19141.45
381 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | WWA-8 | 11660.59
382 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | WWA-9 | 12278.16
383 | Salak | SLK - 2021 | Drilling Cost | LIH | LIH | LIH | General | 1531986.77
384 | Salak | SLK - 2021 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2089596.15 |  | S
385 | Salak | SLK - 2021 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1721630.85 |  | S
386 | Salak | SLK - 2021 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 240894.27 | 4052121.27 | S
387 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 16-08 | 425099.43
388 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 16-09 | 402339.51
389 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | Awi 21-05 | 472745.02
390 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | Awi 21-06 | 356852.49
391 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-10 | 527713.81
392 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 16-08 | 467276.53
393 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 16-09 | 164541.09
394 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | Awi 21-05 | 215162.26
395 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | Awi 21-06 | 91365.62
396 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-10 | 267325.16
397 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Others | Awi 21-05 | 20805.02
398 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Others | AWI 9-10 | 4044.28
399 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 16-08 | 153306.91
400 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 16-09 | 138386.43
401 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | Awi 21-05 | 1777.1
402 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | Awi 21-06 | 1017.84
403 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-10 | 91686.64
404 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 16-08 | 152674
405 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 16-09 | 96387
406 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | Awi 21-05 | 107327
407 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | Awi 21-06 | 96387
408 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-10 | 96387
409 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 16-08 | 91320.71
410 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 16-09 | 73700.11
411 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | Awi 21-05 | 54026.09
412 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | Awi 21-06 | 54473.34
413 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-10 | 72940.53
414 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 16-08 | 901112.84
415 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 16-09 | 436221.84
416 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | Awi 21-05 | 337535.81
417 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | Awi 21-06 | 355841.12
418 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-10 | 480970.12
419 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 16-08 | 1120266.73
420 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 16-09 | 529448.46
421 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | Awi 21-05 | 610958.48
422 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | Awi 21-06 | 353180.05
423 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-10 | 625984.53
424 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 16-08 | 437427.53
425 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 16-09 | 224302.69
426 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | Awi 21-05 | 261948.12
427 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | Awi 21-06 | 166333.3
428 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-10 | 260085.35
429 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 16-08 | 18622.03
430 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 16-09 | 8683.85
431 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | Awi 21-05 | 9585.31
432 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-10 | 9709.76
433 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 16-08 | 488997.36
434 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 16-09 | 248812.25
435 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | Awi 21-05 | 459144.39
436 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | Awi 21-06 | 176541.56
437 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-10 | 304583.66
438 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 16-08 | 124815.55
439 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 16-09 | 37123.29
440 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | Awi 21-05 | 64079.18
441 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | Awi 21-06 | 479.69
442 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-10 | 59122.98
443 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 16-08 | 38542
444 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 16-09 | 18270
445 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | Awi 21-05 | 22062
446 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | Awi 21-06 | 12500
447 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-10 | 21991
448 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 16-08 | 553955.47
449 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 16-09 | 380369.19
450 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | Awi 21-05 | 215916.4
451 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | Awi 21-06 | 163342.31
452 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-10 | 389865.09
453 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 16-08 | 9633.44
454 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 16-09 | 13578.53
455 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | Awi 21-05 | 12218
456 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | Awi 21-06 | 13875.08
457 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-10 | 14359.78
458 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 16-08 | 339463.67
459 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 16-09 | 234866.72
460 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | Awi 21-05 | 181353.4
461 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | Awi 21-06 | 275766.02
462 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 9-10 | 321789.39
463 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 16-08 | 1000
464 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 16-09 | 608
465 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | Awi 21-05 | 662
466 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | Awi 21-06 | 416
467 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-10 | 1877.11
468 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 16-08 | 136509.33
469 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 16-09 | 51266.89
470 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | Awi 21-05 | 64507.2
471 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | Awi 21-06 | 31377.29
472 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-10 | 55436.83
473 | Salak | SLK - 2021 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Other | General | 73309.31
474 | Salak | SLK - 2021 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 115695.83
475 | Salak | SLK - 2021 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 194.66
476 | Salak | SLK - 2021 | Support Cost | PGPA & Security | PGPA & Security | Other | General | 4042.69
477 | Salak | SLK - 2021 | Support Cost | PGPA & Security | PGPA & Security | PGPA & Security | General | 106038.43
478 | Salak | SLK - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 56448.66
479 | Salak | SLK - 2021 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 296189.13
480 | Salak | SLK - 2021 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 1154.8
481 | Salak | SLK - 2021 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 14769.16
482 | Salak | SLK - 2021 | Support Cost | SHE | SHE Permit | Environment Permit | General | 5318.4
483 | Salak | SLK - 2021 | Support Cost | SHE | SHE Permit | Others | General | 143.34
484 | Salak | SLK - 2021 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 281675.05
485 | Salak | SLK - 2021 | Support Cost | Well Testing | Well Testing | Well Testing | General | 339981.58
486 | Salak | SLK - 2021 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 88740.03
487 | Salak | SLK - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Others | General | 73521.98
488 | Salak | SLK - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Service | Service | General | 844257.09
489 | Salak | SLK - 2021 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 703912.78
490 | Salak | SLK - 2021 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 15826.09
491 | Salak | SLK - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 102042.51
492 | Salak | SLK - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 894047.32
493 | Salak | SLK - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 1063466.97
494 | Darajat | DRJ - 2022 | Drilling Cost | Explosive | Explosive | Explosive | General | 119099.02
495 | Darajat | DRJ - 2022 | Drilling Cost | LIH | LIH | LIH | General | 0
496 | Darajat | DRJ - 2022 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2658145.82 |  | D
497 | Darajat | DRJ - 2022 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1615754.88 |  | D
498 | Darajat | DRJ - 2022 | Drilling Cost | Rig Skid | Skid Moving | Rig Skid | General | 169380.89 | 4443281.59 | D
499 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-38RD | 13514.56
500 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-49OH | 31535.17
501 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-50OH | 22400.72
502 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-51OH | 19432.99
503 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-52OH | 21580.53
504 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-38RD | 198087.95
505 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-49OH | 414603.22
506 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-50OH | 419472.97
507 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-51OH | 532953.13
508 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-52OH | 319725.93
509 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-38RD | 332119.15
510 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-49OH | 473986.83
511 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-50OH | 433704.53
512 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-51OH | 337680.73
513 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-52OH | 587193.81
514 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-38RD | 678.26
515 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-49OH | 52635.16
516 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-50OH | 67957.22
517 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-51OH | 51443.06
518 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-52OH | 55296.04
519 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-38RD | 7653.56
520 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-49OH | 26370.44
521 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-50OH | 26370.44
522 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-51OH | 26370.44
523 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-52OH | 26370.44
524 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-38RD | 53020.16
525 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-49OH | 88305.13
526 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-50OH | 78769.12
527 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-51OH | 54349.72
528 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-52OH | 55784.64
529 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-38RD | 60128
530 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-49OH | 231601
531 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-50OH | 151482.5
532 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-51OH | 120098.5
533 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-52OH | 105762.5
534 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-38RD | 34670.49
535 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-49OH | 66375.81
536 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-50OH | 53644.74
537 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-51OH | 51885.17
538 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-52OH | 67979.2
539 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-38RD | 431610.05
540 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-49OH | 728386.4
541 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-50OH | 415221.41
542 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-51OH | 634852.06
543 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-52OH | 476892.74
544 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-38RD | 867517.38
545 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-49OH | 1033044.74
546 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-50OH | 838855.14
547 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-51OH | 821879
548 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-52OH | 577880
549 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-38RD | 0
550 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-49OH | 0
551 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-50OH | 0
552 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-51OH | 0
553 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-52OH | 0
554 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-38RD | 348618.99
555 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-49OH | 426500.84
556 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-50OH | 415437.95
557 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-51OH | 401366.06
558 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-52OH | 271966.42
559 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-38RD | 13026.14
560 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-49OH | 15440.29
561 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-50OH | 12880.89
562 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-51OH | 0
563 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-52OH | 8354.05
564 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-38RD | 798979.46
565 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-49OH | 430103.37
566 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-50OH | 475803.33
567 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-51OH | 438722.44
568 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-52OH | 269816.43
569 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-38RD | 36907.27
570 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-49OH | 40807.21
571 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-50OH | 41017.02
572 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-51OH | 40772.11
573 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-52OH | 51925.49
574 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-38RD | 78091.96
575 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-49OH | 89256.93
576 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-50OH | 66927.07
577 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-51OH | 74087.43
578 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-52OH | 80498.53
579 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-38RD | 30000
580 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-49OH | 34905
581 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-50OH | 29229
582 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-51OH | 29312
583 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-52OH | 67575
584 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-38RD | 319451.08
585 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-49OH | 443856.33
586 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-50OH | 305156.59
587 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-51OH | 369513.61
588 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-52OH | 345656.38
589 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-38RD | 56043.99
590 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-49OH | 33042.43
591 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-50OH | 62912.89
592 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-51OH | 14136.94
593 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-52OH | 32029.56
594 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-38RD | 127992
595 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-49OH | 0
596 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-50OH | 35818.98
597 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-51OH | 64482.04
598 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-52OH | 0
599 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-38RD | 0
600 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-49OH | 12170.25
601 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-50OH | 16468.12
602 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-51OH | 20360.22
603 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-52OH | 16329.48
604 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-38RD | 0
605 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-49OH | 0
606 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-50OH | 0
607 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-51OH | 0
608 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-52OH | 0
609 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-38RD | 999
610 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-49OH | 1311
611 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-50OH | 974
612 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-51OH | 980
613 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-52OH | 679
614 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-38RD | 90519.15
615 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-49OH | 92633.31
616 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-50OH | 85446.68
617 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-51OH | 86100.33
618 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-52OH | 60329.68
619 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-38RD | 173.86
620 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-49OH | 0
621 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-50OH | 0
622 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-51OH | 0
623 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-52OH | 0
624 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-38RD | 12413.28
625 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-49OH | 16005.34
626 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-50OH | 10851.89
627 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-51OH | 7705.26
628 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-52OH | 7619.82
629 | Darajat | DRJ - 2022 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 111242.84
630 | Darajat | DRJ - 2022 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 383588.08
631 | Darajat | DRJ - 2022 | Support Cost | IT & Communication | Hardware Supply | Hardware Supply | General | 5049.74
632 | Darajat | DRJ - 2022 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 0
633 | Darajat | DRJ - 2022 | Support Cost | PGPA & Security | PGPA | PGPA | General | 32221.37
634 | Darajat | DRJ - 2022 | Support Cost | PGPA & Security | Security | Security | General | 29263.28
635 | Darajat | DRJ - 2022 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 14086.9
636 | Darajat | DRJ - 2022 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 431181.96
637 | Darajat | DRJ - 2022 | Support Cost | SHE | Drill Cutting | Heavy Equipment for Drill Cutting | General | 55128.71
638 | Darajat | DRJ - 2022 | Support Cost | SHE | Environmental Monitoring | Environmental Monitoring | General | 11182
639 | Darajat | DRJ - 2022 | Support Cost | SHE | Environmental Monitoring | IPAL | General | 0
640 | Darajat | DRJ - 2022 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 74043.23
641 | Darajat | DRJ - 2022 | Support Cost | SHE | SHE Permit | Andalalin | General | 0
642 | Darajat | DRJ - 2022 | Support Cost | SHE | SHE Permit | Environment Permit | General | 18968.04
643 | Darajat | DRJ - 2022 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 298156.75
644 | Darajat | DRJ - 2022 | Support Cost | Well Testing | Well Testing | Well Testing | General | 397045.52
645 | Darajat | DRJ - 2022 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 84508.19
646 | Darajat | DRJ - 2022 | Surface Facilities Cost | Conductor Casing Installation & Material | Material | Material | General | 361333.57
647 | Darajat | DRJ - 2022 | Surface Facilities Cost | Conductor Casing Installation & Material | Services | Service | General | 610128.96
648 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 784372.53
649 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 11467.04
650 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 0
651 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Procurement | Material - Non LL | General | 62393.78
652 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 217964.53
653 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 0
654 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - LL | General | 60098.57
655 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - Non LL | General | 49110.91
656 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 801479.81
657 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 33004.1
658 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 18900.82
659 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 683599.01
660 | Darajat | DRJ - 2024 | Drilling Cost | Explosive | Explosive | Explosive | General | 22676.26
661 | Darajat | DRJ - 2024 | Drilling Cost | LIH | LIH | LIH | General | 0
662 | Darajat | DRJ - 2024 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 3485865.57
663 | Darajat | DRJ - 2024 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1557867.01
664 | Darajat | DRJ - 2024 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 103749.54 | 5147482.12 | D
665 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-53 | 6771.23
666 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-54 | 0
667 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-55 | 0
668 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-56 | 0
669 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-57 | 6042.02
670 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | General | 0
671 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-53 | 51344.18
672 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-54 | 555950.62
673 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-55 | 889177.81
674 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-56 | 710970.27
675 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-57 | 892680.61
676 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | General | 0
677 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-53 | 0
678 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-54 | 212268.85
679 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-55 | 0
680 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-56 | 0
681 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-57 | 0
682 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | General | 0
683 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-53 | 0
684 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-54 | 79581.86
685 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-55 | 81369.12
686 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-56 | 78767.68
687 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-57 | 81618.21
688 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | General | 0
689 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-53 | 179613.75
690 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-54 | 491709.18
691 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-55 | 312598.37
692 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-56 | 432977.03
693 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-57 | 560934.25
694 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | 0
695 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-53 | 14897.57
696 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-54 | 17937.45
697 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-55 | 21260.21
698 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-56 | 19820.82
699 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-57 | 12009.27
700 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | General | 0
701 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-53 | 58943.01
702 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-54 | 45923.6
703 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-55 | 41026.32
704 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-56 | 56654.67
705 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-57 | 41595.77
706 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | General | 0
707 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-53 | 247456
708 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-54 | 116360
709 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-55 | 258054
710 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-56 | 272200
711 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-57 | 263648
712 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | General | 0
713 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-53 | 50444.7
714 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-54 | 67671.8
715 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-55 | 66983.46
716 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-56 | 89528.22
717 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-57 | 52451.98
718 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | General | 0
719 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-53 | 462888.41
720 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-54 | 472474.63
721 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-55 | 531994.69
722 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-56 | 747394.5
723 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-57 | 542203.17
724 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | 0
725 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-53 | 970902.29
726 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-54 | 977166.3
727 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-55 | 783052.64
728 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-56 | 1174500.15
729 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-57 | 617565.9
730 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | General | 0
731 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-53 | 0
732 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-54 | 0
733 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-55 | 0
734 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-56 | 0
735 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-57 | 0
736 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | General | 0
737 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-53 | 282292.41
738 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-54 | 566232.97
739 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-55 | 270682.54
740 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-56 | 432060.8
741 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-57 | 282841.5
742 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | General | 0
743 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-53 | 10285.62
744 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-54 | 12486.36
745 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-55 | 7271.73
746 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-56 | 20712.73
747 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-57 | 7720.67
748 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | 0
749 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-53 | 318237.95
750 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-54 | 582091.74
751 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-55 | 475623.6
752 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-56 | 1167015.34
753 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-57 | 665835.97
754 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | General | 0
755 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-53 | 24972.38
756 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-54 | 10541.25
757 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-55 | 26590.89
758 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-56 | 20014.65
759 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-57 | 29044.52
760 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | General | 0
761 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-53 | 74275.07
762 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-54 | 38209.46
763 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-55 | 93130.32
764 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-56 | 108360.54
765 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-57 | 53406.26
766 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | General | 0
767 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-53 | 71350
768 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-54 | 70250
769 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-55 | 49750
770 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-56 | 110100
771 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-57 | 48700
772 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | 0
773 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-53 | 637251.5
774 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-54 | 444820.5
775 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-55 | 336707.5
776 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-56 | 697896.5
777 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-57 | 315167.5
778 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | General | 0
779 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-53 | 34146.57
780 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-54 | 40556.83
781 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-55 | 21811.64
782 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-56 | 61439.88
783 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-57 | 17509.14
784 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | General | 0
785 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-53 | 0
786 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-54 | 249600
787 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-55 | 0
788 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-56 | 571655.2
789 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-57 | 0
790 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | General | 0
791 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-53 | 0
792 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-54 | 18849.94
793 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-55 | 11385.84
794 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-56 | 15491.37
795 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-57 | 7701.69
796 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | General | 0
797 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-53 | 0
798 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-54 | 0
799 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-55 | 0
800 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-56 | 0
801 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-57 | 0
802 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | General | 0
803 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-53 | 1500
804 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-54 | 1500
805 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-55 | 1500
806 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-56 | 1500
807 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-57 | 1500
808 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | 0
809 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-53 | 100381.75
810 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-54 | 100847.09
811 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-55 | 68405.98
812 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-56 | 116299.85
813 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-57 | 53151.03
814 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | General | 0
815 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-53 | 0
816 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-54 | 0
817 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-55 | 0
818 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-56 | 0
819 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-57 | 0
820 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | General | 0
821 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-53 | 11619.22
822 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-54 | 16524.2
823 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-55 | 11566.43
824 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-56 | 20618.01
825 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-57 | 9670.59
826 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | General | 0
827 | Darajat | DRJ - 2024 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 188116.74
828 | Darajat | DRJ - 2024 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 132251.66
829 | Darajat | DRJ - 2024 | Support Cost | IT & Communication | Drilling Facilities Support | Hardware Supply | General | 20405.19
830 | Darajat | DRJ - 2024 | Support Cost | Permitting (IPPKH/IPJLPB) | Hardware Supply | Permitting | General | 156205.65
831 | Darajat | DRJ - 2024 | Support Cost | PGPA & Security | PGPA | PGPA | General | 82973.05
832 | Darajat | DRJ - 2024 | Support Cost | PGPA & Security | Security | Security | General | 37958.17
833 | Darajat | DRJ - 2024 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 443299.87
834 | Darajat | DRJ - 2024 | Support Cost | SHE | Drill Cutting | Heavy Equipment for Drill Cutting | General | 22092.53
835 | Darajat | DRJ - 2024 | Support Cost | SHE | Environmental Monitoring | Environmental Monitoring | General | 20422.64
836 | Darajat | DRJ - 2024 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 18729.87
837 | Darajat | DRJ - 2024 | Support Cost | SHE | SHE Permit | Environment Permit | General | 19289.67
838 | Darajat | DRJ - 2024 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 196078.03
839 | Darajat | DRJ - 2024 | Support Cost | Well Testing | Well Testing | Well Testing | General | 494955.41
840 | Darajat | DRJ - 2024 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 110325.8
841 | Darajat | DRJ - 2024 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Material | General | 579209.1
842 | Darajat | DRJ - 2024 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 810634.08
843 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 1514304.52
844 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 55525.52
845 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 0
846 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Procurement | Material - Non LL | General | 106778.84
847 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 122872.65
848 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 11687.08
849 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - LL | General | 465218.82
850 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - Non LL | General | 114836.25
851 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 908012.89
852 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 55781.32
853 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 266811.29
854 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 594127.03
855 | Salak | SLK - 2025 | Contingency | Contingency | Contingency | Contingency | General | 0
856 | Salak | SLK - 2025 | Drilling Cost | Explosive | Explosive | Explosive | General | 142754.25
857 | Salak | SLK - 2025 | Drilling Cost | LIH | LIH | LIH | General | 0
858 | Salak | SLK - 2025 | Drilling Cost | Logging Cost | Logging Cost | Logging Cost | General | 0
859 | Salak | SLK - 2025 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2472778.98 |  | S
860 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 985714.21 |  | S
861 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Services | Rig Move | General | 709217.51 |  | S
862 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Skid Moving | Rig Move | General | 830091.9 |  | S
863 | Salak | SLK - 2025 | Drilling Cost | Rig Skid | Skid Moving | Rig Skid | General | 274554.31 | 5272356.91 | S
864 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 21-7 | 0
865 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 21-8 | 0
866 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 23-1 | 0
867 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 23-2 | 0
868 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 2-6 | 0
869 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 2-7 ML | 0
870 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 3-9 | 0
871 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 9-10 RD | 0
872 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 9-11 | 0
873 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 21-7 | 429505.88
874 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 21-8 | 435335.47
875 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 23-1 | 1054232.96
876 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 23-2 | 965451.4
877 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 2-6 | 575229.74
878 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 2-7 ML | 725447.72
879 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 3-9 | 592905.89
880 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-10 RD | 16239.59
881 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-11 | 3831.42
882 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 21-7 | 38422.66
883 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 21-8 | 0
884 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 23-1 | 0
885 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 23-2 | 0
886 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 2-6 | 45349.48
887 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 2-7 ML | 33522.6
888 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 3-9 | 0
889 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 9-10 RD | 0
890 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 9-11 | 0
891 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 21-7 | 126062.42
892 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 21-8 | 100429.12
893 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 23-1 | 329002.18
894 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 23-2 | 199759.8
895 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 2-6 | 95453.76
896 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 2-7 ML | 295020.14
897 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 3-9 | 239039.65
898 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-10 RD | 0
899 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-11 | 32866.56
900 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 21-7 | 71550.58
901 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 21-8 | 71550.58
902 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 23-1 | 79719.94
903 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 23-2 | 76400.29
904 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 2-6 | 55714.09
905 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 2-7 ML | 111558.08
906 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 3-9 | 56322.38
907 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-10 RD | 0
908 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-11 | 0
909 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 21-7 | 13955.48
910 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 21-8 | 589.92
911 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 23-1 | 14250.42
912 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 23-2 | 576.42
913 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 2-6 | 26254.71
914 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 2-7 ML | 43003.2
915 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 3-9 | 6555.58
916 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 9-10 RD | 3627.98
917 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 9-11 | 27548.57
918 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 21-7 | 1072.77
919 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 21-8 | 42179.35
920 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 23-1 | 16080.49
921 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 23-2 | 34147.78
922 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 2-6 | 9498.84
923 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 2-7 ML | 13606.35
924 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 3-9 | 15034.32
925 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 9-10 RD | 6359.84
926 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 9-11 | 9621.15
927 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 21-7 | 94068
928 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 21-8 | 172456
929 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 23-1 | 226776
930 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 23-2 | 241956
931 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 2-6 | 226776
932 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 2-7 ML | 129276
933 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 3-9 | 76071
934 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-10 RD | 0
935 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-11 | 0
936 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 21-7 | 47835.3
937 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 21-8 | 48247.53
938 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 23-1 | 48609.99
939 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 23-2 | 65679.52
940 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 2-6 | 64407.34
941 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 2-7 ML | 80541.2
942 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 3-9 | 47547.44
943 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-10 RD | 0
944 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-11 | 0
945 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 21-7 | 439155.86
946 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 21-8 | 485092.21
947 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 23-1 | 687821.17
948 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 23-2 | 556572.63
949 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 2-6 | 257054.57
950 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 2-7 ML | 452778.44
951 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 3-9 | 484916.72
952 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-10 RD | 0
953 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-11 | 0
954 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 21-7 | 555095.7
955 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 21-8 | 337932.78
956 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 23-1 | 408535.21
957 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 23-2 | 441013.53
958 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 2-6 | 0
959 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 2-7 ML | 202739.53
960 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 3-9 | 586102.57
961 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-10 RD | 0
962 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-11 | 0
963 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 21-7 | 0
964 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 21-8 | 0
965 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 23-1 | 0
966 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 23-2 | 0
967 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 2-6 | 0
968 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 2-7 ML | 0
969 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 3-9 | 0
970 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 9-10 RD | 0
971 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 9-11 | 0
972 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 21-7 | 208104.94
973 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 21-8 | 276141.51
974 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 23-1 | 330360.01
975 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 23-2 | 305864.51
976 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 2-6 | 383225.5
977 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 2-7 ML | 539568.66
978 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 3-9 | 280036.51
979 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-10 RD | 0
980 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-11 | 17280
981 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 21-7 | 415673.72
982 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 21-8 | 395934.56
983 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 23-1 | 658713.31
984 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 23-2 | 535788.29
985 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 2-6 | 219911.21
986 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 2-7 ML | 636198.74
987 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 3-9 | 553353.44
988 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 9-10 RD | 0
989 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 9-11 | 0
990 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 21-7 | 6569.31
991 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 21-8 | 7386.96
992 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 23-1 | 9010.76
993 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 23-2 | 9851.29
994 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 2-6 | 4450.16
995 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 2-7 ML | 10083.5
996 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 3-9 | 6928.95
997 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-10 RD | 0
998 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-11 | 0
999 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 21-7 | 294408.35
1000 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 21-8 | 236707.6
1001 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 23-1 | 299466.1
1002 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 23-2 | 286869.75
1003 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 2-6 | 0
1004 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 2-7 ML | 569931.8
1005 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 3-9 | 251905.6
1006 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-10 RD | 0
1007 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-11 | 0
1008 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 21-7 | 6459.45
1009 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 21-8 | 5235.62
1010 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 23-1 | 9269.86
1011 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 23-2 | 5090.54
1012 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 2-6 | 7572.76
1013 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 2-7 ML | 14521.32
1014 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 3-9 | 5122.93
1015 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 9-10 RD | 3114.37
1016 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 9-11 | 4367.5
1017 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 21-7 | 33177.69
1018 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 21-8 | 138436.38
1019 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 23-1 | 127600.61
1020 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 23-2 | 74352.56
1021 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 2-6 | 58439.03
1022 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 2-7 ML | 211145.09
1023 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 3-9 | 112627.87
1024 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-10 RD | 15785.96
1025 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-11 | 15786.07
1026 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 21-7 | 49600
1027 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 21-8 | 31400
1028 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 23-1 | 42637.5
1029 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 23-2 | 45900
1030 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 2-6 | 23525
1031 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 2-7 ML | 53900
1032 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 3-9 | 43000
1033 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-10 RD | 0
1034 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-11 | 0
1035 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 21-7 | 299496
1036 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 21-8 | 297688.5
1037 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 23-1 | 254115
1038 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 23-2 | 410447
1039 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 2-6 | 218933
1040 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 2-7 ML | 330676
1041 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 3-9 | 258317
1042 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-10 RD | 0
1043 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-11 | 0
1044 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 21-7 | 12977.87
1045 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 21-8 | 32818.09
1046 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 23-1 | 17992.77
1047 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 23-2 | 12618.12
1048 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 2-6 | 11942.24
1049 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 2-7 ML | 27067.6
1050 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 3-9 | 19673.31
1051 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 9-10 RD | 0
1052 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 9-11 | 0.04
1053 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 21-7 | 0
1054 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 21-8 | 0
1055 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 23-1 | 199400
1056 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 23-2 | 0
1057 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 2-6 | 0
1058 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 2-7 ML | 183600
1059 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 3-9 | 0
1060 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 9-10 RD | 0
1061 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 9-11 | 0
1062 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 21-7 | 0
1063 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 21-8 | 0
1064 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 23-1 | 0
1065 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 23-2 | 0
1066 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 2-6 | 0
1067 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 2-7 ML | 0
1068 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 3-9 | 0
1069 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-10 RD | 0
1070 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-11 | 0
1071 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 21-7 | 0
1072 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 21-8 | 0
1073 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 23-1 | 0
1074 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 23-2 | 0
1075 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 2-6 | 0
1076 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 2-7 ML | 0
1077 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 3-9 | 0
1078 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 9-10 RD | 0
1079 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 9-11 | 0
1080 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 21-7 | 825
1081 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 21-8 | 795
1082 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 23-1 | 1050
1083 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 23-2 | 1095
1084 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 2-6 | 0
1085 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 2-7 ML | 1350
1086 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 3-9 | 850.5
1087 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-10 RD | 0
1088 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-11 | 0
1089 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 21-7 | 39787.77
1090 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 21-8 | 70968.66
1091 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 23-1 | 65296.11
1092 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 23-2 | 56306.36
1093 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 2-6 | 45711.43
1094 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 2-7 ML | 55185.55
1095 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 3-9 | 33542.53
1096 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-10 RD | 0
1097 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-11 | 0
1098 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 21-7 | 0
1099 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 21-8 | 0
1100 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 23-1 | 0
1101 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 23-2 | 0
1102 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 2-6 | 0
1103 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 2-7 ML | 0
1104 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 3-9 | 0
1105 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 9-10 RD | 0
1106 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 9-11 | 0
1107 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 21-7 | 0
1108 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 21-8 | 0
1109 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 23-1 | 0
1110 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 23-2 | 0
1111 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 2-6 | 0
1112 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 2-7 ML | 0
1113 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 3-9 | 0
1114 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 9-10 RD | 0
1115 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 9-11 | 0
1116 | Salak | SLK - 2025 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 475455.58
1117 | Salak | SLK - 2025 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 320332
1118 | Salak | SLK - 2025 | Support Cost | IT & Communication | Hardware Supply | Hardware Supply | General | 4000.06
1119 | Salak | SLK - 2025 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 5138.14
1120 | Salak | SLK - 2025 | Support Cost | PGPA & Security | PGPA | PGPA | General | 113196.24
1121 | Salak | SLK - 2025 | Support Cost | PGPA & Security | Security | Security | General | 23682.08
1122 | Salak | SLK - 2025 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 13129.99
1123 | Salak | SLK - 2025 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 373275.99
1124 | Salak | SLK - 2025 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 6855.03
1125 | Salak | SLK - 2025 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 951.75
1126 | Salak | SLK - 2025 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 131647.73
1127 | Salak | SLK - 2025 | Support Cost | Well Testing | Well Testing | Well Testing | General | 417018.49
1128 | Salak | SLK - 2025 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 147941.46
1129 | Salak | SLK - 2025 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Material | General | 677988.38
1130 | Salak | SLK - 2025 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 1165594.54
1131 | Salak | SLK - 2025 | Surface Facilities Cost | New Rig Pavement | Construction | New Rig Pavement | General | 0
1132 | Salak | SLK - 2025 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 737235.37
1133 | Salak | SLK - 2025 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 67334.7
1134 | Salak | SLK - 2025 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 0
1135 | Salak | SLK - 2025 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 43417.87
1136 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 377631.68
1137 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 292017.33
1138 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 1051404.93
1139 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 208699.68

## General.Camp.Data
No | Asset | Campaign | WBS CODE | Pad Name | Well Name Actual | Well Name SAP | Well Name Alt 1 | Well Name Alt 2 | ST Yes or No | Actual Depth Original, ft MD | Actual Depth Side Track, ft MD | Actual depth, ft MD | Spud Date | Drilling Duration, hrs | Drilling Duration, days equivalent | NPT hours | Target depth, ft MD | Target Depth, eq. m MD | Actual Depth, eq. m MD
1 | Wayang Windu | WW - 2018 | E500-2-0-8501-185003 | Pad MBA | MBA-6 | MBA-6 | MBA-6 | MBA-6 | No | 5732 | 0 | 5732 | 2018-11-27 14:30 | 654 | 27.25 | 0.5 | 5807 | 1769.9736 | 1747.1136
2 | Wayang Windu | WW - 2018 | E500-2-0-8501-185003 | Pad MBA | MBA-7 | MBA-7 | MBA-7 | MBA-7 | No | 4965 | 0 | 4965 | 2018-12-29 16:00 | 597.5 | 24.8958 | 36.75 | 5413 | 1649.8824 | 1513.332
3 | Wayang Windu | WW - 2018 | E500-2-0-8501-185003 | Pad MBD | MBD-7 | MBD-7 | MBD-7 | MBD-7 | No | 4997 | 0 | 4997 | 2019-02-09 17:30 | 214 | 38.7708 | 3 | 4997 | 1523.0856 | 1523.0856
4 | Wayang Windu | WW - 2018 | E500-2-0-8501-185003 | Pad MBD | MBD-8 | MBD-8 | MBD-8 | MBD-8 | Yes | 4083 | 4140 | 4140 | 2019-03-25 03:30 | 1214.5 | 50.6042 | 52.5 | 8202 | 2499.9696 | 1261.872
5 | Darajat | DRJ - 2019 | E530-30101-D19001 | Pad 20 | DRJ-48 | Well 20 02 | DRJ 20 NE | DRJ-48 | No | 5399.5 | 0 | 5399.5 | 2020-02-15 11:30 | 515.5 | 21.4792 | 1.25 | 5400 | 1645.92 | 1645.7676
6 | Darajat | DRJ - 2019 | E530-30101-D19001 | Pad S4 | DRJ-47 | Well S4 03 | DRJ S4 SW | DRJ-47 | No | 5902 | 0 | 5902 | 2019-12-27 16:00 | 600 | 25 | 3 | 5902 | 1798.9296 | 1798.9296
7 | Darajat | DRJ - 2019 | E530-30101-D19001 | Pad 20 | DRJ-44 | Well 20 01 | DRJ 20 WNW | DRJ-44 | No | 5860 | 0 | 5860 | 2019-06-24 15:00 | 598.5 | 24.9375 | 1 | 5979 | 1822.3992 | 1786.128
8 | Darajat | DRJ - 2019 | E530-30101-D19001 | Pad S4 | DRJ-45 | Well S4 01 | DRJ S4SSE | DRJ-45 | No | 5977 | 0 | 5977 | 2019-08-15 18:30 | 1567.25 | 65.3021 | 32 | 5977 | 1821.7896 | 1821.7896
9 | Darajat | DRJ - 2019 | E530-30101-D19001 | Pad S4 | DRJ-46 | Well S4 02 | DRJ S4S | DRJ-46 | No | 5836 | 0 | 5836 | 2019-11-06 22:30 | 976.5 | 40.6875 | 2 | 5735 | 1748.028 | 1778.8128
10 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad MBI | MBI-1 | MBI 1 | MBI 1 | MBI-1 | No | 4325 | 0 | 4325 | 2021-05-27 14:00 | 262 | 10.9167 | 0.5 | 4391 | 1338.3768 | 1318.26
11 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad WWA | WWA-9 | WWA 9 | WWA 9 | WWA-9 | No | 7158 | 0 | 7158 | 2021-03-03 22:00 | 356.5 | 14.8542 | 1.5 | 7191 | 2191.8168 | 2181.7584
12 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad WWA | WWA-8 | WWA 8 | WWA 8 | WWA-8 | No | 5263 | 0 | 5263 | 2021-03-25 | 1085.5 | 45.2292 | 20.25 | 7166 | 2184.1968 | 1604.1624
13 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad MBE | MBE-7 | MBE 07 | MBE 07 | MBE-7 | No | 7065 | 0 | 7065 | 2021-01-08 21:30 | 578.5 | 24.1042 | 7 | 7500 | 2286 | 2153.412
14 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad MBE | MBE-6 | MBE 06 | MBE 06 | MBE-6 | No | 4500 | 0 | 4500 | 2020-12-20 05:30 | 365.5 | 15.2292 | 3 | 4500 | 1371.6 | 1371.6
15 | Wayang Windu | WW - 2021 | E500-30101-D205011 | Pad MBD | MBD-8WO | MBD 8 WO | MBD 8 WO | MBD-8WO | [7 empty] | 0
16 | Salak | SLK - 2021 | E540-30101-D20001 | Pad 21 | AWI 21-6 | AWI 21-06 | AWI 21-06 | AWI 21-6 | No | 4918 | 0 | 4918 | 2021-08-01 12:00 | 214 | 8.9167 | 0 | 5021 | 1530.4008 | 1499.0064
17 | Salak | SLK - 2021 | E540-30101-D20001 | Pad 21 | AWI 21-5 | AWI 21-05 | AWI 21-05 | AWI 21-5 | No | 4685 | 0 | 4685 | 2021-07-07 21:30 | 529.5 | 22.0625 | 1.75 | 4846 | 1477.0608 | 1427.988
18 | Salak | SLK - 2021 | E540-30101-D20001 | Pad 16 | AWI 16-9 | AWI 16-09 | AWI 16-09 | AWI 16-9 | No | 5379 | 0 | 5379 | 2021-10-08 | 438.5 | 18.2708 | 0 | 5591 | 1704.1368 | 1639.5192
19 | Salak | SLK - 2021 | E540-30101-D20001 | Pad 16 | AWI 16-8 | AWI 16-08 | AWI 16-08 | AWI 16-8 | Yes | 4114 | 5000 | 5000 | 2021-08-27 03:00 | 414 | 17.25 | 2.75 | 5385 | 1641.348 | 1524
20 | Salak | SLK - 2021 | E540-30101-D20001 | Pad 9 | AWI 9-10 | AWI 9-10 | AWI 9-10 | AWI 9-10 | Yes | 8919 | 0 | 8919 | 2021-11-19 23:00 | 528 | 22 | 1 | 9263 | 2823.3624 | 2718.5112
21 | Darajat | DRJ - 2022 | E530-30101-D225301 | Pad 14 | DRJ-51 | DRJ 14-1 | DRJ 14-1 | DRJ-51 | No | 4993 | 0 | 4993 | 2022-06-06 08:30 | 706.5 | 29.4375 | 5 | 6200 | 1889.76 | 1521.8664
22 | Darajat | DRJ - 2022 | E530-30101-D225301 | Pad 14 | DRJ-52 | DRJ 14-2 | DRJ 14-2 | DRJ-52 | No | 5765 | 0 | 5765 | 2022-07-08 09:00 | 489 | 20.375 | 1.5 | 6000 | 1828.8 | 1757.172
23 | Darajat | DRJ - 2022 | E530-30101-D225301 | Pad 20 | DRJ-50 | DRJ 20-1 | DRJ 20-1 | DRJ-50 | No | 5749 | 0 | 5749 | 2022-04-23 06:30 | 701.5 | 29.2292 | 1.75 | 6300 | 1920.24 | 1752.2952
24 | Darajat | DRJ - 2022 | E530-30101-D225301 | Pad SF | DRJ-49 | DRJ SF-1 | DRJ SF-1 | DRJ-49 | No | 6310 | 0 | 6310 | 2022-03-06 11:00 | 840.5 | 35.0208 | 2 | 6300 | 1920.24 | 1923.288
25 | Darajat | DRJ - 2022 | E530-30101-D225301 | Pad SF | DRJ-38RD | DRJ SF-ML | DRJ SF-ML | DRJ-38RD | Yes | 8250.0003 | 6748 | 6748 | 2022-02-01 12:00 | 720 | 30 | 91.5 | 7000 | 2133.6 | 2056.7904
26 | Darajat | DRJ - 2024 | E530-30101-D235301 | Pad 15 | DRJ-53 | DRJ Steam 6 | DRJ Steam 6 | DRJ-53 | No | 6500 | 0 | 6500 | 2024-04-25 23:30 | 546.5 | 22.7708 | 3.5 | 6500 | 1981.2 | 1981.2
27 | Darajat | DRJ - 2024 | E530-30101-D235301 | Pad 18 | DRJ-54 | DRJ Steam 2 | DRJ Steam 2 | DRJ-54 | No | 6014 | 0 | 6014 | 2024-05-31 23:30 | 712.5 | 29.6875 | 166 | 6000 | 1828.8 | 1833.0672
28 | Darajat | DRJ - 2024 | E530-30101-D235301 | Pad 18 | DRJ-55 | DRJ Steam 3 | DRJ Steam 3 | DRJ-55 | No | 6000 | 0 | 6000 | 2024-07-03 19:30 | 437.5 | 18.2292 | 6.5 | 6000 | 1828.8 | 1828.8
29 | Darajat | DRJ - 2024 | E530-30101-D235301 | Pad 20 | DRJ-56 | DRJ Steam 4 | DRJ Steam 4 | DRJ-56 | No | 6500 | 0 | 6500 | 2024-08-02 23:30 | 1207.5 | 50.3125 | 2 | 6500 | 1981.2 | 1981.2
30 | Darajat | DRJ - 2024 | E530-30101-D235301 | Pad 20 | DRJ-57 | DRJ Steam 5 | DRJ Steam 5 | DRJ-57 | No | 6000 | 0 | 6000 | 2024-10-02 21:30 | 452.5 | 18.8542 | 0.5 | 6000 | 1828.8 | 1828.8
31 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 21 | AWI 21-8 | AWI 21-8 | AWI 21-8 | AWI 21-8 | No | 4055 | 0 | 4055 | 2025-07-08 15:30 | 334 | 13.9167 | 4.5 | 4000 | 1219.2 | 1235.964
32 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 21 | AWI 21-7 | AWI 21-7 | AWI 21-7 | AWI 21-7 | No | 5060 | 0 | 5060 | 2025-07-27 09:30 | 394 | 16.4167 | 2 | 5200 | 1584.96 | 1542.288
33 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 3 | AWI 3-9 | AWI 3-9 | AWI 3-9 | AWI 3-9 | No | 5500 | 0 | 5500 | 2025-09-10 10:30 | 302 | 12.5833 | 3.5 | 5500 | 1676.4 | 1676.4
34 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 23 | AWI 23-1 | AWI 23-1 | AWI 23-1 | AWI 23-1 | No | 9000 | 0 | 9000 | 2025-10-18 10:00 | 328.75 | 13.6979 | 1 | 9000 | 2743.2 | 2743.2
35 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 23 | AWI 23-2 | AWI 23-2 | AWI 23-2 | AWI 23-2 | No | 8050 | 0 | 8050 | 2025-11-11 17:30 | 480 | 20 | 0.5 | 9000 | 2743.2 | 2453.64
36 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 2 | AWI 2-7 ML | AWI 2-7 ML | AWI 2-7 ML | AWI 2-7 ML | No | 5497 | 0 | 5497 | 2025-12-23 18:30 | 624 | 26 | 1 | 5500 | 1676.4 | 1675.4856
37 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 2 | AWI 2-6 | AWI 2-6 | AWI 2-6 | AWI 2-6 | No | 5484 | 0 | 5484 | 2026-01-22 09:00 | 265 | 11.0417 | 11 | 5500 | 1676.4 | 1671.5232
38 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 9 | AWI 9-11 | AWI 9-11 | AWI 9-11 | AWI 9-11 | No | 9000 | 0 | 9000 | 2026-03-05 16:00 | 0 | 11.3333 | 3 | 9000 | 2743.2 | 2743.2
39 | Salak | SLK - 2025 | E540-30101-D245401 | Pad 9 | AWI 9-10 RD | AWI 9-10RD | AWI 9-10RD | AWI 9-10 RD | [7 empty] | 0

## NPT.Data
Non-Productive Time
# | Well Name | Job Cat Drill / Sidetrack / Well Service | Event Reference No. | Start Date | End Date | Unsch Maj Cat | Unscheduled Detail | Definition | Dur (Net) (hr) | Accountable Party | Service Contract | Campaign
1 | AWI 10-4 | Well Services | 1 | 2019-04-05 11:00 | 2019-04-05 13:00 | WO | PERSONNEL | Wait On - Personnel. | 2 | Operator | STAR
2 | AWI 10-4 | Drill and Complete | 3 | 2012-07-17 10:00 | 2012-07-19 11:00 | WO | HES | Wait On - HSE. Safety stand-downs, investigations. | 49 | Operator's Other Contractors | Kharisma Citatunggal
5 | AWI 10-4 | Drill and Complete | 4 | 2012-07-23 06:00 | 2012-08-03 16:00 | WO | REG PERMIT | Wait On - Regulations/Permits. | 274 | Operator | Chevron Geothermal Indonesia Ltd.
6 | AWI 10-4 | Drill and Complete | 5 | 2012-08-05 14:00 | 2012-08-10 17:00 | FSH | FSH ALL OH | Fishing Job | 123 | Operator's Other Contractors | Sperry Sun
7 | AWI 10-4 | Drill and Complete | 6 | 2012-08-12 01:30 | 2012-08-12 02:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 1 | Rig Contractor | Apexindo Duta Pratama, PT
8 | AWI 10-4 | Drill and Complete | 7 | 2012-08-12 10:00 | 2012-08-12 15:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 5 | Rig Contractor | Apexindo Duta Pratama, PT
9 | AWI 10-4 | Drill and Complete | 8 | 2012-08-15 18:30 | 2012-08-16 01:00 | WO | SUPPLIES | Wait On - Supplies. | 6.5 | Operator | Chevron Geothermal Indonesia Ltd.
10 | AWI 10-4 | Drill and Complete | 9 | 2012-08-16 21:00 | 2012-08-16 23:00 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 2 | Rig Contractor | Apexindo Duta Pratama, PT
12 | AWI 10-4 | Drill and Complete | 11 | 2012-08-25 08:00 | 2012-08-25 10:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | Apexindo Duta Pratama, PT
13 | AWI 16-08 | Drill and Complete | 1 | 2021-08-28 09:15 | 2021-08-28 12:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2.75 | Rig Contractor | PT. DATI
14 | AWI 16-08 | Drill and Complete | 2 | 2021-08-28 12:00 | 2021-08-28 16:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 4.5 | Rig Contractor | PT. DATI
15 | AWI 16-08 | Drill and Complete | 3 | 2021-08-28 16:30 | 2021-08-28 19:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2.5 | Rig Contractor | PT. DATI
16 | AWI 16-08 | Drill and Complete | 4 | 2021-08-31 06:30 | 2021-08-31 08:30 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 2 | Sub-Contractor | Schlumberger Anadrill
17 | AWI 16-08 | Drill and Complete | 5 | 2021-09-04 20:00 | 2021-09-04 20:30 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 0.5 | Rig Contractor | PT. DATI
18 | AWI 16-08 | Drill and Complete | 6 | 2021-09-28 09:15 | 2021-09-28 10:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Rig Contractor | PT. DATI
19 | AWI 16-08 | Drill and Complete | 7 | 2021-09-29 07:00 | 2021-09-29 07:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.5 | Rig Contractor | PT. DATI
20 | AWI 2-6 | Drill and Complete | 1 | 2026-01-30 01:00 | 2026-01-30 12:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 11 | Rig Contractor | STAR Energy Geothermal Drilling Services | SLK - 2025
21 | AWI 2-6 | Drill and Complete | 2 | 2026-01-31 03:30 | 2026-01-31 09:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 5.5 | Rig Contractor | STAR Energy Geothermal Drilling Services | SLK - 2025
22 | AWI 2-7 ML | Drill and Complete | 1 | 2025-12-25 05:00 | 2025-12-25 06:00 | RREQ | COMPTR | Rig Repair - Computers/Controls. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
23 | AWI 2-7 ML | Drill and Complete | 2 | 2025-12-26 03:00 | 2025-12-26 04:30 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 1.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
24 | AWI 2-7 ML | Drill and Complete | 3 | 2026-01-01 10:30 | 2026-01-03 20:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 57.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
25 | AWI 2-7 ML | Drill and Complete | 4 | 2026-01-06 03:30 | 2026-01-06 04:30 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
26 | AWI 2-7 ML | Drill and Complete | 5 | 2026-01-10 19:00 | 2026-01-10 20:00 | SW | TOOL FAIL | Stuck Wireline - Downhole tool failure. | 1 | Contractor | SLB | SLK - 2025
27 | AWI 2-7 ML | Drill and Complete | 6 | 2026-01-14 21:00 | 2026-01-14 22:30 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 1.5 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
28 | AWI 2-7 ML | Drill and Complete | 7 | 2026-01-15 21:00 | 2026-01-15 21:30 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
29 | AWI 21-05 | Drill and Complete | 1 | 2021-07-17 05:15 | 2021-07-17 07:00 | WO | EQP | Wait On - Equipment. | 1.75 | Contractor | Schlumberger
30 | AWI 21-05 | Drill and Complete | 2 | 2021-07-22 07:30 | 2021-07-22 09:30 | RREQ | EQP | Rig Repair - General Equipment. | 2 | Rig Contractor | PT. DATI
31 | AWI 21-05 | Drill and Complete | 3 | 2021-07-25 20:00 | 2021-07-25 20:15 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.25 | Rig Contractor | PT. DATI
32 | AWI 21-05 | Drill and Complete | 4 | 2021-07-26 06:45 | 2021-07-26 13:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 6.75 | Contractor | Air Drilling Associates Indonesia
33 | AWI 21-7 | Drill and Complete | 1 | 2025-07-30 10:30 | 2025-07-30 12:30 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 2 | Contractor | VARCO INDO | SLK - 2025
34 | AWI 21-7 | Drill and Complete | 2 | 2025-07-30 22:15 | 2025-07-30 22:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 0.25 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
35 | AWI 21-7 | Drill and Complete | 3 | 2025-08-03 15:30 | 2025-08-03 16:30 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 1 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
36 | AWI 21-7 | Drill and Complete | 4 | 2025-08-03 20:30 | 2025-08-03 20:45 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 0.25 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
37 | AWI 21-7 | Drill and Complete | 5 | 2025-08-03 21:15 | 2025-08-03 22:30 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 1.25 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
38 | AWI 21-7 | Drill and Complete | 6 | 2025-08-04 21:00 | 2025-08-04 22:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 1.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
39 | AWI 21-7 | Drill and Complete | 7 | 2025-08-05 01:00 | 2025-08-05 03:30 | RREQ | ROT | Rig Repair - Rotary Equipment. | 2.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
40 | AWI 21-7 | Drill and Complete | 8 | 2025-08-05 11:00 | 2025-08-05 11:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
41 | AWI 21-7 | Drill and Complete | 9 | 2025-08-06 08:30 | 2025-08-06 09:00 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 0.5 | Contractor | VARCO INDO | SLK - 2025
42 | AWI 21-7 | Drill and Complete | 10 | 2025-08-07 02:30 | 2025-08-07 03:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
43 | AWI 21-7 | Drill and Complete | 11 | 2025-08-07 11:00 | 2025-08-07 11:30 | PR | ERROR | Process - Human Error. Non-mechanical. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
44 | AWI 21-7 | Drill and Complete | 12 | 2025-08-07 20:30 | 2025-08-07 23:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 3 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
45 | AWI 21-7 | Drill and Complete | 13 | 2025-08-08 04:30 | 2025-08-08 05:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
46 | AWI 21-7 | Drill and Complete | 14 | 2025-08-08 | 2025-08-08 01:30 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 1.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
47 | AWI 21-7 | Drill and Complete | 15 | 2025-08-10 09:00 | 2025-08-10 09:30 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 0.5 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
48 | AWI 21-8 | Drill and Complete | 2 | 2025-07-11 01:30 | 2025-07-11 06:00 | EQPS | EL UNIT | Equipment - Surface E-line Unit. Excludes downhole tools. | 4.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
49 | AWI 21-8 | Drill and Complete | 3 | 2025-07-12 10:00 | 2025-07-12 14:00 | RREQ | COMPTR | Rig Repair - Computers/Controls. | 4 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
50 | AWI 21-8 | Drill and Complete | 4 | 2025-07-14 08:00 | 2025-07-14 08:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
51 | AWI 21-8 | Drill and Complete | 5 | 2025-07-15 02:00 | 2025-07-15 02:30 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
52 | AWI 21-8 | Drill and Complete | 6 | 2025-07-16 17:00 | 2025-07-16 18:00 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 1 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
53 | AWI 21-8 | Drill and Complete | 7 | 2025-07-18 15:00 | 2025-07-18 15:30 | RREQ | EQP | Rig Repair - General Equipment. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
54 | AWI 21-8 | Drill and Complete | 8 | 2025-07-18 16:00 | 2025-07-18 17:00 | WO | RIG | Wait On - Rig activities. | 1 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
55 | AWI 21-8 | Drill and Complete | 9 | 2025-07-18 01:30 | 2025-07-18 04:00 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 2.5 | Operator | STAR ENERGY GEOTHERMAL SALAK | SLK - 2025
56 | AWI 21-8 | Drill and Complete | 10 | 2025-07-20 01:30 | 2025-07-20 04:30 | RREQ | EQP | Rig Repair - General Equipment. | 3 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
57 | AWI 21-8 | Drill and Complete | 11 | 2025-07-21 09:30 | 2025-07-21 11:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 2 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
58 | AWI 21-8 | Drill and Complete | 12 | 2025-07-21 13:00 | 2025-07-21 13:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.5 | Contractor | ADA | SLK - 2025
59 | AWI 21-8 | Drill and Complete | 13 | 2025-07-23 06:30 | 2025-07-23 08:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 1.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
60 | AWI 23-1 | Drill and Complete | 1 | 2025-10-26 16:45 | 2025-10-26 17:45 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 1 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
61 | AWI 23-1 | Drill and Complete | 2 | 2025-10-27 20:15 | 2025-10-27 20:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
62 | AWI 23-1 | Drill and Complete | 3 | 2025-11-01 15:00 | 2025-11-01 16:45 | EQPS | PIPE HANDL | Equipment - Surface Pipe Handling. Third-party. | 1.75 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
63 | AWI 23-2 | Drill and Complete | 1 | 2025-11-13 17:30 | 2025-11-13 18:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
64 | AWI 23-2 | Drill and Complete | 2 | 2025-11-14 07:30 | 2025-11-14 08:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
65 | AWI 23-2 | Drill and Complete | 3 | 2025-11-14 12:30 | 2025-11-14 13:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
66 | AWI 23-2 | Drill and Complete | 4 | 2025-11-14 16:00 | 2025-11-14 16:15 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.25 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
67 | AWI 23-2 | Drill and Complete | 5 | 2025-11-15 18:00 | 2025-11-15 21:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 3.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
68 | AWI 23-2 | Drill and Complete | 6 | 2025-11-20 04:30 | 2025-11-20 04:45 | EQP | CMT | Equipment - Cement Downhole Equipment. Use EQPS for surface. | 0.25 | Sub-Contractor | DOWELL | SLK - 2025
69 | AWI 23-2 | Drill and Complete | 7 | 2025-11-26 04:30 | 2025-11-26 05:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.5 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
70 | AWI 23-2 | Drill and Complete | 8 | 2025-11-27 16:30 | 2025-11-27 17:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
71 | AWI 3-9 | Drill and Complete | 1 | 2025-09-12 21:30 | 2025-09-13 01:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 3.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
72 | AWI 3-9 | Drill and Complete | 2 | 2025-09-13 | 2025-09-13 01:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
73 | AWI 3-9 | Drill and Complete | 3 | 2025-09-15 10:00 | 2025-09-15 11:30 | EQPS | CRANE | Equipment - Surface Crane. Third-party only. | 1.5 | Contractor | CHAS | SLK - 2025
74 | AWI 3-9 | Drill and Complete | 4 | 2025-09-17 22:30 | 2025-09-18 04:30 | RREQ | COMPTR | Rig Repair - Computers/Controls. | 6 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
75 | AWI 3-9 | Drill and Complete | 5 | 2025-09-18 09:30 | 2025-09-18 10:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
76 | AWI 3-9 | Drill and Complete | 6 | 2025-09-22 07:00 | 2025-09-22 08:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
77 | AWI 3-9 | Drill and Complete | 7 | 2025-09-22 10:30 | 2025-09-22 11:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
78 | AWI 3-9 | Drill and Complete | 8 | 2025-09-24 11:00 | 2025-09-24 13:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2.25 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
79 | AWI 8-3 | Well Services | 1 | 2019-03-26 06:00 | 2019-03-26 18:00 | WO | EQP | Wait On - Equipment. | 12 | Contractor | TNG Energy Services Indonesia, Pt
80 | AWI 8-3 | Well Services | 1 | 2019-03-27 06:00 | 2019-03-27 10:00 | WO | EQP | Wait On - Equipment. | 4 | Contractor | TNG Energy Services Indonesia, Pt
81 | AWI 8-3 | Well Services | 2 | 2019-03-27 12:00 | 2019-03-27 13:00 | WO | WTHR | Wait On - Weather. Storms, lightning, wind, temperature. | 1 | Operator | STAR
82 | AWI 8-3 | Well Services | 3 | 2019-03-27 13:00 | 2019-03-27 14:00 | WO | TRANSPORT | Wait On - Transport/Logistics. | 1 | Contractor | Cipta Hasil Sugiarto, PT
83 | AWI 8-3 | Well Services | 4 | 2019-03-27 15:00 | 2019-03-27 15:30 | RREQ | MOD | Rig Repair - Equipment Modification. | 0.5 | Contractor | TNG Energy Services Indonesia, Pt
84 | AWI 8-3 | Well Services | 1 | 2019-03-28 11:00 | 2019-03-28 18:00 | WO | EQP | Wait On - Equipment. | 7 | Contractor | TNG Energy Services Indonesia, Pt
85 | AWI 8-3 | Well Services | 1 | 2019-03-29 06:00 | 2019-03-29 07:30 | WO | EQP | Wait On - Equipment. | 1.5 | Contractor | TNG Energy Services Indonesia, Pt
86 | AWI 8-3 | Well Services | 5 | 2019-03-29 11:30 | 2019-03-29 12:30 | EQPS | CRANE | Equipment - Surface Crane. Third-party only. | 1 | Contractor | Cipta Hasil Sugiarto, PT
87 | AWI 8-3 | Well Services | 6 | 2019-03-29 12:30 | 2019-03-29 14:30 | WO | EQP | Wait On - Equipment. | 2 | Operator | STAR
88 | AWI 8-3 | Well Services | 2 | 2019-03-29 15:30 | 2019-03-29 17:00 | WO | WTHR | Wait On - Weather. Storms, lightning, wind, temperature. | 1.5 | Operator | STAR
89 | AWI 8-3 | Well Services | 7 | 2019-03-29 17:00 | 2019-03-29 18:00 | WO | PERSONNEL | Wait On - Personnel. | 1 | Contractor | TNG Energy Services Indonesia, Pt
90 | AWI 8-3 | Well Services | 8 | 2019-03-31 11:00 | 2019-03-31 18:00 | WP | JUNK | Well Problem - Junk in hole. Non-formation related. | 7 | Contractor | TNG Energy Services Indonesia, Pt
91 | AWI 8-3 | Well Services | 8 | 2019-04-01 06:00 | 2019-04-01 18:00 | WP | JUNK | Well Problem - Junk in hole. Non-formation related. | 12 | Contractor | TNG Energy Services Indonesia, Pt
92 | AWI 8-3 | Well Services | 9 | 2019-04-03 10:00 | 2019-04-03 11:30 | EQPS | PSI CNTRL | Equipment - Surface Pressure Control. Excludes BOP/Diverter. | 1.5 | Contractor | TNG Energy Services Indonesia, Pt
93 | AWI 9-10 | Drill and Complete | 1 | 2021-11-20 09:00 | 2021-11-20 10:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Rig Contractor | PT. DATI | SLK - 2021
94 | AWI 9-10 | Drill and Complete | 2 | 2021-11-20 03:45 | 2021-11-20 05:30 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 1.75 | Contractor | Star Energy | SLK - 2021
95 | AWI 9-10 | Drill and Complete | 3 | 2021-11-23 04:15 | 2021-11-23 04:45 | EQP | FL DISP | Equipment - Fluid Displacement. | 0.5 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing | SLK - 2021
96 | AWI 9-10 | Drill and Complete | 4 | 2021-11-30 | 2021-11-30 21:00 | WP | CMT JOB | Well Problem - Cement job failure. | 21 | Operator | Star Energy | SLK - 2021
97 | AWI 9-10 | Drill and Complete | 5 | 2021-12-08 22:30 | 2021-12-09 04:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 5.5 | Rig Contractor | PT. DATI | SLK - 2021
98 | AWI 9-11 | Drill and Complete | 1 | 2026-03-05 19:30 | 2026-03-05 22:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 3 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
99 | AWI 9-11 | Drill and Complete | 2 | 2026-03-06 07:00 | 2026-03-06 08:30 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 1.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
100 | AWI 9-11 | Drill and Complete | 3 | 2026-03-10 11:00 | 2026-03-10 11:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
101 | AWI 9-11 | Drill and Complete | 4 | 2026-03-10 21:30 | 2026-03-10 22:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
102 | AWI 9-11 | Drill and Complete | 5 | 2026-03-11 05:00 | 2026-03-11 05:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.5 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
103 | AWI 9-11 | Drill and Complete | 6 | 2026-03-13 08:30 | 2026-03-13 09:30 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 1 | Rig Contractor | PARKER WELLBORE INDONESIA, PT. | SLK - 2025
104 | DRJ-37 | Drill and Complete | WO05 | 2010-02-15 | 2010-02-25 | WO | ORDERS | Wait On - Orders. | 240
105 | DRJ-37 | Well Services | 1 | 2013-12-15 07:00 | 2013-12-15 09:00 | EQPS | CRANE | Equipment - Surface Crane. Third-party only. | 2 | Rig Contractor | BJ Pumping Services
106 | DRJ-37 | Well Services | 1 | 2015-10-16 07:30 | 2015-10-16 10:30 | EQP | WH | Equipment - Wellhead. Includes wear bushings. | 3 | Operator | Chevron Geothermal Indonesia Ltd.
107 | DRJ-37 | Well Services | 1 | 2018-12-22 18:00 | 2018-12-23 20:00 | EQPS | CRANE | Equipment - Surface Crane. Third-party only. | 26 | Contractor | CHAS
108 | DRJ-37 | Drill and Complete | RR09 | 2010-03-06 03:30 | 2010-03-06 07:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 3.4997 |  | Apexindo Duta Pratama, PT
109 | DRJ-37 | Well Services | 2 | 2013-12-16 02:00 | 2013-12-16 08:00 | EQPS | CT UNIT | Equipment - Surface CT Unit. Excludes downhole tools. | 6 | Rig Contractor | BJ Pumping Services
110 | DRJ-37 | Well Services | 2 | 2015-10-16 22:30 | 2015-10-17 06:30 | WO | TRANSPORT | Wait On - Transport/Logistics. | 8 | Rig Contractor | BJ Pumping Services
112 | DRJ-37 | Drill and Complete | RR03 | 2010-03-06 18:00 | 2010-03-06 21:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 3 |  | Apexindo Duta Pratama, PT
113 | DRJ-37 | Well Services | 3 | 2013-12-17 21:30 | 2013-12-17 22:00 | EQPS | COMPTR | Equipment- Computer | 0.5 | Rig Contractor | BJ Pumping Services
114 | DRJ-37 | Well Services | 3 | 2015-10-17 13:30 | 2015-10-17 18:30 | WO | HES | Wait On - HSE. Safety stand-downs, investigations. | 5 | Operator | Chevron Geothermal Indonesia Ltd.
115 | DRJ-37 | Well Services | 3 | 2018-12-25 17:30 | 2018-12-25 19:30 | EQP | FLTR | Equipment - Filtration. For equipment or fluid. | 2 | Operator | SE
116 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-08 11:00 | 2010-03-08 15:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 3.9997 |  | Chevron Indonesia Company
117 | DRJ-37 | Well Services | 4 | 2018-12-25 20:00 | 2018-12-25 20:30 | EQP | FLTR | Equipment - Filtration. For equipment or fluid. | 0.5 | Contractor | BHGE
118 | DRJ-37 | Drill and Complete | RR12 | 2010-03-11 01:00 | 2010-03-11 02:00 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 1.0003
120 | DRJ-37 | Drill and Complete | DHF01 | 2010-03-11 04:30 | 2010-03-11 08:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 3.5003
121 | DRJ-37 | Well Services | 6 | 2018-12-27 | 2018-12-27 02:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 2 | Contractor | BHGE
122 | DRJ-37 | Drill and Complete | RR09 | 2010-03-11 08:00 | 2010-03-11 08:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.49972
123 | DRJ-37 | Drill and Complete | DHF01 | 2010-03-11 08:30 | 2010-03-11 11:30 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 3
124 | DRJ-37 | Drill and Complete | CMT04 | 2010-03-14 07:30 | 2010-03-14 11:00 | WP | CMT JOB | Well Problem - Cement job failure. | 3.5003
125 | DRJ-37 | Drill and Complete | RR09 | 2010-03-14 11:00 | 2010-03-14 11:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.49972
126 | DRJ-37 | Drill and Complete | DHF02 | 2010-03-16 07:00 | 2010-03-16 14:00 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 7.0003 |  | Halliburton Directional Drilling
127 | DRJ-37 | Drill and Complete | SFC18 | 2010-03-16 14:00 | 2010-03-16 14:30 | EQPS | SURFEQP | Equipment- Surface EQ | 0.49972 |  | Air Drilling
128 | DRJ-37 | Drill and Complete | RR02 | 2010-03-18 09:00 | 2010-03-18 09:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.50028 |  | Apexindo Duta Pratama, PT
129 | DRJ-37 | Drill and Complete | DHF02 | 2010-03-18 13:00 | 2010-03-18 17:30 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 4.5
130 | DRJ-37 | Drill and Complete | RR09 | 2010-03-18 17:30 | 2010-03-18 18:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 |  | Apexindo Duta Pratama, PT
131 | DRJ-37 | Drill and Complete | DHF02 | 2010-03-18 18:00 | 2010-03-18 23:30 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 5.5
132 | DRJ-37 | Drill and Complete | RR09 | 2010-03-18 23:30 | 2010-03-19 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 |  | Apexindo Duta Pratama, PT
133 | DRJ-37 | Drill and Complete | DHF02 | 2010-03-19 | 2010-03-19 01:00 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 1
134 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-19 01:00 | 2010-03-19 03:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 2
135 | DRJ-37 | Drill and Complete | DHF02 | 2010-03-19 23:00 | 2010-03-20 09:00 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 9.9997
136 | DRJ-37 | Drill and Complete | SP08 | 2010-03-21 03:30 | 2010-03-21 05:00 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 1.5
137 | DRJ-37 | Drill and Complete | WBP05 | 2010-03-21 08:30 | 2010-03-21 09:00 | WP | LOST CIR | Well Problem- loss Circulation | 0.5
138 | DRJ-37 | Drill and Complete | DHF01 | 2010-03-21 16:30 | 2010-03-22 06:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 13.5
139 | DRJ-37 | Drill and Complete | F06 | 2010-03-22 07:30 | 2010-03-22 09:30 | PR | FL CONDT | Process - Fluid Conditioning. Properties, underbalance, barite, gas. | 2.0003
140 | DRJ-37 | Drill and Complete | SP08 | 2010-03-22 12:30 | 2010-03-22 13:30 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 0.99972
141 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-22 23:30 | 2010-03-23 01:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1.5
142 | DRJ-37 | Drill and Complete | SFC07 | 2010-03-24 05:30 | 2010-03-24 08:00 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 2.5003
144 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-25 15:30 | 2010-03-26 02:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 10.5
145 | DRJ-37 | Drill and Complete | F06 | 2010-03-26 02:00 | 2010-03-26 03:00 | PR | FL CONDT | Process - Fluid Conditioning. Properties, underbalance, barite, gas. | 0.99972
146 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-26 14:30 | 2010-03-26 16:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1.5
147 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-26 19:30 | 2010-03-26 20:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1
148 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-27 01:00 | 2010-03-27 07:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 6.5
149 | DRJ-37 | Drill and Complete | RR09 | 2010-03-27 07:30 | 2010-03-27 08:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.50028
150 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-27 08:00 | 2010-03-27 12:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 3.9997
151 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-27 13:00 | 2010-03-28 01:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 12.5
152 | DRJ-37 | Drill and Complete | WBP14 | 2010-03-28 13:00 | 2010-03-29 02:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 13.5
153 | DRJ-38 | Drill and Complete | 1 | 2010-09-27 06:30 | 2010-09-27 20:00 | WO | SUPPLIES | Wait On - Supplies. | 13.5 | Operator
154 | DRJ-38 | Well Services | 1 | 2018-12-19 14:00 | 2018-12-19 17:00 | WO | TRANSPORT | Wait On - Transport/Logistics. | 3 | Contractor | BJ Services Indonesia, PT
155 | DRJ-38RD | Sidetrack | 1 | 2022-02-05 12:30 | 2022-02-09 08:00 | FISH | FISH ALL CH | Fishing - Cased hole operations. | 91.5 | Operator | Star Energy | DRJ - 2022
157 | DRJ-38RD | Sidetrack | 2 | 2022-02-09 08:00 | 2022-02-09 08:30 | EQP | WHPSTK | Equipment - Whipstock. Running/setting/retrieval. | 0.5 | Contractor | Schlumberger | DRJ - 2022
158 | DRJ-38 | Drill and Complete | 3 | 2010-10-02 05:30 | 2010-10-02 07:30 | EQP | PLUG | Equipment - Plug. Includes retrievable/drillable. | 2
159 | DRJ-38RD | Sidetrack | 3 | 2022-02-09 08:30 | 2022-02-09 17:30 | FISH | FISH ALL CH | Fishing - Cased hole operations. | 9 | Operator | Star Energy | DRJ - 2022
160 | DRJ-38 | Drill and Complete | 4 | 2010-10-02 16:30 | 2010-10-02 18:30 | RREQ | DIVERTER | Rig Repair - Diverter. | 2
161 | DRJ-38RD | Sidetrack | 4 | 2022-02-18 02:15 | 2022-02-18 02:30 | RREQ | POWER | Rig Repair - Power System. | 0.25 | Contractor | PT. DATI | DRJ - 2022
162 | DRJ-38 | Drill and Complete | 5 | 2010-10-08 12:00 | 2010-10-08 13:30 | EQP | LOG TOOL | Equipment - Logging Tools. Excludes MWD/LWD. | 1.5
163 | DRJ-38RD | Sidetrack | 5 | 2022-02-11 11:00 | 2022-02-12 18:30 | EQP | WIN | Equipment - Whipstock/Window Milling. | 31.5 | Contractor | WIS (Wellbore Integrity Solution) | DRJ - 2022
165 | DRJ-38RD | Sidetrack | 6 | 2022-02-24 13:15 | 2022-02-24 17:00 | EQP | JWLRY | Equipment - Completion Jewelry. Initial installation only. | 3.75 | Contractor | Schlumberger | DRJ - 2022
167 | DRJ-38RD | Sidetrack | 7 | 2022-02-28 20:30 | 2022-03-01 04:45 | EQP | JWLRY | Equipment - Completion Jewelry. Initial installation only. | 8.25 | Contractor | Schlumberger | DRJ - 2022
168 | DRJ-38 | Drill and Complete | 8 | 2010-10-12 01:00 | 2010-10-12 03:00 | WO | HES ALARM | Wait On - HSE Alarms. | 2 | Operator
169 | DRJ-38RD | Sidetrack | 8 | 2022-03-01 19:15 | 2022-03-01 19:30 | EQP | DS WS | Equipment - Drillpipe/Workstring. | 0.25 | Contractor | PT. DATI | DRJ - 2022
170 | DRJ-38 | Drill and Complete | 9 | 2010-10-12 03:30 | 2010-10-12 04:00 | WO | HES ALARM | Wait On - HSE Alarms. | 0.5 | Operator
171 | DRJ-38RD | Sidetrack | 9 | 2022-03-02 08:30 | 2022-03-02 09:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Contractor | PT. DATI | DRJ - 2022
172 | DRJ-38 | Drill and Complete | 10 | 2010-10-12 05:30 | 2010-10-12 06:00 | WO | HES ALARM | Wait On - HSE Alarms. | 0.5 | Operator
173 | DRJ-38 | Drill and Complete | 11 | 2010-10-12 12:30 | 2010-10-16 18:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 101.5 | Rig Contractor | Apexindo Duta Pratama, PT
174 | DRJ-38 | Drill and Complete | 12 | 2010-10-12 12:30 | 2010-10-12 13:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | Apexindo Duta Pratama, PT
175 | DRJ-38 | Drill and Complete | 13 | 2010-10-17 04:00 | 2010-10-17 04:30 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.5 | Rig Contractor | Apexindo Duta Pratama, PT
176 | DRJ-38 | Drill and Complete | 14 | 2010-10-17 20:00 | 2010-10-18 00:30 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 4.5 | Operator
177 | DRJ-38 | Drill and Complete | 15 | 2010-10-18 04:00 | 2010-10-18 04:30 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 0.5 | Operator
178 | DRJ-44OH | Drill and Complete | 1 | 2019-06-28 20:30 | 2019-06-28 21:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1 | Operator | Star Energy
179 | DRJ-44OH | Drill and Complete | 2 | 2019-07-02 04:30 | 2019-07-02 07:00 | EQP | SC | Equipment - Sand Control. | 25 | Operator's Other Contractors | MI Swaco
181 | DRJ-44OH | Drill and Complete | 4 | 2019-07-06 02:45 | 2019-07-09 05:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 74.25 | Contractor | Schlumberger Anadrill
182 | DRJ-44OH | Drill and Complete | 5 | 2019-07-29 15:30 | 2019-07-30 08:00 | EQP | LOG TOOL | Equipment - Logging Tools. Excludes MWD/LWD. | 16.5 | Operator's Other Contractors | SABS
183 | DRJ-45OH | Drill and Complete | 1 | 2019-08-17 05:00 | 2019-08-18 13:00 | EQPS | EQPS | Equipment- Surface EQ | 32 | Rig Contractor | PT. DATI
184 | DRJ-45OH | Drill and Complete | 2 | 2019-09-02 18:00 | 2019-09-02 18:30 | EQPS | EQPS | Equipment- Surface EQ | 0.5 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing
185 | DRJ-45OH | Drill and Complete | 3 | 2019-09-04 16:30 | 2019-09-05 15:00 | EQPS | EQPS | Equipment- Surface EQ | 22.5 | Contractor | Schlumberger Anadrill
186 | DRJ-45OH | Drill and Complete | 4 | 2019-09-18 20:00 | 2019-09-18 23:30 | EQPS | EQPS | Equipment- Surface EQ | 3.5 | Operator | Star Energy
187 | DRJ-46OH | Drill and Complete | 1 | 2019-11-09 22:30 | 2019-11-10 00:30 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 2 | Rig Contractor | PT. DATI
188 | DRJ-46OH | Drill and Complete | 2 | 2019-11-18 18:00 | 2019-11-18 18:30 | WP | TORQ | Well Problem - Excessive torque. | 0.5 | Operator | Star Energy
189 | DRJ-46OH | Drill and Complete | 3 | 2019-11-18 18:30 | 2019-11-18 20:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | PT. DATI
190 | DRJ-46OH | Drill and Complete | 4 | 2019-11-18 20:30 | 2019-11-18 21:00 | RREQ | ROT | Rig Repair - Rotary Equipment. | 0.5 | Rig Contractor | PT. DATI
191 | DRJ-46OH | Drill and Complete | 5 | 2019-11-18 21:00 | 2019-11-18 23:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 2 | Operator | Star Energy
192 | DRJ-46OH | Drill and Complete | 6 | 2019-12-02 06:30 | 2019-12-02 08:30 | EQPS | PWR SWVL | Equipment - Surface Power Swivel. | 2 | Contractor | Air Drilling Associates Indonesia
193 | DRJ-46OH | Drill and Complete | 7 | 2019-12-03 13:00 | 2019-12-04 12:00 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 23 | Operator | Star Energy
194 | DRJ-46OH | Drill and Complete | 8 | 2019-12-23 22:45 | 2019-12-23 23:59 | WC | KICK | Well Control - Kick. Uncontrolled formation fluid influx. | 1.2333 | Operator | Star Energy
195 | DRJ-47OH | Drill and Complete | 1 | 2019-12-28 22:30 | 2019-12-29 01:30 | WP | TORQ | Well Problem - Excessive torque. | 3 | Operator | Star Energy
197 | DRJ-47OH | Drill and Complete | 3 | 2020-01-09 07:30 | 2020-01-09 08:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1.25 | Rig Contractor | PT. DATI
198 | DRJ-47OH | Drill and Complete | 4 | 2020-01-14 20:30 | 2020-01-15 10:30 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 14 | Rig Contractor | PT. DATI
199 | DRJ-47OH | Drill and Complete | 5 | 2020-01-28 13:00 | 2020-01-29 20:30 | RREQ |  | Rig Equipment | 31.5 | Operator | Star Energy
200 | DRJ-48 | Drill and Complete | 1 | 2020-02-16 03:30 | 2020-02-16 04:45 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 1.25 | Sub-Contractor | Schlumberger Anadrill | DRJ - 2019
201 | DRJ-48 | Drill and Complete | 2 | 2020-02-16 04:45 | 2020-02-16 06:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 1.25 | Rig Contractor | PT. DATI | DRJ - 2019
202 | DRJ-48 | Drill and Complete | 3 | 2020-02-17 12:00 | 2020-02-17 13:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Operator | Star Energy | DRJ - 2019
203 | DRJ-48 | Drill and Complete | 4 | 2020-02-19 18:00 | 2020-02-21 02:00 | WP | FRM INSTAB | Well Problem - Wellbore instability. Unconsolidated formations. | 32 | Operator | Star Energy | DRJ - 2019
204 | DRJ-48 | Drill and Complete | 5 | 2020-02-21 17:30 | 2020-02-21 18:00 | EQPS | CMT | Equipment - Surface Cement. Use EQP for downhole. | 0.5 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing | DRJ - 2019
205 | DRJ-49OH | Drill and Complete | 1 | 2022-03-06 14:45 | 2022-03-06 16:45 | EQP | JWLRY | Equipment - Completion Jewelry. Initial installation only. | 2 | Contractor | Schlumberger
206 | DRJ-49OH | Drill and Complete | 2 | 2022-03-06 17:30 | 2022-03-06 21:00 | WO | WATER | Wait On - Water supply. | 3.5 | Operator | Star Energy
207 | DRJ-49OH | Drill and Complete | 3 | 2022-03-07 17:00 | 2022-03-07 19:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 2 | Operator | Star Energy
208 | DRJ-49OH | Drill and Complete | 4 | 2022-03-07 21:00 | 2022-03-07 22:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1.5 | Operator | Star Energy
209 | DRJ-49OH | Drill and Complete | 3 | 2022-03-08 11:30 | 2022-03-08 17:45 | WP | TIGHT HOLE | Well Problem - Tight hole. | 6.25 | Operator | Star Energy
210 | DRJ-49OH | Drill and Complete | 4 | 2022-03-31 12:45 | 2022-03-31 19:45 | WP | TIGHT HOLE | Well Problem - Tight hole. | 7 | Operator | Star Energy
211 | DRJ-49OH | Drill and Complete | 5 | 2022-04-02 13:00 | 2022-04-03 01:45 | EQP | BIT | Equipment - Bit/Underreamer/Hole Opener. | 12.75 | Operator | Star Energy
212 | DRJ-49OH | Drill and Complete | 6 | 2022-04-05 07:30 | 2022-04-05 11:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 3.5 | Contractor | Schlumberger
213 | DRJ-49OH | Drill and Complete | 7 | 2022-04-05 11:00 | 2022-04-05 15:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 4.5 | Rig Contractor | PT. DATI
214 | DRJ-49OH | Drill and Complete | 6 | 2022-04-05 15:30 | 2022-04-05 16:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 1 | Contractor | Schlumberger
215 | DRJ-49OH | Drill and Complete | 6 | 2022-04-06 17:30 | 2022-04-06 23:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 6 | Contractor | Schlumberger
216 | DRJ-49OH | Drill and Complete | 8 | 2022-04-07 07:15 | 2022-04-07 11:15 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 4 | Rig Contractor | PT. DATI
217 | DRJ-49OH | Drill and Complete | 8 | 2022-04-07 16:00 | 2022-04-07 20:00 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 4 | Rig Contractor | PT. DATI
218 | DRJ-49OH | Drill and Complete | 9 | 2022-03-26 11:45 | 2022-03-26 21:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 9.25 | Contractor | Schlumberger Anadrill
219 | DRJ-50OH | Drill and Complete | 1 | 2022-04-23 11:00 | 2022-04-23 12:45 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 1.75 | Contractor | Air Drilling Associates Indonesia
220 | DRJ-50OH | Drill and Complete | 2 | 2022-05-18 | 2022-05-18 04:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 4.75 | Contractor | PT. DATI
221 | DRJ-50OH | Drill and Complete | 3 | 2022-05-18 12:45 | 2022-05-18 13:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Contractor | PT. DATI
222 | DRJ-50OH | Drill and Complete | 4 | 2022-05-19 04:15 | 2022-05-19 08:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 4.5 | Contractor | PT. DATI
223 | DRJ-51OH | Drill and Complete | 1 | 2022-06-07 17:30 | 2022-06-07 22:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 5 | Rig Contractor | PT. DATI
224 | DRJ-51OH | Drill and Complete | 2 | 2022-06-08 01:00 | 2022-06-08 03:45 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 2.75 | Rig Contractor | PT. DATI
225 | DRJ-51OH | Drill and Complete | 3 | 2022-06-09 22:30 | 2022-06-10 11:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 12.5 | Operator | Star Energy
227 | DRJ-51OH | Drill and Complete | 5 | 2022-06-15 15:00 | 2022-06-15 18:00 | EQPS | EL UNIT | Equipment - Surface E-line Unit. Excludes downhole tools. | 3 | Contractor | Schlumberger
229 | DRJ-52OH | Drill and Complete | 1 | 2022-07-14 18:15 | 2022-07-14 19:45 | EQRCH | ADA RCH | Equipment- Air Drilling Rubber Change | 1.5 | Contractor | Schlumberger
230 | DRJ-52OH | Drill and Complete | 2 | 2022-07-20 05:30 | 2022-07-20 12:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 7.25 | Contractor | PT. DATI
231 | DRJ-52OH | Drill and Complete | 3 | 2022-07-20 13:30 | 2022-07-20 16:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2.5 | Contractor | PT. DATI
232 | DRJ-52OH | Drill and Complete | 4 | 2022-07-21 05:45 | 2022-07-21 07:15 | WC | STEAM | Well Control - Steam influx. | 1.5 | Operator | Star Energy
233 | DRJ-52OH | Drill and Complete | 4 | 2022-07-21 12:00 | 2022-07-21 15:45 | WC | STEAM | Well Control - Steam influx. | 3.75 | Operator | Star Energy
234 | DRJ-52OH | Drill and Complete | 5 | 2022-07-21 17:45 | 2022-07-21 18:00 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 0.25 | Contractor | PT. DATI
235 | DRJ-52OH | Drill and Complete | 6 | 2022-07-21 21:45 | 2022-07-22 04:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 6.25 | Contractor | PT. DATI
236 | DRJ-52OH | Drill and Complete | 6 | 2022-07-22 08:15 | 2022-07-22 11:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 3.5 | Contractor | PT. DATI
239 | DRJ-52OH | Drill and Complete | 6 | 2022-07-25 14:45 | 2022-07-25 15:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Contractor | PT. DATI
240 | DRJ-52OH | Drill and Complete | 4 | 2022-07-25 15:00 | 2022-07-25 16:00 | WC | STEAM | Well Control - Steam influx. | 1 | Operator | Star Energy
241 | DRJ-52OH | Drill and Complete | 6 | 2022-07-25 16:00 | 2022-07-25 23:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 7.75 | Contractor | PT. DATI
243 | DRJ-53 | Drill and Complete | 1 | 2024-04-26 07:30 | 2024-04-26 11:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 3.5 | Operator | SEG | DRJ - 2024
244 | DRJ-53 | Drill and Complete | 3 | 2024-04-28 09:30 | 2024-04-28 10:00 | RREQ | COMPTR | Rig Repair - Computers/Controls. | 0.5 | Contractor | VARCO INDO | DRJ - 2024
246 | DRJ-53 | Drill and Complete | 5 | 2024-04-29 23:30 | 2024-04-30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
247 | DRJ-53 | Drill and Complete | 5 | 2024-04-30 | 2024-04-30 00:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
248 | DRJ-53 | Drill and Complete | 5 | 2024-04-30 12:00 | 2024-05-01 11:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 23.5 | Rig Contractor | PARKER | DRJ - 2024
249 | DRJ-53 | Drill and Complete | 6 | 2024-05-05 01:30 | 2024-05-05 01:45 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 0.25 | Contractor | VARCO INDO | DRJ - 2024
250 | DRJ-53 | Drill and Complete | 7 | 2024-05-05 13:00 | 2024-05-05 13:15 | PR | PROC | Process - Procedure changes. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
251 | DRJ-53 | Drill and Complete | 8 | 2024-05-09 02:30 | 2024-05-09 02:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
252 | DRJ-53 | Drill and Complete | 9 | 2024-05-16 05:45 | 2024-05-16 07:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1.75 | Rig Contractor | PARKER | DRJ - 2024
253 | DRJ-54 | Drill and Complete | 1 | 2024-06-11 02:00 | 2024-06-18 | SPWS | HOLE CLEAN | Stuck Pipe Well Stability- Hole Cleaning | 166 | Operator |  | DRJ - 2024
254 | DRJ-54 | Drill and Complete | 2 | 2024-06-18 | 2024-06-18 09:00 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 9 | Contractor | SLB | DRJ - 2024
255 | DRJ-54 | Drill and Complete | 3 | 2024-06-18 09:00 | 2024-06-20 17:00 | SPWS | STABILITY | Stuck Pipe - Wellbore stability. General. | 56 | Operator |  | DRJ - 2024
256 | DRJ-54 | Drill and Complete | 4 | 2024-06-24 16:00 | 2024-06-24 17:00 | EQP | AIR DRILLING | Equipment- Air Drilling | 1 | Contractor | ADA | DRJ - 2024
257 | DRJ-54 | Drill and Complete | 5 | 2024-06-24 09:00 | 2024-06-24 10:00 | MAINTENANCE | SLIP AND CUT DRL LINE | MAINTENANCE-SLIP AND CUT DRL LINE | 1 | Rig Contractor | PARKER | DRJ - 2024
258 | DRJ-55 | Drill and Complete | 2 | 2024-07-15 12:00 | 2024-07-15 18:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 6.5 | Sub-Contractor | ADA | DRJ - 2024
259 | DRJ-55 | Drill and Complete | 1 | 2024-07-10 17:15 | 2024-07-10 18:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Rig Contractor | PARKER | DRJ - 2024
260 | DRJ-55 | Drill and Complete | 3 | 2024-07-15 12:30 | 2024-07-15 16:30 | WC | WC | Well Controll | 4 | Operator | SEG | DRJ - 2024
261 | DRJ-55 | Drill and Complete | 4 | 2024-07-16 12:00 | 2024-07-16 15:30 | WC | WC | Well Controll | 3.5 | Operator | SEG | DRJ - 2024
262 | DRJ-55 | Drill and Complete | 5 | 2024-07-18 10:00 | 2024-07-18 21:00 | WO | WATER | Wait On - Water supply. | 11 | Operator | SEG | DRJ - 2024
263 | DRJ-55 | Drill and Complete | 5 | 2024-07-18 21:30 | 2024-07-19 10:00 | WO | WATER | Wait On - Water supply. | 12.5 | Operator | SEG | DRJ - 2024
264 | DRJ-56 | Drill and Complete | 1 | 2024-08-08 15:45 | 2024-08-08 17:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | PARKER | DRJ - 2024
265 | DRJ-56 | Drill and Complete | 2 | 2024-08-09 21:30 | 2024-08-09 23:30 | SCL | STUCK | Stuck Casing/Liner - Unknown cause. | 2 | Operator | SEG | DRJ - 2024
266 | DRJ-56 | Drill and Complete | 3 | 2024-08-13 15:00 | 2024-08-17 16:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 97 | Operator | SEG | DRJ - 2024
267 | DRJ-56 | Drill and Complete | 4 | 2024-08-17 16:00 | 2024-08-18 | WP | TIGHT HOLE | Well Problem - Tight hole. | 8 | Operator | SEG | DRJ - 2024
268 | DRJ-56 | Drill and Complete | 6 | 2024-08-18 | 2024-08-19 07:30 | WP | CMT JOB | Well Problem - Cement job failure. | 31.5 | Operator | SEG | DRJ - 2024
269 | DRJ-56 | Drill and Complete | 5 | 2024-08-19 07:30 | 2024-08-19 08:30 | EQPS | ML | Equipment - Surface Mud Logging. | 1 | Contractor | SLB | DRJ - 2024
270 | DRJ-56 | Drill and Complete | 7 | 2024-08-21 07:00 | 2024-08-21 08:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Rig Contractor | PARKER | DRJ - 2024
271 | DRJ-56 | Drill and Complete | 8 | 2024-08-22 05:30 | 2024-08-25 11:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 77.5 | Operator | SEG | DRJ - 2024
272 | DRJ-56 | Drill and Complete | 9 | 2024-08-24 16:30 | 2024-08-24 18:00 | SW | STUCK | Stuck Wireline - General. | 1.5 | Contractor | SLB | DRJ - 2024
273 | DRJ-56 | Drill and Complete | 7 | 2024-08-25 21:45 | 2024-08-27 02:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 28.25 | Rig Contractor | PARKER | DRJ - 2024
275 | DRJ-56 | Drill and Complete | 7 | 2024-08-28 | 2024-08-28 00:30 | RREQ | ROT | Rig Repair - Rotary Equipment. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
276 | DRJ-56 | Drill and Complete | 7 | 2024-08-28 08:00 | 2024-08-28 09:00 | RREQ | ROT | Rig Repair - Rotary Equipment. | 1 | Rig Contractor | PARKER | DRJ - 2024
278 | DRJ-56 | Drill and Complete | 7 | 2024-08-28 10:00 | 2024-08-28 10:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
281 | DRJ-56 | Drill and Complete | 7 | 2024-08-28 19:30 | 2024-08-28 20:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Rig Contractor | PARKER | DRJ - 2024
282 | DRJ-56 | Drill and Complete | 7 | 2024-08-28 23:00 | 2024-08-28 23:59 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.98333 | Rig Contractor | PARKER | DRJ - 2024
283 | DRJ-56 | Drill and Complete | 7 | 2024-08-29 | 2024-08-29 00:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
284 | DRJ-56 | Drill and Complete | 7 | 2024-08-29 01:30 | 2024-08-29 02:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
285 | DRJ-56 | Drill and Complete | 8 | 2024-08-31 02:50 | 2024-08-31 03:05 | RRBOP | SURF | Rig Repair - Surface BOP. | 0.25 | Sub-Contractor | SLB | DRJ - 2024
286 | DRJ-56 | Drill and Complete | 9 | 2024-09-01 07:00 | 2024-09-03 04:30 | WO | PERSONNEL | Wait On - Personnel. | 45.5 | Contractor | SLB | DRJ - 2024
287 | DRJ-56 | Drill and Complete | 7 | 2024-09-03 16:00 | 2024-09-03 16:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
288 | DRJ-56 | Drill and Complete | 11 | 2024-09-04 00:45 | 2024-09-04 01:30 | EQP | PLUG | Equipment - Plug. Includes retrievable/drillable. | 0.75 | Contractor | SLB | DRJ - 2024
289 | DRJ-56 | Drill and Complete | 7 | 2024-09-04 07:00 | 2024-09-04 07:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
290 | DRJ-56 | Drill and Complete | 7 | 2024-09-04 18:00 | 2024-09-04 20:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | PARKER | DRJ - 2024
291 | DRJ-56 | Drill and Complete | 8 | 2024-09-05 03:00 | 2024-09-06 03:30 | EQP | WHPSTK | Equipment - Whipstock. Running/setting/retrieval. | 24.5 | Operator | SEG | DRJ - 2024
292 | DRJ-56 | Drill and Complete | 11 | 2024-09-10 17:15 | 2024-09-10 17:30 | EQP | DS WS | Equipment - Drillpipe/Workstring. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
293 | DRJ-56 | Drill and Complete | 12 | 2024-09-11 05:30 | 2024-09-11 12:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 6.5 | Rig Contractor | SLB | DRJ - 2024
294 | DRJ-56 | Drill and Complete | 13 | 2024-09-16 21:15 | 2024-09-16 21:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
295 | DRJ-56 | Drill and Complete | 14 | 2024-09-18 00:45 | 2024-09-18 01:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Rig Contractor | PARKER | DRJ - 2024
296 | DRJ-56 | Drill and Complete | 15 | 2024-09-02 14:00 | 2024-09-02 15:00 | SW | TOOL FAIL | Stuck Wireline - Downhole tool failure. | 1 | Contractor | SEG | DRJ - 2024
297 | DRJ-56 | Drill and Complete | 16 | 2024-09-09 23:00 | 2024-09-10 03:30 | EQP | MWD | Equipment - MWD issues. Excludes survey. | 4.5 | Contractor | SLB | DRJ - 2024
298 | DRJ-56 | Drill and Complete | 17 | 2024-09-10 10:45 | 2024-09-10 13:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 2.25 | Contractor | SLB | DRJ - 2024
299 | DRJ-57 | Drill and Complete | 1 | 2024-10-03 15:00 | 2024-10-03 15:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PARKER | DRJ - 2024
300 | DRJ-57 | Drill and Complete | 2 | 2024-10-03 21:00 | 2024-10-03 21:45 | RREQ | PIPE HANDL | Rig Repair - Pipe Handling. | 0.75 | Contractor | PARKER | DRJ - 2024
301 | DRJ-57 | Drill and Complete | 3 | 2024-10-04 09:15 | 2024-10-04 09:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
302 | DRJ-57 | Drill and Complete | 4 | 2024-10-07 | 2024-10-07 03:00 | RRBOP | SURF | Rig Repair - Surface BOP. | 3 | Rig Contractor | PARKER | DRJ - 2024
303 | DRJ-57 | Drill and Complete | 5 | 2024-10-07 11:00 | 2024-10-07 13:30 | RREQ | DERRICK | Rig Repair - Derrick. | 2.5 | Rig Contractor | PARKER | DRJ - 2024
304 | DRJ-57 | Drill and Complete | 6 | 2024-10-17 22:30 | 2024-10-17 23:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
305 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 00:30 | 2024-10-19 01:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Rig Contractor | PARKER | DRJ - 2024
306 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 03:00 | 2024-10-19 05:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | PARKER | DRJ - 2024
307 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 15:00 | 2024-10-19 15:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
308 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 15:30 | 2024-10-19 16:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER | DRJ - 2024
309 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 16:00 | 2024-10-19 17:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1.5 | Rig Contractor | PARKER | DRJ - 2024
310 | DRJ-57 | Drill and Complete | 6 | 2024-10-19 17:30 | 2024-10-19 19:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 2 | Rig Contractor | PARKER | DRJ - 2024
311 | HMD-A01 | Drill and Complete | 1 | 2025-10-19 11:30 | 2025-10-19 16:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 5 | Rig Contractor | PARKER
312 | HMD-A01 | Drill and Complete | 2 | 2025-10-20 19:30 | 2025-10-20 20:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.5 | Rig Contractor | PARKER
313 | HMD-A01 | Drill and Complete | 3 | 2025-10-20 22:00 | 2025-10-21 02:30 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 4.5 | Rig Contractor | PARKER
314 | HMD-A01 | Drill and Complete | 4 | 2025-10-21 10:00 | 2025-10-21 16:00 | EQP | CMT | Equipment - Cement Downhole Equipment. Use EQPS for surface. | 6 | Service Company | NMS
315 | HMD-A01 | Drill and Complete | 5 | 2025-10-23 23:00 | 2025-10-24 02:00 | PR | FL CONDT | Process - Fluid Conditioning. Properties, underbalance, barite, gas. | 3 | Service Company | SLB
316 | HMD-A01 | Drill and Complete | 6 | 2025-10-26 15:30 | 2025-10-26 16:30 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 1 | Rig Contractor | PARKER
318 | HMD-A01 | Drill and Complete | 8 | 2025-10-31 10:30 | 2025-10-31 11:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PARKER
319 | HMD-A01 | Drill and Complete | 9 | 2025-11-01 18:30 | 2025-11-01 19:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.5 | Rig Contractor | PARKER
320 | HMD-A01 | Drill and Complete | 10 | 2025-11-03 12:30 | 2025-11-03 13:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 1 | Contractor | MI SWACO
321 | HMD-A01 | Drill and Complete | 11 | 2025-11-07 | 2025-11-07 00:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.5 | Contractor | ADA
322 | HMD-A01 | Drill and Complete | 12 | 2025-11-07 17:30 | 2025-11-07 20:00 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 2.5 | Rig Contractor | PARKER
323 | HMD-A01 | Drill and Complete | 13 | 2025-11-08 15:30 | 2025-11-08 17:00 | EQP | LOG TOOL | Equipment - Logging Tools. Excludes MWD/LWD. | 1.5 | Contractor | SABS
324 | HMD-A01 | Drill and Complete | 14 | 2025-11-08 19:00 | 2025-11-08 21:00 | EQP | LOG TOOL | Equipment - Logging Tools. Excludes MWD/LWD. | 2 | Contractor | PARKER
325 | HMD-A02 | Drill and Complete | 1 | 2025-11-18 05:30 | 2025-11-18 15:30 | EQP | MWD | Equipment - MWD issues. Excludes survey. | 10 | Service Company | DOWELL ANADRILL
326 | HMD-A02 | Drill and Complete | 2 | 2025-11-20 14:30 | 2025-11-20 15:00 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 0.5 | Contractor | PARKER
327 | HMD-A02 | Drill and Complete | 3 | 2025-11-21 11:30 | 2025-11-21 19:30 | WO | CMT | Wait On - Cement. Waiting on cement. | 8 | Service Company | DOWELL ANADRILL
328 | HMD-A02 | Drill and Complete | 4 | 2025-11-21 19:30 | 2025-11-21 22:00 | EQPS | CMT | Equipment - Surface Cement. Use EQP for downhole. | 2.5 | Service Company | DOWELL ANADRILL
329 | MBA-6 | Drill and Complete | 1 | 2018-12-01 14:30 | 2018-12-01 15:00 | RREQ | MOD | Rig Repair - Equipment Modification. | 0.5 | Rig Contractor | PT. DATI | WW - 2018
330 | MBA-6 | Drill and Complete | 2 | 2018-12-02 04:30 | 2018-12-02 05:00 | EQPS | CMT | Equipment - Surface Cement. Use EQP for downhole. | 0.5 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing | WW - 2018
332 | MBA-6 | Drill and Complete | 4 | 2018-12-08 03:15 | 2018-12-08 06:45 | EQPS | AIR DRILLING | Equipment- Air Drilling | 3.5 | Contractor | Air Drilling Associates Indonesia | WW - 2018
333 | MBA-6 | Drill and Complete | 5 | 2018-12-20 22:30 | 2018-12-21 00:30 | WC | STEAM | Well Control - Steam influx. | 3 | Operator | STAR | WW - 2018
334 | MBA-6 | Drill and Complete | 6 | 2018-12-25 08:30 | 2018-12-25 13:00 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 4.5 | Rig Contractor | PT. DATI | WW - 2018
335 | MBA-7 | Drill and Complete | 1 | 2018-12-30 01:15 | 2018-12-31 14:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 36.75 | Rig Contractor | PT. DATI | WW - 2018
336 | MBA-7 | Drill and Complete | 2 | 2019-01-07 10:15 | 2019-01-07 11:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 1.25 | Contractor | MI Swaco | WW - 2018
337 | MBA-7 | Drill and Complete | 3 | 2019-01-10 15:30 | 2019-01-11 04:30 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 13 | Operator | STAR | WW - 2018
338 | MBA-7 | Drill and Complete | 4 | 2019-01-16 15:15 | 2019-01-16 16:15 | WP | FRM INSTAB | Well Problem - Wellbore instability. Unconsolidated formations. | 1 | Operator | STAR | WW - 2018
339 | MBA-7 | Drill and Complete | 5 | 2019-01-17 10:30 | 2019-01-17 17:00 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 6.5 | Operator | STAR | WW - 2018
340 | MBA-7 | Drill and Complete | 6 | 2019-01-23 15:00 | 2019-01-23 16:00 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 1 | Contractor | Schlumberger | WW - 2018
341 | MBA-7 | Drill and Complete | 7 | 2019-01-24 10:00 | 2019-01-24 10:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.5 | Contractor | Air Drilling Associates Indonesia | WW - 2018
342 | MBD-7 | Drill and Complete | 1 | 2019-02-13 10:00 | 2019-02-13 15:00 | SCL | GEOMETRY | Stuck Casing/Liner - Wellbore geometry. Excessive dogleg. | 3 | Operator | Star Energy | WW - 2018
343 | MBD-7 | Drill and Complete | 2 | 2019-02-17 22:00 | 2019-02-17 22:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Rig Contractor | PT. DATI | WW - 2018
345 | MBD-7 | Drill and Complete | 4 | 2019-02-18 10:30 | 2019-02-18 11:00 | WO | ORDERS | Wait On - Orders. | 0.5 | Operator | Star Energy | WW - 2018
346 | MBD-7 | Drill and Complete | 5 | 2019-02-20 23:30 | 2019-02-21 04:30 | EQP | CMT | Equipment - Cement Downhole Equipment. Use EQPS for surface. | 5 | Contractor | Sagatrade Murni | WW - 2018
347 | MBD-7 | Drill and Complete | 2 | 2019-02-22 11:00 | 2019-02-22 11:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PT. DATI | WW - 2018
349 | MBD-7 | Drill and Complete | 6 | 2019-02-22 04:45 | 2019-02-22 05:00 | RRBOP | SURF | Rig Repair - Surface BOP. | 0.25 | Rig Contractor | PT. DATI | WW - 2018
350 | MBD-7 | Drill and Complete | 7 | 2019-02-23 04:00 | 2019-02-23 12:00 | WO | EQP | Wait On - Equipment. | 8 | Rig Contractor | PT. DATI | WW - 2018
351 | MBD-7 | Drill and Complete | 8 | 2019-02-25 02:30 | 2019-02-26 03:00 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 24.5 | Operator | Star Energy | WW - 2018
353 | MBD-7 | Drill and Complete | 10 | 2019-02-27 18:15 | 2019-02-27 18:30 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 0.25 | Contractor | Air Drilling Associates Indonesia | WW - 2018
354 | MBD-7 | Drill and Complete | 11 | 2019-02-28 14:30 | 2019-03-01 | EQPS | CIRSYS | Equipment - Surface Circulation System. Third-party. | 9.5 | Contractor | Air Drilling Associates Indonesia | WW - 2018
355 | MBD-7 | Drill and Complete | 12 | 2019-03-01 03:45 | 2019-03-04 14:15 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 82.5 | Contractor | Air Drilling Associates Indonesia | WW - 2018
356 | MBD-7 | Drill and Complete | 12 | 2019-03-04 15:30 | 2019-03-06 05:30 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 38 | Contractor | Air Drilling Associates Indonesia | WW - 2018
357 | MBD-7 | Drill and Complete | 2 | 2019-03-09 19:30 | 2019-03-09 20:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Rig Contractor | PT. DATI | WW - 2018
358 | MBD-7 | Drill and Complete | 13 | 2019-03-12 06:00 | 2019-03-19 17:00 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 18 | Operator | Star Energy | WW - 2018
359 | MBD-8OH | Drill and Complete | 1 | 2019-03-25 03:30 | 2019-03-25 07:00 | PR | ERROR | Process - Human Error. Non-mechanical. | 3.5 | Contractor | Schlumberger
360 | MBD-8 | Sidetrack | 1 | 2020-11-08 23:00 | 2020-11-11 03:30 | SP | CMT | Stuck Pipe - Cement. Includes drillpipe, workstring, tubing. | 52.5 | Operator | Star Energy | WW - 2018
361 | MBD-8OH | Drill and Complete | 2 | 2019-03-28 14:00 | 2019-03-28 16:30 | EQP | CMT | Equipment - Cement Downhole Equipment. Use EQPS for surface. | 2.5 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing
362 | MBD-8 | Sidetrack | 2 | 2020-11-11 03:30 | 2020-11-11 15:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 12 | Operator | Star Energy | WW - 2018
363 | MBD-8OH | Drill and Complete | 3 | 2019-03-29 14:00 | 2019-03-29 17:00 | RREQ | DERRICK | Rig Repair - Derrick. | 3 | Rig Contractor | PT. DATI
364 | MBD-8 | Sidetrack | 4 | 2020-11-13 06:00 | 2020-11-13 07:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 1.5 | Rig Contractor | PT. DATI | WW - 2018
365 | MBD-8OH | Drill and Complete | 3 | 2019-03-29 18:00 | 2019-03-30 | RREQ | DERRICK | Rig Repair - Derrick. | 6 | Rig Contractor | PT. DATI
366 | MBD-8 | Sidetrack | 4 | 2020-11-13 11:30 | 2020-11-13 13:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 2 | Rig Contractor | PT. DATI | WW - 2018
367 | MBD-8OH | Drill and Complete | 3 | 2019-03-30 | 2019-03-30 13:30 | RREQ | DERRICK | Rig Repair - Derrick. | 13.5 | Rig Contractor | PT. DATI
368 | MBD-8 | Sidetrack | 5 | 2020-11-20 08:00 | 2020-11-20 08:30 | WP | TIGHT HOLE | Well Problem - Tight hole. | 0.5 | Operator | Star Energy | WW - 2018
369 | MBD-8OH | Drill and Complete | 4 | 2019-04-07 03:45 | 2019-04-07 11:15 | PR | PROC | Process - Procedure changes. | 7.5 | Operator | Star Energy
370 | MBD-8 | Sidetrack | 6 | 2020-11-20 11:30 | 2020-11-21 | WP | TIGHT HOLE | Well Problem - Tight hole. | 12.5 | Operator | Star Energy | WW - 2018
371 | MBD-8OH | Drill and Complete | 5 | 2019-04-10 21:00 | 2019-04-10 22:30 | SP | STUCK | Stuck Pipe - Unknown cause. | 1.5 | Operator | Star Energy
372 | MBD-8 | Sidetrack | 7 | 2020-11-21 19:30 | 2020-11-26 | WP | TIGHT HOLE | Well Problem - Tight hole. | 100.5 | Operator | Star Energy | WW - 2018
373 | MBD-8OH | Drill and Complete | 6 | 2019-04-10 23:30 | 2019-04-22 10:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 274.5 | Operator | Star Energy
374 | MBD-8 | Sidetrack | 8 | 2020-12-02 09:30 | 2020-12-02 10:15 | WO | WATER | Wait On - Water supply. | 0.75 | Rig Contractor | PT. DATI | WW - 2018
375 | MBD-8OH | Drill and Complete | 7 | 2019-04-21 02:00 | 2019-04-22 10:00 | SW | STUCK | Stuck Wireline - General. | 32 | Contractor | SLB - Logging/Wireline Services
376 | MBD-8OH | Drill and Complete | 6 | 2019-04-22 10:00 | 2019-04-22 14:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 4 | Operator | Star Energy
377 | MBD-8OH | Drill and Complete | 8 | 2019-04-22 14:00 | 2019-04-22 16:30 | RRBOP | SURF | Rig Repair - Surface BOP. | 2.5 | Rig Contractor | PT. DATI
378 | MBD-8OH | Drill and Complete | 6 | 2019-04-22 16:30 | 2019-04-22 17:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 0.5 | Operator | Star Energy
379 | MBD-8OH | Drill and Complete | 8 | 2019-04-22 17:00 | 2019-04-22 18:00 | RRBOP | SURF | Rig Repair - Surface BOP. | 1 | Rig Contractor | PT. DATI
380 | MBD-8OH | Drill and Complete | 6 | 2019-04-22 18:00 | 2019-04-23 19:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 25 | Operator | Star Energy
381 | MBD-8OH | Drill and Complete | 9 | 2019-04-23 19:00 | 2019-04-23 23:00 | RREQ | POWER | Rig Repair - Power System. | 4 | Rig Contractor | PT. DATI
382 | MBD-8OH | Drill and Complete | 6 | 2019-04-23 23:00 | 2019-04-29 16:30 | SP | STUCK | Stuck Pipe - Unknown cause. | 49 | Operator | Star Energy
383 | MBD-8OH | Drill and Complete | 10 | 2019-04-29 14:30 | 2019-04-29 15:15 | WC | STEAM | Well Control - Steam influx. | 0.75 | Operator | Star Energy
384 | MBD-8OH | Drill and Complete | 11 | 2019-04-29 16:30 | 2019-04-29 18:00 | WC | STEAM | Well Control - Steam influx. | 1.5 | Operator | Star Energy
385 | MBD-8OH | Drill and Complete | 6 | 2019-04-29 18:00 | 2019-04-30 02:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 8 | Operator | Star Energy
386 | MBD-8OH | Drill and Complete | 12 | 2019-04-30 02:00 | 2019-04-30 02:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Rig Contractor | PT. DATI
387 | MBD-8OH | Drill and Complete | 6 | 2019-04-30 02:30 | 2019-05-04 18:00 | SP | STUCK | Stuck Pipe - Unknown cause. | 111.5 | Operator | Star Energy
388 | MBD-8OH | Drill and Complete | 13 | 2019-05-09 15:30 | 2019-05-10 15:30 | WP | SLTSUT INSTAB | Well Problem - Flowing/mobile shales, salt inclusions. | 8.5 | Operator | Star Energy
389 | MBD-8OH | Drill and Complete | 14 | 2019-05-12 14:00 | 2019-05-12 16:30 | EQPS | CSG HAN | Equipment - Surface Casing Handling. | 2.5 | Rig Contractor | PT. DATI
390 | MBE-6 | Drill and Complete | 1 | 2020-12-22 05:00 | 2020-12-22 08:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 3 | Operator | Star Energy | WW - 2021
391 | MBE-6 | Drill and Complete | 2 | 2020-12-22 09:00 | 2020-12-22 11:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 2 | Operator | Star Energy | WW - 2021
392 | MBE-6 | Drill and Complete | 3 | 2020-12-23 03:00 | 2020-12-23 03:15 | EQP | CSG LN | Equipment - Casing/Liner. Includes accessories, excludes hangers. | 0.25 | Contractor | VarcoIndo | WW - 2021
393 | MBE-6 | Drill and Complete | 4 | 2020-12-24 14:30 | 2020-12-24 19:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 4.75 | Rig Contractor | PT. DATI | WW - 2021
394 | MBE-6 | Drill and Complete | 5 | 2020-12-25 16:30 | 2020-12-25 16:45 | RREQ | DW HOIST | Rig Repair - Drawworks/Hoisting. | 0.25 | Rig Contractor | PT. DATI | WW - 2021
395 | MBE-6 | Drill and Complete | 6 | 2020-12-26 23:15 | 2020-12-27 11:00 | RREQ | EQP | Rig Repair - General Equipment. | 11.75 | Rig Contractor | PT. DATI | WW - 2021
396 | MBE-6 | Drill and Complete | 7 | 2020-12-30 08:30 | 2020-12-30 14:15 | WO | CMT | Wait On - Cement. Waiting on cement. | 5.75 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing | WW - 2021
397 | MBE-6 | Drill and Complete | 8 | 2021-01-01 23:30 | 2021-01-02 00:45 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.5 | Operator | Star Energy | WW - 2021
398 | MBE-6 | Drill and Complete | 9 | 2021-01-02 02:30 | 2021-01-02 03:15 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.75 | Operator | Star Energy | WW - 2021
399 | MBE-6 | Drill and Complete | 10 | 2021-01-02 04:00 | 2021-01-02 05:00 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 1 | Operator | Star Energy | WW - 2021
400 | MBE-7 | Drill and Complete | 1 | 2021-01-09 10:00 | 2021-01-09 17:00 | WP | TIGHT HOLE | Well Problem - Tight hole. | 7 | Operator | Star Energy | WW - 2021
401 | MBE-7 | Drill and Complete | 1 | 2021-01-09 17:15 | 2021-01-09 18:45 | WP | TIGHT HOLE | Well Problem - Tight hole. | 1.5 | Operator | Star Energy | WW - 2021
402 | MBE-7 | Drill and Complete | 2 | 2021-01-09 17:00 | 2021-01-09 17:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.25 | Rig Contractor | PT. DATI | WW - 2021
403 | MBE-7 | Drill and Complete | 3 | 2021-01-19 19:00 | 2021-01-19 22:30 | WO | HES | Wait On - HSE. Safety stand-downs, investigations. | 3.5 | Rig Contractor | PT. DATI | WW - 2021
404 | MBE-7 | Drill and Complete | 3 | 2021-01-20 | 2021-01-20 17:30 | WO | HES | Wait On - HSE. Safety stand-downs, investigations. | 17.5 | Rig Contractor | PT. DATI | WW - 2021
405 | MBE-7 | Drill and Complete | 3 | 2021-01-20 17:45 | 2021-01-20 18:00 | WO | HES | Wait On - HSE. Safety stand-downs, investigations. | 0.25 | Rig Contractor | PT. DATI | WW - 2021
406 | MBE-7 | Drill and Complete | 4 | 2021-01-24 03:15 | 2021-01-24 06:15 | SCL | GEOMETRY | Stuck Casing/Liner - Wellbore geometry. Excessive dogleg. | 3 | Operator | Star Energy | WW - 2021
407 | MBE-7 | Drill and Complete | 5 | 2021-01-24 09:00 | 2021-01-26 05:00 | SCL | GEOMETRY | Stuck Casing/Liner - Wellbore geometry. Excessive dogleg. | 44 | Operator | Star Energy | WW - 2021
408 | MBE-7 | Drill and Complete | 6 | 2021-01-26 06:00 | 2021-01-26 09:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 3.75 | Contractor | PT. DATI | WW - 2021
409 | MBE-7 | Drill and Complete | 7 | 2021-01-29 19:30 | 2021-01-29 20:00 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PT. DATI | WW - 2021
410 | MBE-7 | Drill and Complete | 8 | 2021-01-30 02:15 | 2021-01-30 03:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1 | Contractor | PT. DATI | WW - 2021
411 | MBI-1 | Drill and Complete | 1 | 2021-06-02 12:15 | 2021-06-02 12:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.5 | Contractor | PT. DATI | WW - 2021
412 | MBI-1 | Drill and Complete | 2 | 2021-06-05 09:15 | 2021-06-05 09:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 0.25 | Contractor | PT. DATI | WW - 2021
413 | WWA-8 | Drill and Complete | 1 | 2021-03-26 18:15 | 2021-03-27 14:30 | FISH | FISH ALL OH | Fishing - Open hole operations. | 20.25 | Rig Contractor | PT. DATI | WW - 2021
414 | WWA-8 | Drill and Complete | 2 | 2021-03-31 16:30 | 2021-03-31 22:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 5.75 | Rig Contractor | PT. DATI | WW - 2021
415 | WWA-8 | Drill and Complete | 3 | 2021-04-02 01:00 | 2021-04-02 01:45 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Rig Contractor | PT. DATI | WW - 2021
416 | WWA-8 | Drill and Complete | 4 | 2021-04-06 18:30 | 2021-04-06 19:30 | RREQ | EQP | Rig Repair - General Equipment. | 1 | Rig Contractor | PT. DATI | WW - 2021
417 | WWA-8 | Drill and Complete | 5 | 2021-04-07 17:30 | 2021-04-08 | RREQ | DP | Rig Repair - Dynamic Positioning. | 6.5 | Operator | Star Energy | WW - 2021
418 | WWA-8 | Drill and Complete | 6 | 2021-04-12 20:30 | 2021-04-12 21:15 | RREQ | DP | Rig Repair - Dynamic Positioning. | 0.75 | Rig Contractor | PT. DATI | WW - 2021
419 | WWA-8 | Drill and Complete | 7 | 2021-04-12 21:45 | 2021-04-12 23:30 | RREQ | DP | Rig Repair - Dynamic Positioning. | 1.75 | Rig Contractor | PT. DATI | WW - 2021
420 | WWA-8 | Drill and Complete | 8 | 2021-04-14 22:15 | 2021-04-15 | EQP | BHA | Equipment - BHA. Includes adjustable gauge stabilizers, excludes motors, MWD, bits, reamers. | 1.75 | Operator | Star Energy | WW - 2021
421 | WWA-8 | Drill and Complete | 9 | 2021-04-26 21:00 | 2021-04-26 22:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 1.5 | Rig Contractor | PT. DATI | WW - 2021
422 | WWA-8 | Drill and Complete | 10 | 2021-05-01 23:30 | 2021-05-02 00:15 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 0.75 | Rig Contractor | PT. DATI | WW - 2021
423 | WWA-8 | Drill and Complete | 11 | 2021-05-03 21:45 | 2021-05-03 23:00 | EQPS | CMT | Equipment - Surface Cement. Use EQP for downhole. | 1.25 | Contractor | Dowell Anadrill Schlumberger, PT - Cementing | WW - 2021
424 | WWA-8 | Drill and Complete | 12 | 2021-05-05 14:45 | 2021-05-06 16:30 | RREQ | TOP DRIVE | Rig Repair - Top Drive. | 25.75 | Rig Contractor | PT. DATI | WW - 2021
425 | WWA-8 | Drill and Complete | 13 | 2021-05-06 16:30 | 2021-05-08 15:00 | SP | HOLE CLEAN | Stuck Pipe - Poor hole cleaning. | 46.5 | Rig Contractor | PT. DATI | WW - 2021
426 | WWA-9 | Drill and Complete | 1 | 2021-03-07 19:00 | 2021-03-07 20:30 | RREQ | CIRSYS | Rig Repair - Circulation System/Mud Pumps. | 1.5 | Contractor | PT. DATI | WW - 2021
427 | WWA-9 | Drill and Complete | 2 | 2021-03-08 20:30 | 2021-03-09 04:00 | RREQ | ROT | Rig Repair - Rotary Equipment. | 7.5 | Contractor | PT. DATI | WW - 2021

## Check.Total
Row Labels | Sum of Actual Cost USD
DRJ - 2019 | 42003384.16
DRJ - 2022 | 30669524.9
DRJ - 2024 | 37367109.64
SLK - 2021 | 28051247.74
SLK - 2025 | 38522325.57
WW - 2018 | 26986999.9
WW - 2021 | 27074998.19
Grand Total | 230675590.1

## Drill.Depth.Days
# | Well Name (WellView Version) | Job Category | Report Number | Depth End (MD) | Cum Time Log Days_WV | Depth Progress | Net Depth Progress_WV ft | Report Start Date | Report End Date | Phase | Campaign | dZ ft | dT days | dT flat time days | Year Start Date | Year Start Label | Well Name | Campaign | Well Name (WellView Version)
1 | AWI 8-3 | Drill and Complete | 1 | 0 | 1 |  |  | 1993-03-14 | 1993-03-15 |  | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 10-4 | DRJ - 2019 | DRJ-44
2 | AWI 8-3 | Drill and Complete | 2 | 0 | 2 |  |  | 1993-03-15 | 1993-03-16 |  | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 16-8 | DRJ - 2019 | DRJ-45
3 | AWI 8-3 | Drill and Complete | 3 | 0 | 3 |  |  | 1993-03-16 | 1993-03-17 |  | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 16-9 | DRJ - 2019 | DRJ-46
4 | AWI 8-3 | Drill and Complete | 4 | 0 | 4 |  |  | 1993-03-17 | 1993-03-18 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 21-5 | DRJ - 2019 | DRJ-47
5 | AWI 8-3 | Drill and Complete | 5 | 0 | 5 |  |  | 1993-03-18 | 1993-03-19 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 21-6 | DRJ - 2019 | DRJ-48
6 | AWI 8-3 | Drill and Complete | 6 | 0 | 6 |  |  | 1993-03-19 | 1993-03-20 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 21-7 | DRJ - 2022 | DRJ-38RD
7 | AWI 8-3 | Drill and Complete | 7 | 56 | 7 | 11 | 11 | 1993-03-20 | 1993-03-21 | MOB, RU | A_Others | 56 | 1 | 0 | 1993 | 1993 | AWI 21-8 | DRJ - 2022 | DRJ-49
8 | AWI 8-3 | Drill and Complete | 8 | 56 | 8 | 0 | 0 | 1993-03-21 | 1993-03-22 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 23-1 | DRJ - 2022 | DRJ-50
9 | AWI 8-3 | Drill and Complete | 9 | 56 | 9 | 0 | 0 | 1993-03-22 | 1993-03-23 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 23-2 | DRJ - 2022 | DRJ-51
10 | AWI 8-3 | Drill and Complete | 10 | 400 | 10 | 0 | 0 | 1993-03-23 | 1993-03-24 | MOB, RU | A_Others | 344 | 1 | 0 | 1993 | 1993 | AWI 2-6 | DRJ - 2022 | DRJ-52
11 | AWI 8-3 | Drill and Complete | 11 | 400 | 11 | 0 | 0 | 1993-03-24 | 1993-03-25 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 2-7 ML | DRJ - 2024 | DRJ-53
12 | AWI 8-3 | Drill and Complete | 12 | 400 | 12 | 0 | 0 | 1993-03-25 | 1993-03-26 | MOB, RU | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 3-9 | DRJ - 2024 | DRJ-54
13 | AWI 8-3 | Drill and Complete | 13 | 403 | 13 | 3 | 3 | 1993-03-26 | 1993-03-27 | MOB, RU | A_Others | 3 | 1 | 1 | 1993 | 1993 | AWI 8-3 | DRJ - 2024 | DRJ-55
14 | AWI 8-3 | Drill and Complete | 14 | 403 | 14 | 0 | 0 | 1993-03-27 | 1993-03-28 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | AWI 9-10 | DRJ - 2024 | DRJ-56
15 | AWI 8-3 | Drill and Complete | 15 | 481 | 15 | 0 | 0 | 1993-03-28 | 1993-03-29 | COND, CSGCMT | A_Others | 78 | 1 | 0 | 1993 | 1993 | AWI 9-11 | DRJ - 2024 | DRJ-57
16 | AWI 8-3 | Drill and Complete | 16 | 481 | 16 | 0 | 0 | 1993-03-29 | 1993-03-30 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-16 | SLK - 2021 | AWI 16-8
17 | AWI 8-3 | Drill and Complete | 17 | 481 | 17 | 0 | 0 | 1993-03-30 | 1993-03-31 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-37 | SLK - 2021 | AWI 16-9
18 | AWI 8-3 | Drill and Complete | 18 | 481 | 18 | 0 | 0 | 1993-03-31 | 1993-04-01 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-38 | SLK - 2021 | AWI 21-5
19 | AWI 8-3 | Drill and Complete | 19 | 481 | 19 | 0 | 0 | 1993-04-01 | 1993-04-02 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-38RD | SLK - 2021 | AWI 21-6
20 | AWI 8-3 | Drill and Complete | 20 | 481 | 20 | 0 | 0 | 1993-04-02 | 1993-04-03 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-44 | SLK - 2021 | AWI 9-10
21 | AWI 8-3 | Drill and Complete | 21 | 481 | 21 | 0 | 0 | 1993-04-03 | 1993-04-04 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-45 | SLK - 2025 | AWI 21-7
22 | AWI 8-3 | Drill and Complete | 22 | 481 | 22 | 0 | 0 | 1993-04-04 | 1993-04-05 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-46 | SLK - 2025 | AWI 21-8
23 | AWI 8-3 | Drill and Complete | 23 | 1339 | 23 | 0 | 0 | 1993-04-05 | 1993-04-06 | COND, CSGCMT | A_Others | 858 | 1 | 0 | 1993 | 1993 | DRJ-47 | SLK - 2025 | AWI 23-1
24 | AWI 8-3 | Drill and Complete | 24 | 1339 | 24 | 0 | 0 | 1993-04-06 | 1993-04-07 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-48 | SLK - 2025 | AWI 23-2
25 | AWI 8-3 | Drill and Complete | 25 | 1339 | 25 | 0 | 0 | 1993-04-07 | 1993-04-08 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-49 | SLK - 2025 | AWI 2-6
26 | AWI 8-3 | Drill and Complete | 26 | 1339 | 26 | 0 | 0 | 1993-04-08 | 1993-04-09 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-50 | SLK - 2025 | AWI 2-7 ML
27 | AWI 8-3 | Drill and Complete | 27 | 1339 | 27 | 0 | 0 | 1993-04-09 | 1993-04-10 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-51 | SLK - 2025 | AWI 3-9
28 | AWI 8-3 | Drill and Complete | 28 | 1339 | 28 | 0 | 0 | 1993-04-10 | 1993-04-11 | COND, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-52 | SLK - 2025 | AWI 9-11
29 | AWI 8-3 | Drill and Complete | 29 | 1530 | 29 | 0 | 0 | 1993-04-11 | 1993-04-12 | INTCSG1, CSGCMT | A_Others | 191 | 1 | 0 | 1993 | 1993 | DRJ-53 | WW - 2018 | MBA-6
30 | AWI 8-3 | Drill and Complete | 30 | 1530 | 30 | 0 | 0 | 1993-04-12 | 1993-04-13 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-54 | WW - 2018 | MBA-7
31 | AWI 8-3 | Drill and Complete | 31 | 1530 | 31 | 0 | 0 | 1993-04-13 | 1993-04-14 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-55 | WW - 2018 | MBD-7
32 | AWI 8-3 | Drill and Complete | 32 | 1530 | 32 | 0 | 0 | 1993-04-14 | 1993-04-15 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-56 | WW - 2018 | MBD-8
33 | AWI 8-3 | Drill and Complete | 33 | 1530 | 33 | 0 | 0 | 1993-04-15 | 1993-04-16 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | DRJ-57 | WW - 2021 | MBE-6
34 | AWI 8-3 | Drill and Complete | 34 | 1530 | 34 | 0 | 0 | 1993-04-16 | 1993-04-17 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | HMD-A01 | WW - 2021 | MBE-7
35 | AWI 8-3 | Drill and Complete | 35 | 1530 | 35 | 0 | 0 | 1993-04-17 | 1993-04-18 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | HMD-A02 | WW - 2021 | MBI-1
36 | AWI 8-3 | Drill and Complete | 36 | 1530 | 36 | 0 | 0 | 1993-04-18 | 1993-04-19 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | MBA-6 | WW - 2021 | WWA-8
37 | AWI 8-3 | Drill and Complete | 37 | 1530 | 37 | 0 | 0 | 1993-04-19 | 1993-04-20 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | MBA-7 | WW - 2021 | WWA-9
38 | AWI 8-3 | Drill and Complete | 38 | 1530 | 38 | 0 | 0 | 1993-04-20 | 1993-04-21 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | MBD-7
39 | AWI 8-3 | Drill and Complete | 39 | 3723 | 39 | 0 | 0 | 1993-04-21 | 1993-04-22 | INTCSG1, CSGCMT | A_Others | 2193 | 1 | 0 | 1993 | 1993 | MBD-8
40 | AWI 8-3 | Drill and Complete | 40 | 3723 | 40 | 0 | 0 | 1993-04-22 | 1993-04-23 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | MBE-6
41 | AWI 8-3 | Drill and Complete | 41 | 4505 | 41 | 0 | 0 | 1993-04-23 | 1993-04-24 | DRLGLNR1, CSGCMT | A_Others | 782 | 1 | 0 | 1993 | 1993 | MBE-7
42 | AWI 8-3 | Drill and Complete | 42 | 4505 | 42 | 0 | 0 | 1993-04-24 | 1993-04-25 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | MBI-1
43 | AWI 8-3 | Drill and Complete | 43 | 4505 | 43 | 0 | 0 | 1993-04-25 | 1993-04-26 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | WWA-8
44 | AWI 8-3 | Drill and Complete | 44 | 4505 | 44 | 0 | 0 | 1993-04-26 | 1993-04-27 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993 | WWA-9
45 | AWI 8-3 | Drill and Complete | 45 | 4505 | 45 | 0 | 0 | 1993-04-27 | 1993-04-28 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
46 | AWI 8-3 | Drill and Complete | 46 | 4505 | 46 | 0 | 0 | 1993-04-28 | 1993-04-29 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
47 | AWI 8-3 | Drill and Complete | 47 | 4505 | 47 | 0 | 0 | 1993-04-29 | 1993-04-30 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
48 | AWI 8-3 | Drill and Complete | 48 | 4505 | 48 | 0 | 0 | 1993-04-30 | 1993-05-01 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
49 | AWI 8-3 | Drill and Complete | 49 | 5243 | 49 | 0 | 0 | 1993-05-01 | 1993-05-02 | DRLGLNR1, CSGCMT | A_Others | 738 | 1 | 0 | 1993 | 1993
50 | AWI 8-3 | Drill and Complete | 50 | 5243 | 50 | 0 | 0 | 1993-05-02 | 1993-05-03 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
51 | AWI 8-3 | Drill and Complete | 51 | 5243 | 51 | 0 | 0 | 1993-05-03 | 1993-05-04 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
52 | AWI 8-3 | Drill and Complete | 52 | 6234 | 52 | 0 | 0 | 1993-05-04 | 1993-05-05 | DRLGLNR1, CSGCMT | A_Others | 991 | 1 | 0 | 1993 | 1993
53 | AWI 8-3 | Drill and Complete | 53 | 6234 | 53 | 0 | 0 | 1993-05-05 | 1993-05-06 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
54 | AWI 8-3 | Drill and Complete | 54 | 6234 | 54 | 0 | 0 | 1993-05-06 | 1993-05-07 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
55 | AWI 8-3 | Drill and Complete | 55 | 6946 | 55 | 0 | 0 | 1993-05-07 | 1993-05-08 | DRLGLNR1, CSGCMT | A_Others | 712 | 1 | 0 | 1993 | 1993
56 | AWI 8-3 | Drill and Complete | 56 | 6946 | 56 | 0 | 0 | 1993-05-08 | 1993-05-09 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
57 | AWI 8-3 | Drill and Complete | 57 | 6946 | 57.125 | 0 | 0 | 1993-05-09 | 1993-05-10 | DRLGLNR1, CSGCMT | A_Others | 0 | 1.125 | 1.125 | 1993 | 1993
58 | AWI 8-3 | Drill and Complete | 58 | 7383 | 58.125 | 0 | 0 | 1993-05-10 | 1993-05-11 | DRLGLNR1, CSGCMT | A_Others | 437 | 1 | 0 | 1993 | 1993
59 | AWI 8-3 | Drill and Complete | 59 | 7383 | 59.125 | 0 | 0 | 1993-05-11 | 1993-05-12 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
60 | AWI 8-3 | Drill and Complete | 60 | 7383 | 60.125 | 0 | 0 | 1993-05-12 | 1993-05-13 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
61 | AWI 8-3 | Drill and Complete | 61 | 7383 | 61.125 | 0 | 0 | 1993-05-13 | 1993-05-14 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
62 | AWI 8-3 | Drill and Complete | 62 | 7383 | 62.125 | 0 | 0 | 1993-05-14 | 1993-05-15 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
63 | AWI 8-3 | Drill and Complete | 63 | 7383 | 63.125 | 0 | 0 | 1993-05-15 | 1993-05-16 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
64 | AWI 8-3 | Drill and Complete | 64 | 7950 | 64.125 | 0 | 0 | 1993-05-16 | 1993-05-17 | DRLGLNR, TB | A_Others | 567 | 1 | 0 | 1993 | 1993
65 | AWI 8-3 | Drill and Complete | 65 | 7950 | 65.125 | 0 | 0 | 1993-05-17 | 1993-05-18 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 1993 | 1993
66 | AWI 8-3 | Drill and Complete | 66 | 7950 | 66.125 | 0 | 0 | 1993-05-18 | 1993-05-19 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 1993 | 1993
67 | AWI 8-3 | Drill and Complete | 67 | 7950 | 67.125 | 0 | 0 | 1993-05-19 | 1993-05-20 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 1993 | 1993
68 | AWI 8-3 | Drill and Complete | 68 | 7950 | 68.125 | 0 | 0 | 1993-05-20 | 1993-05-21 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
69 | AWI 8-3 | Drill and Complete | 69 | 7950 | 69.125 | 0 | 0 | 1993-05-21 | 1993-05-22 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 1993 | 1993
70 | DRJ-16 | Drill and Complete | 1 | 0 | 1 |  |  | 1996-12-30 | 1996-12-31 |  | A_Others | 0 | 1 | 1 | 1996 | 1996
71 | DRJ-16 | Drill and Complete | 2 | 0 | 2 |  |  | 1996-12-31 | 1997-01-01 |  | A_Others | 0 | 1 | 1 | 1996 | 1996
72 | DRJ-16 | Drill and Complete | 3 | 0 | 3 |  |  | 1997-01-01 | 1997-01-02 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
73 | DRJ-16 | Drill and Complete | 4 | 0 | 4 |  |  | 1997-01-02 | 1997-01-03 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
74 | DRJ-16 | Drill and Complete | 5 | 0 | 5 |  |  | 1997-01-03 | 1997-01-04 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
75 | DRJ-16 | Drill and Complete | 6 | 0 | 6 |  |  | 1997-01-04 | 1997-01-05 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
76 | DRJ-16 | Drill and Complete | 7 | 0 | 7 |  |  | 1997-01-05 | 1997-01-06 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
77 | DRJ-16 | Drill and Complete | 8 | 0 | 8 |  |  | 1997-01-06 | 1997-01-07 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
78 | DRJ-16 | Drill and Complete | 9 | 0 | 9 |  |  | 1997-01-07 | 1997-01-08 |  | A_Others | 0 | 1 | 1 | 1997 | 1997
79 | DRJ-16 | Drill and Complete | 10 | 0 | 10 |  |  | 1997-01-08 | 1997-01-09 | INTCSG1, DRILL | A_Others | 0 | 1 | 1 | 1997 | 1997
80 | DRJ-16 | Drill and Complete | 11 | 0 | 11 |  |  | 1997-01-09 | 1997-01-10 | INTCSG1, DRILL | A_Others | 0 | 1 | 1 | 1997 | 1997
81 | DRJ-16 | Drill and Complete | 12 | 0 | 12 |  |  | 1997-01-10 | 1997-01-11 | INTCSG1, DRILL | A_Others | 0 | 1 | 1 | 1997 | 1997
82 | DRJ-16 | Drill and Complete | 13 | 0 | 13 |  |  | 1997-01-11 | 1997-01-12 | INTCSG1, DRILL | A_Others | 0 | 1 | 1 | 1997 | 1997
83 | DRJ-16 | Drill and Complete | 14 | 0 | 14 |  |  | 1997-01-12 | 1997-01-13 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
84 | DRJ-16 | Drill and Complete | 15 | 1456 | 15 | 0 | 0 | 1997-01-13 | 1997-01-14 | INTCSG1, CSGCMT | A_Others | 1456 | 1 | 0 | 1997 | 1997
85 | DRJ-16 | Drill and Complete | 16 | 1456 | 15.5833 | 0 | 0 | 1997-01-14 | 1997-01-15 | INTCSG1, CSGCMT | A_Others | 0 | 0.58333 | 0.58333 | 1997 | 1997
86 | DRJ-16 | Drill and Complete | 17 | 1456 | 16.5833 | 0 | 0 | 1997-01-15 | 1997-01-16 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
87 | DRJ-16 | Drill and Complete | 18 | 1456 | 17.5833 | 0 | 0 | 1997-01-16 | 1997-01-17 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
88 | DRJ-16 | Drill and Complete | 19 | 1456 | 18.5833 | 0 | 0 | 1997-01-17 | 1997-01-18 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
89 | DRJ-16 | Drill and Complete | 20 | 1456 | 19.5833 | 0 | 0 | 1997-01-18 | 1997-01-19 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
90 | DRJ-16 | Drill and Complete | 21 | 1456 | 20.5833 | 0 | 0 | 1997-01-19 | 1997-01-20 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
91 | DRJ-16 | Drill and Complete | 22 | 1456 | 21.5833 | 0 | 0 | 1997-01-20 | 1997-01-21 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
92 | DRJ-16 | Drill and Complete | 23 | 1456 | 22.5833 | 0 | 0 | 1997-01-21 | 1997-01-22 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
93 | DRJ-16 | Drill and Complete | 24 | 3237 | 23.5833 | 0 | 0 | 1997-01-22 | 1997-01-23 | INTCSG1, CSGCMT | A_Others | 1781 | 1 | 0 | 1997 | 1997
94 | DRJ-16 | Drill and Complete | 25 | 3237 | 24.5833 | 0 | 0 | 1997-01-23 | 1997-01-24 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
95 | DRJ-16 | Drill and Complete | 26 | 3676 | 25.5833 | 0 | 0 | 1997-01-24 | 1997-01-25 | INTCSG1, CSGCMT | A_Others | 439 | 1 | 0 | 1997 | 1997
96 | DRJ-16 | Drill and Complete | 27 | 3676 | 26.5833 | 0 | 0 | 1997-01-25 | 1997-01-26 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
97 | DRJ-16 | Drill and Complete | 28 | 3940 | 27.5833 | 0 | 0 | 1997-01-26 | 1997-01-27 | DRLGLNR1, CSGCMT | A_Others | 264 | 1 | 0 | 1997 | 1997
98 | DRJ-16 | Drill and Complete | 29 | 3940 | 28.5833 | 0 | 0 | 1997-01-27 | 1997-01-28 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
99 | DRJ-16 | Drill and Complete | 30 | 3940 | 29.5833 | 0 | 0 | 1997-01-28 | 1997-01-29 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
100 | DRJ-16 | Drill and Complete | 31 | 3940 | 30.5833 | 0 | 0 | 1997-01-29 | 1997-01-30 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
101 | DRJ-16 | Drill and Complete | 32 | 3940 | 31.5833 | 0 | 0 | 1997-01-30 | 1997-01-31 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
102 | DRJ-16 | Drill and Complete | 33 | 3891 | 32.5833 | 0 | 0 | 1997-01-31 | 1997-02-01 | DRLGLNR1, CSGCMT | A_Others | -49 | 1 | 1 | 1997 | 1997
103 | DRJ-16 | Drill and Complete | 34 | 4401 | 33.5833 | 0 | 0 | 1997-02-01 | 1997-02-02 | DRLGLNR1, CSGCMT | A_Others | 510 | 1 | 0 | 1997 | 1997
104 | DRJ-16 | Drill and Complete | 35 | 4401 | 34.5833 | 0 | 0 | 1997-02-02 | 1997-02-03 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
105 | DRJ-16 | Drill and Complete | 36 | 4704 | 35.5833 | 0 | 0 | 1997-02-03 | 1997-02-04 | DRLGLNR1, CSGCMT | A_Others | 303 | 1 | 0 | 1997 | 1997
106 | DRJ-16 | Drill and Complete | 37 | 4704 | 36.5833 | 0 | 0 | 1997-02-04 | 1997-02-05 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
107 | DRJ-16 | Drill and Complete | 38 | 4704 | 37.5833 | 0 | 0 | 1997-02-05 | 1997-02-06 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
108 | DRJ-16 | Drill and Complete | 39 | 4704 | 38.5833 | 0 | 0 | 1997-02-06 | 1997-02-07 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
109 | DRJ-16 | Drill and Complete | 40 | 5415 | 39.5833 | 0 | 0 | 1997-02-07 | 1997-02-08 | DRLGLNR1, CSGCMT | A_Others | 711 | 1 | 0 | 1997 | 1997
110 | DRJ-16 | Drill and Complete | 41 | 5415 | 40.5833 | 0 | 0 | 1997-02-08 | 1997-02-09 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
111 | DRJ-16 | Drill and Complete | 42 | 5415 | 41.5833 | 0 | 0 | 1997-02-09 | 1997-02-10 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
112 | DRJ-16 | Drill and Complete | 43 | 6367 | 42.5833 | 0 | 0 | 1997-02-10 | 1997-02-11 | DRLGLNR1, CSGCMT | A_Others | 952 | 1 | 0 | 1997 | 1997
113 | DRJ-16 | Drill and Complete | 44 | 6367 | 43.5833 | 0 | 0 | 1997-02-11 | 1997-02-12 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
114 | DRJ-16 | Drill and Complete | 45 | 6367 | 44.5833 | 0 | 0 | 1997-02-12 | 1997-02-13 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 1997 | 1997
115 | DRJ-37 | Drill and Complete | 1 | 0 | 1 |  |  | 2010-02-13 | 2010-02-14 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
116 | DRJ-37 | Drill and Complete | 2 | 0 | 2 |  |  | 2010-02-14 | 2010-02-15 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
117 | DRJ-37 | Drill and Complete | 3 | 0 | 3 |  |  | 2010-02-15 | 2010-02-16 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
118 | DRJ-37 | Drill and Complete | 4 | 0 | 4 |  |  | 2010-02-16 | 2010-02-17 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
119 | DRJ-37 | Drill and Complete | 5 | 0 | 5 |  |  | 2010-02-17 | 2010-02-18 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
120 | DRJ-37 | Drill and Complete | 6 | 0 | 6 |  |  | 2010-02-18 | 2010-02-19 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
121 | DRJ-37 | Drill and Complete | 7 | 0 | 7 |  |  | 2010-02-19 | 2010-02-20 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
122 | DRJ-37 | Drill and Complete | 8 | 0 | 8 |  |  | 2010-02-20 | 2010-02-21 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
123 | DRJ-37 | Drill and Complete | 9 | 0 | 9 |  |  | 2010-02-21 | 2010-02-22 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
124 | DRJ-37 | Drill and Complete | 10 | 0 | 10 |  |  | 2010-02-22 | 2010-02-23 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
125 | DRJ-37 | Drill and Complete | 11 | 0 | 11 |  |  | 2010-02-23 | 2010-02-24 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
126 | DRJ-37 | Drill and Complete | 12 | 0 | 12 |  |  | 2010-02-24 | 2010-02-25 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
127 | DRJ-37 | Drill and Complete | 13 | 0 | 13 |  |  | 2010-02-25 | 2010-02-26 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
128 | DRJ-37 | Drill and Complete | 14 | 0 | 14 |  |  | 2010-02-26 | 2010-02-27 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
129 | DRJ-37 | Drill and Complete | 15 | 0 | 15 |  |  | 2010-02-27 | 2010-02-28 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
130 | DRJ-37 | Drill and Complete | 16 | 0 | 16 |  |  | 2010-02-28 | 2010-03-01 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
131 | DRJ-37 | Drill and Complete | 17 | 0 | 17 |  |  | 2010-03-01 | 2010-03-02 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
132 | DRJ-37 | Drill and Complete | 18 | 0 | 18 |  |  | 2010-03-02 | 2010-03-03 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
133 | DRJ-37 | Drill and Complete | 19 | 0 | 19 |  |  | 2010-03-03 | 2010-03-04 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
134 | DRJ-37 | Drill and Complete | 20 | 0 | 20 |  |  | 2010-03-04 | 2010-03-05 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
135 | DRJ-37 | Drill and Complete | 21 | 0 | 21 |  |  | 2010-03-05 | 2010-03-06 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
136 | DRJ-37 | Drill and Complete | 22 | 0 | 22 |  |  | 2010-03-06 | 2010-03-07 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
137 | DRJ-37 | Drill and Complete | 23 | 0 | 23 |  |  | 2010-03-07 | 2010-03-08 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
138 | DRJ-37 | Drill and Complete | 24 | 1516 | 24 | 0 | 0 | 2010-03-08 | 2010-03-09 | INTCSG1, CSGCMT | A_Others | 1516 | 1 | 0 | 2010 | 2010
139 | DRJ-37 | Drill and Complete | 25 | 1516 | 25 | 0 | 0 | 2010-03-09 | 2010-03-10 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
140 | DRJ-37 | Drill and Complete | 26 | 1516 | 26 | 0 | 0 | 2010-03-10 | 2010-03-11 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
141 | DRJ-37 | Drill and Complete | 27 | 2748 | 27 | 0 | 0 | 2010-03-11 | 2010-03-12 | INTCSG1, CSGCMT | A_Others | 1232 | 1 | 0 | 2010 | 2010
142 | DRJ-37 | Drill and Complete | 28 | 2748 | 28 | 0 | 0 | 2010-03-12 | 2010-03-13 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
143 | DRJ-37 | Drill and Complete | 29 | 3696.9999 | 29 | 0 | 0 | 2010-03-13 | 2010-03-14 | DRLGLNR1, CSGCMT | A_Others | 948.9999 | 1 | 0 | 2010 | 2010
144 | DRJ-37 | Drill and Complete | 30 | 3696.9999 | 30 | 0 | 0 | 2010-03-14 | 2010-03-15 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
145 | DRJ-37 | Drill and Complete | 31 | 3696.9999 | 31 | 0 | 0 | 2010-03-15 | 2010-03-16 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
146 | DRJ-37 | Drill and Complete | 32 | 3696.9999 | 32 | 0 | 0 | 2010-03-16 | 2010-03-17 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
147 | DRJ-37 | Drill and Complete | 33 | 3696.9999 | 33 | 0 | 0 | 2010-03-17 | 2010-03-18 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
148 | DRJ-37 | Drill and Complete | 34 | 3696.9999 | 34 | 0 | 0 | 2010-03-18 | 2010-03-19 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
149 | DRJ-37 | Drill and Complete | 35 | 3696.9999 | 35 | 0 | 0 | 2010-03-19 | 2010-03-20 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
150 | DRJ-37 | Drill and Complete | 36 | 5118 | 36 | 0 | 0 | 2010-03-20 | 2010-03-21 | DRLGLNR, TB | A_Others | 1421.0001 | 1 | 0 | 2010 | 2010
151 | DRJ-37 | Drill and Complete | 37 | 5118 | 37 | 0 | 0 | 2010-03-21 | 2010-03-22 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
152 | DRJ-37 | Drill and Complete | 38 | 5118 | 38 | 0 | 0 | 2010-03-22 | 2010-03-23 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
153 | DRJ-37 | Drill and Complete | 39 | 6419 | 39 | 0 | 0 | 2010-03-23 | 2010-03-24 | DRLGLNR, TB | A_Others | 1301 | 1 | 0 | 2010 | 2010
154 | DRJ-37 | Drill and Complete | 40 | 6989 | 40 | 0 | 0 | 2010-03-24 | 2010-03-25 | PRODLNR1, CSGCMT | A_Others | 570 | 1 | 0 | 2010 | 2010
155 | DRJ-37 | Drill and Complete | 41 | 7195 | 41 | 206 | 206 | 2010-03-25 | 2010-03-26 | PRODLNR1, CSGCMT | A_Others | 206 | 1 | 0 | 2010 | 2010
156 | DRJ-37 | Drill and Complete | 42 | 7195 | 42 | 0 | 0 | 2010-03-26 | 2010-03-27 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
157 | DRJ-37 | Drill and Complete | 43 | 7672 | 43 | 37 | 37 | 2010-03-27 | 2010-03-28 | PRODLNR1, CSGCMT | A_Others | 477 | 1 | 0 | 2010 | 2010
158 | DRJ-37 | Drill and Complete | 44 | 7672 | 44 | 0 | 0 | 2010-03-28 | 2010-03-29 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
159 | DRJ-37 | Drill and Complete | 45 | 7898.0005 | 45 | 19.0002 | 19.0002 | 2010-03-29 | 2010-03-30 | PRODLNR2, CSGCMT | A_Others | 226.0005 | 1 | 0 | 2010 | 2010
160 | DRJ-37 | Drill and Complete | 46 | 7898.0005 | 45.25 | 0 | 0 | 2010-03-30 | 2010-03-31 | PRODLNR2, CSGCMT | A_Others | 0 | 0.25 | 0.25 | 2010 | 2010
161 | DRJ-38 | Drill and Complete | 1 | 0 | 1 |  |  | 2010-09-25 | 2010-09-26 |  | A_Others | 0 | 1 | 1 | 2010 | 2010
162 | DRJ-38 | Drill and Complete | 2 | 951 | 2 | 777 | 777 | 2010-09-26 | 2010-09-27 |  | A_Others | 951 | 1 | 0 | 2010 | 2010
163 | DRJ-38 | Drill and Complete | 3 | 1232 | 3 | 114 | 114 | 2010-09-27 | 2010-09-28 |  | A_Others | 281 | 1 | 0 | 2010 | 2010
164 | DRJ-38 | Drill and Complete | 4 | 1890.0001 | 4 | 658 | 658 | 2010-09-28 | 2010-09-29 |  | A_Others | 658 | 1 | 0 | 2010 | 2010
165 | DRJ-38 | Drill and Complete | 5 | 2000.0001 | 5 | 110 | 110 | 2010-09-29 | 2010-09-30 | INTCSG1, CSGCMT | A_Others | 110 | 1 | 0 | 2010 | 2010
166 | DRJ-38 | Drill and Complete | 6 | 2000.0001 | 6 | 0 | 0 | 2010-09-30 | 2010-10-01 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
167 | DRJ-38 | Drill and Complete | 7 | 2000.0001 | 7 | 0 | 0 | 2010-10-01 | 2010-10-02 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2010 | 2010
168 | DRJ-38 | Drill and Complete | 8 | 2183.0001 | 8 | 182.9999 | 182.9999 | 2010-10-02 | 2010-10-03 | INTCSG1, CSGCMT | A_Others | 182.9999 | 1 | 0 | 2010 | 2010
169 | DRJ-38 | Drill and Complete | 9 | 2628 | 9 | 445 | 445 | 2010-10-03 | 2010-10-04 | INTCSG1, CSGCMT | A_Others | 445 | 1 | 0 | 2010 | 2010
170 | DRJ-38 | Drill and Complete | 10 | 3184.0001 | 10 | 556 | 556 | 2010-10-04 | 2010-10-05 | INTCSG1, CSGCMT | A_Others | 556 | 1 | 0 | 2010 | 2010
171 | DRJ-38 | Drill and Complete | 11 | 3808.0002 | 11 | 624.0002 | 624.0002 | 2010-10-05 | 2010-10-06 | INTCSG1, CSGCMT | A_Others | 624.0002 | 1 | 0 | 2010 | 2010
172 | DRJ-38 | Drill and Complete | 12 | 4137.0001 | 12 | 328.9999 | 328.9999 | 2010-10-06 | 2010-10-07 | DRLGLNR1, DRILL | A_Others | 328.9999 | 1 | 0 | 2010 | 2010
173 | DRJ-38 | Drill and Complete | 13 | 4611.0002 | 13 | 474.0001 | 474.0001 | 2010-10-07 | 2010-10-08 | DRLGLNR1, DRILL | A_Others | 474.0001 | 1 | 0 | 2010 | 2010
174 | DRJ-38 | Drill and Complete | 14 | 4650.0002 | 14 | 39 | 39 | 2010-10-08 | 2010-10-09 | DRLGLNR1, DRILL | A_Others | 39 | 1 | 1 | 2010 | 2010
175 | DRJ-38 | Drill and Complete | 15 | 4650.0002 | 15 | 0 | 0 | 2010-10-09 | 2010-10-10 | DRLGLNR1, DRILL | A_Others | 0 | 1 | 1 | 2010 | 2010
176 | DRJ-38 | Drill and Complete | 16 | 4650.0002 | 16 | 0 | 0 | 2010-10-10 | 2010-10-11 | DRLGLNR1, DRILL | A_Others | 0 | 1 | 1 | 2010 | 2010
177 | DRJ-38 | Drill and Complete | 17 | 4650.0002 | 17 | 0 | 0 | 2010-10-11 | 2010-10-12 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
178 | DRJ-38 | Drill and Complete | 18 | 4931.9999 | 18 | 281.9996 | 281.9996 | 2010-10-12 | 2010-10-13 | DRLGLNR, TB | A_Others | 281.9996 | 1 | 0 | 2010 | 2010
179 | DRJ-38 | Drill and Complete | 19 | 4650.0002 | 19 | 0 | 0 | 2010-10-13 | 2010-10-14 | DRLGLNR, TB | A_Others | -281.9996 | 1 | 1 | 2010 | 2010
180 | DRJ-38 | Drill and Complete | 20 | 4650.0002 | 20 | 0 | 0 | 2010-10-14 | 2010-10-15 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
181 | DRJ-38 | Drill and Complete | 21 | 4650.0002 | 21 | 0 | 0 | 2010-10-15 | 2010-10-16 | DRLGLNR, TB | A_Others | 0 | 1 | 1 | 2010 | 2010
182 | DRJ-38 | Drill and Complete | 22 | 5105.0001 | 22 | 173.0002 | 173.0002 | 2010-10-16 | 2010-10-17 | DRLGLNR, TB | A_Others | 454.9999 | 1 | 0 | 2010 | 2010
183 | DRJ-38 | Drill and Complete | 23 | 5701 | 23 | 595.9999 | 595.9999 | 2010-10-17 | 2010-10-18 | DRLGLNR, TB | A_Others | 595.9999 | 1 | 0 | 2010 | 2010
184 | DRJ-38 | Drill and Complete | 24 | 5774.9999 | 24 | 73.9999 | 73.9999 | 2010-10-18 | 2010-10-19 | PRODLNR1, CSGCMT | A_Others | 73.9999 | 1 | 0 | 2010 | 2010
185 | DRJ-38 | Drill and Complete | 25 | 6250 | 25 | 475.0001 | 475.0001 | 2010-10-19 | 2010-10-20 | PRODLNR1, CSGCMT | A_Others | 475.0001 | 1 | 0 | 2010 | 2010
186 | DRJ-38 | Drill and Complete | 26 | 6448.0002 | 26 | 198.0002 | 198.0002 | 2010-10-20 | 2010-10-21 | PRODLNR1, CSGCMT | A_Others | 198.0002 | 1 | 0 | 2010 | 2010
187 | DRJ-38 | Drill and Complete | 27 | 6868.0002 | 27 | 420 | 420 | 2010-10-21 | 2010-10-22 | PRODLNR1, CSGCMT | A_Others | 420 | 1 | 0 | 2010 | 2010
188 | DRJ-38 | Drill and Complete | 28 | 7105 | 28 | 236.9998 | 236.9998 | 2010-10-22 | 2010-10-23 | PRODLNR1, CSGCMT | A_Others | 236.9998 | 1 | 0 | 2010 | 2010
189 | DRJ-38 | Drill and Complete | 29 | 7673.9999 | 29 | 568.9998 | 568.9998 | 2010-10-23 | 2010-10-24 | PRODLNR1, CSGCMT | A_Others | 568.9998 | 1 | 0 | 2010 | 2010
190 | DRJ-38 | Drill and Complete | 30 | 7898.0005 | 30 | 224.0006 | 224.0006 | 2010-10-24 | 2010-10-25 | PRODLNR2, CSGCMT | A_Others | 224.0006 | 1 | 0 | 2010 | 2010
191 | DRJ-38 | Drill and Complete | 31 | 8224.0003 | 31 | 325.9998 | 325.9998 | 2010-10-25 | 2010-10-26 | PRODLNR2, CSGCMT | A_Others | 325.9998 | 1 | 0 | 2010 | 2010
192 | DRJ-38 | Drill and Complete | 32 | 8250.0003 | 32 | 26 | 26 | 2010-10-26 | 2010-10-27 | PRODLNR3, CSGCMT | A_Others | 26 | 1 | 1 | 2010 | 2010
193 | AWI 10-4 | Drill and Complete | 1 | 0 | 0.35417 |  |  | 2012-07-08 15:30 | 2012-07-09 |  | A_Others | 0 | 0.35417 | 0.35417 | 2012 | 2012
194 | AWI 10-4 | Drill and Complete | 2 | 0 | 1.3542 |  |  | 2012-07-09 | 2012-07-10 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
195 | AWI 10-4 | Drill and Complete | 3 | 0 | 2.3542 |  |  | 2012-07-10 | 2012-07-11 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
196 | AWI 10-4 | Drill and Complete | 4 | 0 | 3.3542 |  |  | 2012-07-11 | 2012-07-12 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
197 | AWI 10-4 | Drill and Complete | 5 | 0 | 4.3542 |  |  | 2012-07-12 | 2012-07-13 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
198 | AWI 10-4 | Drill and Complete | 6 | 0 | 5.3542 |  |  | 2012-07-13 | 2012-07-14 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
199 | AWI 10-4 | Drill and Complete | 7 | 0 | 6.3542 |  |  | 2012-07-14 | 2012-07-15 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
200 | AWI 10-4 | Drill and Complete | 8 | 0 | 7.3542 |  |  | 2012-07-15 | 2012-07-16 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
201 | AWI 10-4 | Drill and Complete | 9 | 0 | 8.3542 |  |  | 2012-07-16 | 2012-07-17 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
202 | AWI 10-4 | Drill and Complete | 10 | 0 | 9.3542 |  |  | 2012-07-17 | 2012-07-18 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
203 | AWI 10-4 | Drill and Complete | 11 | 0 | 10.3542 |  |  | 2012-07-18 | 2012-07-19 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
204 | AWI 10-4 | Drill and Complete | 12 | 0 | 11.3542 |  |  | 2012-07-19 | 2012-07-20 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
205 | AWI 10-4 | Drill and Complete | 13 | 0 | 12.3542 |  |  | 2012-07-20 | 2012-07-21 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
206 | AWI 10-4 | Drill and Complete | 14 | 0 | 13.3542 |  |  | 2012-07-21 | 2012-07-22 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
207 | AWI 10-4 | Drill and Complete | 15 | 0 | 14.3542 |  |  | 2012-07-22 | 2012-07-23 |  | A_Others | 0 | 1 | 1 | 2012 | 2012
208 | AWI 10-4 | Drill and Complete | 16 | 0 | 15.3542 |  |  | 2012-07-23 | 2012-07-24 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
209 | AWI 10-4 | Drill and Complete | 17 | 0 | 16.3542 |  |  | 2012-07-24 | 2012-07-25 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
210 | AWI 10-4 | Drill and Complete | 18 | 0 | 17.3542 |  |  | 2012-07-25 | 2012-07-26 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
211 | AWI 10-4 | Drill and Complete | 19 | 0 | 18.3542 |  |  | 2012-07-26 | 2012-07-27 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
212 | AWI 10-4 | Drill and Complete | 20 | 0 | 19.3542 |  |  | 2012-07-27 | 2012-07-28 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
213 | AWI 10-4 | Drill and Complete | 21 | 0 | 20.3542 |  |  | 2012-07-28 | 2012-07-29 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
214 | AWI 10-4 | Drill and Complete | 22 | 0 | 21.3542 |  |  | 2012-07-29 | 2012-07-30 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
215 | AWI 10-4 | Drill and Complete | 23 | 0 | 22.3542 |  |  | 2012-07-30 | 2012-07-31 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
216 | AWI 10-4 | Drill and Complete | 24 | 0 | 23.3542 |  |  | 2012-07-31 | 2012-08-01 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
217 | AWI 10-4 | Drill and Complete | 25 | 0 | 24.3542 |  |  | 2012-08-01 | 2012-08-02 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
218 | AWI 10-4 | Drill and Complete | 26 | 0 | 25.3542 |  |  | 2012-08-02 | 2012-08-03 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
219 | AWI 10-4 | Drill and Complete | 27 | 0 | 26.3542 |  |  | 2012-08-03 | 2012-08-04 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
220 | AWI 10-4 | Drill and Complete | 28 | 970 | 27.3542 | 645 | 645 | 2012-08-04 | 2012-08-05 | MOB, RU | A_Others | 970 | 1 | 0 | 2012 | 2012
221 | AWI 10-4 | Drill and Complete | 29 | 1205 | 28.3542 | 235 | 235 | 2012-08-05 | 2012-08-06 | MOB, RU | A_Others | 235 | 1 | 0 | 2012 | 2012
222 | AWI 10-4 | Drill and Complete | 30 | 1205 | 29.3542 | 0 | 0 | 2012-08-06 | 2012-08-07 | MOB, RU | A_Others | 0 | 1 | 1 | 2012 | 2012
223 | AWI 10-4 | Drill and Complete | 31 | 793 | 30.3542 | 21 | 0 | 2012-08-07 | 2012-08-08 | MOB, RU | A_Others | -412 | 1 | 1 | 2012 | 2012
224 | AWI 10-4 | Drill and Complete | 32 | 844 | 31.3542 | 38 | 38 | 2012-08-08 | 2012-08-09 | MOB, RU | A_Others | 51 | 1 | 0 | 2012 | 2012
225 | AWI 10-4 | Drill and Complete | 33 | 857 | 32.3542 | 169 | 13 | 2012-08-09 | 2012-08-10 | MOB, RU | A_Others | 13 | 1 | 1 | 2012 | 2012
226 | AWI 10-4 | Drill and Complete | 34 | 1391 | 33.3542 | 448 | 448 | 2012-08-10 | 2012-08-11 | MOB, RU | A_Others | 534 | 1 | 0 | 2012 | 2012
227 | AWI 10-4 | Drill and Complete | 35 | 1807 | 34.3542 | 416 | 416 | 2012-08-11 | 2012-08-12 | INTCSG1, CSGCMT | A_Others | 416 | 1 | 0 | 2012 | 2012
228 | AWI 10-4 | Drill and Complete | 36 | 1807 | 35.3542 | 0 | 0 | 2012-08-12 | 2012-08-13 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
229 | AWI 10-4 | Drill and Complete | 37 | 2330 | 36.3542 | 523 | 523 | 2012-08-13 | 2012-08-14 | INTCSG1, CSGCMT | A_Others | 523 | 1 | 0 | 2012 | 2012
230 | AWI 10-4 | Drill and Complete | 38 | 3050 | 37.3542 | 720 | 720 | 2012-08-14 | 2012-08-15 | INTCSG1, CSGCMT | A_Others | 720 | 1 | 0 | 2012 | 2012
231 | AWI 10-4 | Drill and Complete | 39 | 3724 | 38.3542 | 674 | 674 | 2012-08-15 | 2012-08-16 | INTCSG1, CSGCMT | A_Others | 674 | 1 | 0 | 2012 | 2012
232 | AWI 10-4 | Drill and Complete | 40 | 4200 | 39.3542 | 476 | 476 | 2012-08-16 | 2012-08-17 | DRLGLNR1, CSGCMT | A_Others | 476 | 1 | 0 | 2012 | 2012
233 | AWI 10-4 | Drill and Complete | 41 | 4200 | 40.3542 | 0 | 0 | 2012-08-17 | 2012-08-18 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
234 | AWI 10-4 | Drill and Complete | 42 | 4200 | 41.3542 | 0 | 0 | 2012-08-18 | 2012-08-19 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
235 | AWI 10-4 | Drill and Complete | 43 | 4200 | 42.3542 | 0 | 0 | 2012-08-19 | 2012-08-20 | DRLGLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
236 | AWI 10-4 | Drill and Complete | 44 | 4969 | 43.3542 | 769 | 769 | 2012-08-20 | 2012-08-21 | DRLGLNR1, CSGCMT | A_Others | 769 | 1 | 0 | 2012 | 2012
237 | AWI 10-4 | Drill and Complete | 45 | 5818 | 44.3542 | 849 | 849 | 2012-08-21 | 2012-08-22 | DRLGLNR1, CSGCMT | A_Others | 849 | 1 | 0 | 2012 | 2012
238 | AWI 10-4 | Drill and Complete | 46 | 6623 | 45.3542 | 805 | 805 | 2012-08-22 | 2012-08-23 | DRLGLNR1, CSGCMT | A_Others | 805 | 1 | 0 | 2012 | 2012
239 | AWI 10-4 | Drill and Complete | 47 | 6623 | 46.3542 | 0 | 0 | 2012-08-23 | 2012-08-24 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
240 | AWI 10-4 | Drill and Complete | 48 | 6623 | 47.3542 | 0 | 0 | 2012-08-24 | 2012-08-25 | PRODLNR1, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
241 | AWI 10-4 | Drill and Complete | 49 | 7591 | 48.3542 | 691 | 691 | 2012-08-25 | 2012-08-26 | PRODLNR1, CSGCMT | A_Others | 968 | 1 | 0 | 2012 | 2012
242 | AWI 10-4 | Drill and Complete | 50 | 8343 | 49.3542 | 752 | 752 | 2012-08-26 | 2012-08-27 | PRODLNR1, CSGCMT | A_Others | 752 | 1 | 0 | 2012 | 2012
243 | AWI 10-4 | Drill and Complete | 51 | 8343 | 50.3542 | 0 | 0 | 2012-08-27 | 2012-08-28 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
244 | AWI 10-4 | Drill and Complete | 52 | 8862 | 51.3542 | 430 | 430 | 2012-08-28 | 2012-08-29 | PRODLNR3, CSGCMT | A_Others | 519 | 1 | 0 | 2012 | 2012
245 | AWI 10-4 | Drill and Complete | 53 | 8862 | 52.3542 | 0 | 0 | 2012-08-29 | 2012-08-30 | PRODLNR3, CSGCMT | A_Others | 0 | 1 | 1 | 2012 | 2012
246 | AWI 10-4 | Drill and Complete | 54 | 8862 | 53.0625 | 0 | 0 | 2012-08-30 | 2012-08-30 17:00 | PRODLNR3, CSGCMT | A_Others | 0 | 0.70833 | 0.70833 | 2012 | 2012
247 | DRJ-37 | Well Services | 1 | 0 | 0.125 |  |  | 2013-12-13 21:00 | 2013-12-14 | PRODLNR2, CSGCMT | A_Others | 0 | 0.125 | 0.125 | 2013 | 2013
248 | DRJ-37 | Well Services | 2 | 0 | 1.125 |  |  | 2013-12-14 | 2013-12-15 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2013 | 2013
249 | DRJ-37 | Well Services | 3 | 0 | 2.125 |  |  | 2013-12-15 | 2013-12-16 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2013 | 2013
250 | DRJ-37 | Well Services | 4 | 0 | 3.125 |  |  | 2013-12-16 | 2013-12-17 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2013 | 2013
251 | DRJ-37 | Well Services | 5 | 0 | 4.125 |  |  | 2013-12-17 | 2013-12-18 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2013 | 2013
252 | DRJ-37 | Well Services | 6 | 0 | 4.6458 |  |  | 2013-12-18 | 2013-12-18 12:30 | PRODLNR2, CSGCMT | A_Others | 0 | 0.52083 | 0.52083 | 2013 | 2013
253 | DRJ-37 | Well Services | 1 | 0 | 0.9375 |  |  | 2015-10-16 01:30 | 2015-10-17 | PRODLNR2, CSGCMT | A_Others | 0 | 0.9375 | 0.9375 | 2015 | 2015
254 | DRJ-37 | Well Services | 2 | 0 | 1.9375 |  |  | 2015-10-17 | 2015-10-18 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2015 | 2015
255 | DRJ-37 | Well Services | 3 | 0 | 2.9375 |  |  | 2015-10-18 | 2015-10-19 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2015 | 2015
256 | DRJ-37 | Well Services | 4 | 0 | 3.9375 |  |  | 2015-10-19 | 2015-10-20 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2015 | 2015
257 | DRJ-37 | Well Services | 5 | 0 | 4.9375 |  |  | 2015-10-20 | 2015-10-21 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2015 | 2015
258 | DRJ-37 | Well Services | 6 | 0 | 5.1042 |  |  | 2015-10-21 | 2015-10-21 04:00 | PRODLNR2, CSGCMT | A_Others | 0 | 0.16667 | 0.16667 | 2015 | 2015
259 | MBA-6 | Drill and Complete | 1 | 343 | 0.39583 | 156 | 156 | 2018-11-27 14:30 | 2018-11-28 |  | WW - 2018 | 343 | 0.39583 | 0 | 2018 | 2018
260 | MBA-6 | Drill and Complete | 2 | 571 | 1.3958 | 228 | 228 | 2018-11-28 | 2018-11-29 |  | WW - 2018 | 228 | 1 | 0 | 2018 | 2018
261 | MBA-6 | Drill and Complete | 3 | 752 | 2.3958 | 181 | 181 | 2018-11-29 | 2018-11-30 |  | WW - 2018 | 181 | 1 | 0 | 2018 | 2018
262 | MBA-6 | Drill and Complete | 4 | 1070 | 3.3958 | 318 | 318 | 2018-11-30 | 2018-12-01 |  | WW - 2018 | 318 | 1 | 0 | 2018 | 2018
263 | MBA-6 | Drill and Complete | 5 | 1070 | 4.3958 | 0 | 0 | 2018-12-01 | 2018-12-02 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
264 | MBA-6 | Drill and Complete | 6 | 1070 | 5.3958 | 0 | 0 | 2018-12-02 | 2018-12-03 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
265 | MBA-6 | Drill and Complete | 7 | 1080 | 6.3958 | 10 | 10 | 2018-12-03 | 2018-12-04 | INTCSG1, CSGCMT | WW - 2018 | 10 | 1 | 1 | 2018 | 2018
266 | MBA-6 | Drill and Complete | 8 | 1306 | 7.3958 | 226 | 226 | 2018-12-04 | 2018-12-05 | INTCSG1, CSGCMT | WW - 2018 | 226 | 1 | 0 | 2018 | 2018
267 | MBA-6 | Drill and Complete | 9 | 1670 | 8.3958 | 364 | 364 | 2018-12-05 | 2018-12-06 | INTCSG1, CSGCMT | WW - 2018 | 364 | 1 | 0 | 2018 | 2018
268 | MBA-6 | Drill and Complete | 10 | 2080 | 9.3958 | 410 | 410 | 2018-12-06 | 2018-12-07 | INTCSG1, CSGCMT | WW - 2018 | 410 | 1 | 0 | 2018 | 2018
269 | MBA-6 | Drill and Complete | 11 | 2384 | 10.3958 | 304 | 304 | 2018-12-07 | 2018-12-08 | INTCSG1, CSGCMT | WW - 2018 | 304 | 1 | 0 | 2018 | 2018
270 | MBA-6 | Drill and Complete | 12 | 2581 | 11.3958 | 197 | 197 | 2018-12-08 | 2018-12-09 | INTCSG1, CSGCMT | WW - 2018 | 197 | 1 | 0 | 2018 | 2018
271 | MBA-6 | Drill and Complete | 13 | 2581 | 12.3958 | 0 | 0 | 2018-12-09 | 2018-12-10 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
272 | MBA-6 | Drill and Complete | 14 | 2581 | 13.3958 | 0 | 0 | 2018-12-10 | 2018-12-11 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
273 | MBA-6 | Drill and Complete | 15 | 2581 | 14.3958 | 0 | 0 | 2018-12-11 | 2018-12-12 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
274 | DRJ-38 | Well Services | 1 | 0 | 1 |  |  | 2018-12-12 | 2018-12-13 | PRODLNR3, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
275 | MBA-6 | Drill and Complete | 16 | 2581 | 15.3958 | 0 | 0 | 2018-12-12 | 2018-12-13 | DRLGLNR1, CSGCMT | WW - 2018 | 2581 | 14.3958 | 0 | 2018 | 2018
276 | MBA-6 | Drill and Complete | 17 | 2581 | 16.3958 | 0 | 0 | 2018-12-13 | 2018-12-14 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
277 | DRJ-38 | Well Services | 2 | 0 | 2 |  |  | 2018-12-13 | 2018-12-14 | PRODLNR3, CSGCMT | A_Others | -2581 | -14.3958 | -14.3958 | 2018 | 2018
278 | DRJ-38 | Well Services | 3 | 0 | 3 |  |  | 2018-12-14 | 2018-12-15 | PRODLNR3, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
279 | MBA-6 | Drill and Complete | 18 | 2581 | 17.3958 | 0 | 0 | 2018-12-14 | 2018-12-15 | DRLGLNR, TB | WW - 2018 | 2581 | 14.3958 | 0 | 2018 | 2018
280 | MBA-6 | Drill and Complete | 19 | 2581 | 18.3958 | 0 | 0 | 2018-12-15 | 2018-12-16 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2018 | 2018
281 | DRJ-38 | Well Services | 4 | 0 | 4 |  |  | 2018-12-15 | 2018-12-16 | PRODLNR3, CSGCMT | A_Others | -2581 | -14.3958 | -14.3958 | 2018 | 2018
282 | MBA-6 | Drill and Complete | 20 | 2681 | 19.3958 | 100 | 100 | 2018-12-16 | 2018-12-17 | DRLGLNR, TB | WW - 2018 | 2681 | 15.3958 | 0 | 2018 | 2018
283 | DRJ-38 | Well Services | 5 | 0 | 5 |  |  | 2018-12-16 | 2018-12-17 | PRODLNR3, CSGCMT | A_Others | -2681 | -14.3958 | -14.3958 | 2018 | 2018
284 | MBA-6 | Drill and Complete | 21 | 3225 | 20.3958 | 544 | 544 | 2018-12-17 | 2018-12-18 | DRLGLNR, TB | WW - 2018 | 3225 | 15.3958 | 0 | 2018 | 2018
285 | DRJ-38 | Well Services | 6 | 0 | 6 |  |  | 2018-12-17 | 2018-12-18 | PRODLNR3, CSGCMT | A_Others | -3225 | -14.3958 | -14.3958 | 2018 | 2018
286 | MBA-6 | Drill and Complete | 22 | 3824 | 21.3958 | 599 | 599 | 2018-12-18 | 2018-12-19 | DRLGLNR, TB | WW - 2018 | 3824 | 15.3958 | 0 | 2018 | 2018
287 | DRJ-38 | Well Services | 7 | 0 | 7 |  |  | 2018-12-18 | 2018-12-19 | PRODLNR3, CSGCMT | A_Others | -3824 | -14.3958 | -14.3958 | 2018 | 2018
288 | DRJ-38 | Well Services | 8 | 0 | 8 |  |  | 2018-12-19 | 2018-12-20 | PRODLNR3, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
289 | MBA-6 | Drill and Complete | 23 | 4270 | 22.3958 | 477 | 477 | 2018-12-19 | 2018-12-20 | DRLGLNR, TB | WW - 2018 | 4270 | 14.3958 | 0 | 2018 | 2018
290 | DRJ-38 | Well Services | 9 | 0 | 9 |  |  | 2018-12-20 | 2018-12-21 | PRODLNR3, CSGCMT | A_Others | -4270 | -13.3958 | -13.3958 | 2018 | 2018
291 | MBA-6 | Drill and Complete | 24 | 4716 | 23.3958 | 446 | 446 | 2018-12-20 | 2018-12-21 | DRLGLNR, TB | WW - 2018 | 4716 | 14.3958 | 0 | 2018 | 2018
292 | DRJ-37 | Well Services | 1 | 0 | 1 |  |  | 2018-12-21 | 2018-12-22 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
293 | MBA-6 | Drill and Complete | 25 | 4716 | 24.3958 | 0 | 0 | 2018-12-21 | 2018-12-22 | PRODLNR1, CSGCMT | WW - 2018 | 4716 | 23.3958 | 0 | 2018 | 2018
294 | DRJ-37 | Well Services | 2 | 0 | 2 |  |  | 2018-12-22 | 2018-12-23 | PRODLNR2, CSGCMT | A_Others | -4716 | -22.3958 | -22.3958 | 2018 | 2018
295 | MBA-6 | Drill and Complete | 26 | 4747 | 25.3958 | 31 | 31 | 2018-12-22 | 2018-12-23 | PRODLNR1, CSGCMT | WW - 2018 | 4747 | 23.3958 | 0 | 2018 | 2018
296 | MBA-6 | Drill and Complete | 27 | 5308 | 26.3958 | 561 | 561 | 2018-12-23 | 2018-12-24 | PRODLNR1, CSGCMT | WW - 2018 | 561 | 1 | 0 | 2018 | 2018
297 | DRJ-37 | Well Services | 3 | 0 | 3 |  |  | 2018-12-23 | 2018-12-24 | PRODLNR2, CSGCMT | A_Others | -5308 | -23.3958 | -23.3958 | 2018 | 2018
298 | MBA-6 | Drill and Complete | 28 | 5732 | 27.3958 | 424 | 424 | 2018-12-24 | 2018-12-25 | PRODLNR1, CSGCMT | WW - 2018 | 5732 | 24.3958 | 0 | 2018 | 2018
299 | DRJ-37 | Well Services | 4 | 0 | 4 |  |  | 2018-12-24 | 2018-12-25 | PRODLNR2, CSGCMT | A_Others | -5732 | -23.3958 | -23.3958 | 2018 | 2018
300 | MBA-6 | Drill and Complete | 29 | 5732 | 28.3958 | 0 | 0 | 2018-12-25 | 2018-12-26 | PRODLNR2, CSGCMT | WW - 2018 | 5732 | 24.3958 | 0 | 2018 | 2018
301 | DRJ-37 | Well Services | 5 | 0 | 5 |  |  | 2018-12-25 | 2018-12-26 | PRODLNR2, CSGCMT | A_Others | -5732 | -23.3958 | -23.3958 | 2018 | 2018
302 | DRJ-37 | Well Services | 6 | 0 | 6 |  |  | 2018-12-26 | 2018-12-27 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
303 | MBA-6 | Drill and Complete | 30 | 5732 | 28.8958 | 0 | 0 | 2018-12-26 | 2018-12-26 12:00 | PRODLNR2, CSGCMT | WW - 2018 | 5732 | 22.8958 | 0 | 2018 | 2018
304 | DRJ-37 | Well Services | 7 | 0 | 7 |  |  | 2018-12-27 | 2018-12-28 | PRODLNR2, CSGCMT | A_Others | -5732 | -21.8958 | -21.8958 | 2018 | 2018
305 | DRJ-37 | Well Services | 8 | 0 | 8 |  |  | 2018-12-28 | 2018-12-29 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2018 | 2018
306 | DRJ-37 | Well Services | 9 | 0 | 8.4167 |  |  | 2018-12-29 | 2018-12-29 10:00 | PRODLNR2, CSGCMT | A_Others | 0 | 0.41667 | 0.41667 | 2018 | 2018
307 | MBA-7 | Drill and Complete | 1 | 338 | 0.33333 | 151 | 151 | 2018-12-29 16:00 | 2018-12-30 |  | WW - 2018 | 338 | 0.33333 | 0 | 2018 | 2018
308 | MBA-7 | Drill and Complete | 2 | 353 | 1.3333 | 15 | 15 | 2018-12-30 | 2018-12-31 |  | WW - 2018 | 15 | 1 | 1 | 2018 | 2018
309 | MBA-7 | Drill and Complete | 3 | 432 | 2.3333 | 79 | 79 | 2018-12-31 | 2019-01-01 |  | WW - 2018 | 79 | 1 | 0 | 2018 | 2018
310 | MBA-7 | Drill and Complete | 4 | 702 | 3.3333 | 270 | 270 | 2019-01-01 | 2019-01-02 |  | WW - 2018 | 270 | 1 | 0 | 2019 | 2019
311 | MBA-7 | Drill and Complete | 5 | 980 | 4.3333 | 278 | 278 | 2019-01-02 | 2019-01-03 |  | WW - 2018 | 278 | 1 | 0 | 2019 | 2019
312 | MBA-7 | Drill and Complete | 6 | 1115 | 5.3333 | 135 | 135 | 2019-01-03 | 2019-01-04 | INTCSG1, CSGCMT | WW - 2018 | 135 | 1 | 0 | 2019 | 2019
313 | MBA-7 | Drill and Complete | 7 | 1115 | 6.3333 | 0 | 0 | 2019-01-04 | 2019-01-05 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
314 | MBA-7 | Drill and Complete | 8 | 1115 | 7.3333 | 0 | 0 | 2019-01-05 | 2019-01-06 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
315 | MBA-7 | Drill and Complete | 9 | 1449 | 8.3333 | 334 | 334 | 2019-01-06 | 2019-01-07 | INTCSG1, CSGCMT | WW - 2018 | 334 | 1 | 0 | 2019 | 2019
316 | MBA-7 | Drill and Complete | 10 | 1909 | 9.3333 | 460 | 460 | 2019-01-07 | 2019-01-08 | INTCSG1, CSGCMT | WW - 2018 | 460 | 1 | 0 | 2019 | 2019
317 | MBA-7 | Drill and Complete | 11 | 2250 | 10.3333 | 341 | 341 | 2019-01-08 | 2019-01-09 | INTCSG1, CSGCMT | WW - 2018 | 341 | 1 | 0 | 2019 | 2019
318 | MBA-7 | Drill and Complete | 12 | 2540 | 11.3333 | 290 | 290 | 2019-01-09 | 2019-01-10 | INTCSG1, CSGCMT | WW - 2018 | 290 | 1 | 0 | 2019 | 2019
319 | MBA-7 | Drill and Complete | 13 | 2540 | 12.3333 | 0 | 0 | 2019-01-10 | 2019-01-11 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
320 | MBA-7 | Drill and Complete | 14 | 2540 | 13.3333 | 0 | 0 | 2019-01-11 | 2019-01-12 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
321 | MBA-7 | Drill and Complete | 15 | 2540 | 14.3333 | 0 | 0 | 2019-01-12 | 2019-01-13 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
322 | MBA-7 | Drill and Complete | 16 | 2540 | 15.3333 | 0 | 0 | 2019-01-13 | 2019-01-14 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
323 | MBA-7 | Drill and Complete | 17 | 2755 | 16.3333 | 215 | 215 | 2019-01-14 | 2019-01-15 | DRLGLNR, TB | WW - 2018 | 215 | 1 | 0 | 2019 | 2019
324 | MBA-7 | Drill and Complete | 18 | 3375 | 17.3333 | 620 | 620 | 2019-01-15 | 2019-01-16 | DRLGLNR, TB | WW - 2018 | 620 | 1 | 0 | 2019 | 2019
325 | MBA-7 | Drill and Complete | 19 | 3629 | 18.3333 | 254 | 254 | 2019-01-16 | 2019-01-17 | DRLGLNR, TB | WW - 2018 | 254 | 1 | 0 | 2019 | 2019
326 | MBA-7 | Drill and Complete | 20 | 3629 | 19.3333 | 0 | 0 | 2019-01-17 | 2019-01-18 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
327 | MBA-7 | Drill and Complete | 21 | 3770 | 20.3333 | 141 | 141 | 2019-01-18 | 2019-01-19 | PRODLNR1, CSGCMT | WW - 2018 | 141 | 1 | 0 | 2019 | 2019
328 | MBA-7 | Drill and Complete | 22 | 4013 | 21.3333 | 243 | 243 | 2019-01-19 | 2019-01-20 | PRODLNR1, CSGCMT | WW - 2018 | 243 | 1 | 0 | 2019 | 2019
329 | MBA-7 | Drill and Complete | 23 | 4325 | 22.3333 | 312 | 312 | 2019-01-20 | 2019-01-21 | PRODLNR1, CSGCMT | WW - 2018 | 312 | 1 | 0 | 2019 | 2019
330 | MBA-7 | Drill and Complete | 24 | 4578 | 23.3333 | 253 | 253 | 2019-01-21 | 2019-01-22 | PRODLNR1, CSGCMT | WW - 2018 | 253 | 1 | 0 | 2019 | 2019
331 | MBA-7 | Drill and Complete | 25 | 4938 | 24.3333 | 360 | 360 | 2019-01-22 | 2019-01-23 | PRODLNR1, CSGCMT | WW - 2018 | 360 | 1 | 0 | 2019 | 2019
332 | MBA-7 | Drill and Complete | 26 | 4965 | 25.3333 | 27 | 27 | 2019-01-23 | 2019-01-24 | PRODLNR1, CSGCMT | WW - 2018 | 27 | 1 | 1 | 2019 | 2019
333 | MBA-7 | Drill and Complete | 27 | 4965 | 26.3333 | 0 | 0 | 2019-01-24 | 2019-01-25 | PRODLNR2, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
334 | MBA-7 | Drill and Complete | 28 | 4965 | 27.3333 | 0 | 0 | 2019-01-25 | 2019-01-26 | PRODLNR2, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
335 | MBA-7 | Drill and Complete | 29 | 4965 | 27.5833 | 0 | 0 | 2019-01-26 | 2019-01-26 06:00 | PRODLNR2, CSGCMT | WW - 2018 | 0 | 0.25 | 0.25 | 2019 | 2019
336 | MBD-7 | Drill and Complete | 1 | 244 | 0.27083 | 58 | 58 | 2019-02-09 17:30 | 2019-02-10 | INTCSG1, DRILL | WW - 2018 | 244 | 0.27083 | 0 | 2019 | 2019
337 | MBD-7 | Drill and Complete | 2 | 545 | 1.2708 | 301 | 301 | 2019-02-10 | 2019-02-11 | INTCSG1, DRILL | WW - 2018 | 301 | 1 | 0 | 2019 | 2019
338 | MBD-7 | Drill and Complete | 3 | 779 | 2.2708 | 234 | 234 | 2019-02-11 | 2019-02-12 | INTCSG1, DRILL | WW - 2018 | 234 | 1 | 0 | 2019 | 2019
339 | MBD-7 | Drill and Complete | 4 | 1032 | 3.2708 | 253 | 253 | 2019-02-12 | 2019-02-13 | INTCSG1, DRILL | WW - 2018 | 253 | 1 | 0 | 2019 | 2019
340 | MBD-7 | Drill and Complete | 5 | 1032 | 4.2708 | 0 | 0 | 2019-02-13 | 2019-02-14 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
341 | MBD-7 | Drill and Complete | 6 | 1032 | 5.2708 |  |  | 2019-02-14 | 2019-02-15 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
342 | MBD-7 | Drill and Complete | 7 | 1251 | 6.2708 | 219 | 219 | 2019-02-15 | 2019-02-16 | INTCSG1, CSGCMT | WW - 2018 | 219 | 1 | 0 | 2019 | 2019
343 | MBD-7 | Drill and Complete | 8 | 1725 | 7.2708 | 474 | 474 | 2019-02-16 | 2019-02-17 | INTCSG1, CSGCMT | WW - 2018 | 474 | 1 | 0 | 2019 | 2019
344 | MBD-7 | Drill and Complete | 9 | 2053 | 8.2708 | 328 | 328 | 2019-02-17 | 2019-02-18 | INTCSG1, CSGCMT | WW - 2018 | 328 | 1 | 0 | 2019 | 2019
345 | MBD-7 | Drill and Complete | 10 | 2310 | 9.2708 | 257 | 257 | 2019-02-18 | 2019-02-19 | INTCSG1, CSGCMT | WW - 2018 | 257 | 1 | 0 | 2019 | 2019
346 | MBD-7 | Drill and Complete | 11 | 2310 | 10.2708 | 0 | 0 | 2019-02-19 | 2019-02-20 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
347 | MBD-7 | Drill and Complete | 12 | 2310 | 11.2708 | 0 | 0 | 2019-02-20 | 2019-02-21 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
348 | MBD-7 | Drill and Complete | 13 | 2310 | 12.2708 | 0 | 0 | 2019-02-21 | 2019-02-22 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
349 | MBD-7 | Drill and Complete | 14 | 2310 | 13.2708 | 0 | 0 | 2019-02-22 | 2019-02-23 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
350 | MBD-7 | Drill and Complete | 15 | 2615 | 14.2708 | 305 | 305 | 2019-02-23 | 2019-02-24 | DRLGLNR, TB | WW - 2018 | 305 | 1 | 0 | 2019 | 2019
351 | MBD-7 | Drill and Complete | 16 | 3180 | 15.2708 | 565 | 565 | 2019-02-24 | 2019-02-25 | DRLGLNR, TB | WW - 2018 | 565 | 1 | 0 | 2019 | 2019
352 | MBD-7 | Drill and Complete | 17 | 3247 | 16.2708 | 67 | 67 | 2019-02-25 | 2019-02-26 | DRLGLNR, TB | WW - 2018 | 67 | 1 | 0 | 2019 | 2019
353 | MBD-7 | Drill and Complete | 18 | 3626 | 17.2708 | 379 | 379 | 2019-02-26 | 2019-02-27 | DRLGLNR, TB | WW - 2018 | 379 | 1 | 0 | 2019 | 2019
354 | MBD-7 | Drill and Complete | 19 | 3721 | 18.2708 | 95 | 95 | 2019-02-27 | 2019-02-28 | DRLGLNR, TB | WW - 2018 | 95 | 1 | 0 | 2019 | 2019
355 | MBD-7 | Drill and Complete | 20 | 3881 | 19.2708 | 160 | 160 | 2019-02-28 | 2019-03-01 | DRLGLNR, TB | WW - 2018 | 160 | 1 | 0 | 2019 | 2019
356 | MBD-7 | Drill and Complete | 21 | 3944 | 20.2708 | 63 | 63 | 2019-03-01 | 2019-03-02 | DRLGLNR, TB | WW - 2018 | 63 | 1 | 0 | 2019 | 2019
357 | MBD-7 | Drill and Complete | 22 | 3944 | 21.2708 | 0 | 0 | 2019-03-02 | 2019-03-03 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
358 | MBD-7 | Drill and Complete | 23 | 3944 | 22.2708 | 0 | 0 | 2019-03-03 | 2019-03-04 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
359 | MBD-7 | Drill and Complete | 24 | 3944 | 23.2708 | 0 | 0 | 2019-03-04 | 2019-03-05 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
360 | MBD-7 | Drill and Complete | 25 | 3944 | 24.2708 | 0 | 0 | 2019-03-05 | 2019-03-06 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
361 | MBD-7 | Drill and Complete | 26 | 4207 | 25.2708 | 263 | 263 | 2019-03-06 | 2019-03-07 | DRLGLNR, TB | WW - 2018 | 263 | 1 | 0 | 2019 | 2019
362 | MBD-7 | Drill and Complete | 27 | 4470 | 26.2708 | 263 | 263 | 2019-03-07 | 2019-03-08 | DRLGLNR, TB | WW - 2018 | 263 | 1 | 0 | 2019 | 2019
363 | MBD-7 | Drill and Complete | 28 | 4700 | 27.2708 | 230 | 230 | 2019-03-08 | 2019-03-09 | DRLGLNR, TB | WW - 2018 | 230 | 1 | 0 | 2019 | 2019
364 | MBD-7 | Drill and Complete | 29 | 4820 | 28.2708 | 120 | 120 | 2019-03-09 | 2019-03-10 | DRLGLNR, TB | WW - 2018 | 120 | 1 | 0 | 2019 | 2019
365 | MBD-7 | Drill and Complete | 30 | 4997 | 29.2708 | 177 | 177 | 2019-03-10 | 2019-03-11 | DRLGLNR, TB | WW - 2018 | 177 | 1 | 0 | 2019 | 2019
366 | MBD-7 | Drill and Complete | 31 | 4997 | 30.2708 | 0 | 0 | 2019-03-11 | 2019-03-12 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
367 | MBD-7 | Drill and Complete | 32 | 4997 | 31.2708 | 0 | 0 | 2019-03-12 | 2019-03-13 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
368 | MBD-7 | Drill and Complete | 33 | 4997 | 32.2708 | 0 | 0 | 2019-03-13 | 2019-03-14 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
369 | MBD-7 | Drill and Complete | 34 | 4997 | 33.2708 | 0 | 0 | 2019-03-14 | 2019-03-15 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
370 | MBD-7 | Drill and Complete | 35 | 4997 | 34.2708 | 0 | 0 | 2019-03-15 | 2019-03-16 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
371 | MBD-7 | Drill and Complete | 36 | 4997 | 35.2708 | 0 | 0 | 2019-03-16 | 2019-03-17 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
372 | MBD-7 | Drill and Complete | 37 | 4997 | 36.2708 | 0 | 0 | 2019-03-17 | 2019-03-18 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
373 | MBD-7 | Drill and Complete | 38 | 4997 | 37.2708 | 0 | 0 | 2019-03-18 | 2019-03-19 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
374 | MBD-7 | Drill and Complete | 39 | 4997 | 38.2708 | 0 | 0 | 2019-03-19 | 2019-03-20 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
375 | MBD-7 | Drill and Complete | 40 | 4997 | 38.7708 | 0 | 0 | 2019-03-20 | 2019-03-21 12:00 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 0.5 | 0.5 | 2019 | 2019
376 | AWI 8-3 | Well Services | 1 | 0 | 1 |  |  | 2019-03-21 | 2019-03-22 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
377 | AWI 8-3 | Well Services | 2 | 0 | 2 |  |  | 2019-03-22 | 2019-03-23 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
378 | AWI 8-3 | Well Services | 3 | 0 | 3 |  |  | 2019-03-23 | 2019-03-24 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
379 | AWI 8-3 | Well Services | 4 | 0 | 4 |  |  | 2019-03-24 | 2019-03-25 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
380 | AWI 8-3 | Well Services | 5 | 0 | 5 |  |  | 2019-03-25 | 2019-03-26 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
381 | MBD-8 | Drill and Complete | 1 | 401 | 0.85417 | 214 | 214 | 2019-03-25 03:30 | 2019-03-26 |  | WW - 2018 | 401 | 0.85417 | 0 | 2019 | 2019
382 | MBD-8 | Drill and Complete | 2 | 401 | 1.8542 | 0 | 0 | 2019-03-26 | 2019-03-27 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
383 | AWI 8-3 | Well Services | 6 | 0 | 6 |  |  | 2019-03-26 | 2019-03-27 | PRODLNR2, CSGCMT | A_Others | -401 | 4.1458 | 4.1458 | 2019 | 2019
384 | AWI 8-3 | Well Services | 7 | 0 | 7 |  |  | 2019-03-27 | 2019-03-28 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
385 | MBD-8 | Drill and Complete | 3 | 1032 | 2.8542 | 248 | 248 | 2019-03-27 | 2019-03-28 |  | WW - 2018 | 1032 | -4.1458 | 0 | 2019 | 2019
386 | MBD-8 | Drill and Complete | 4 | 1032 | 3.8542 | 0 | 0 | 2019-03-28 | 2019-03-29 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
387 | AWI 8-3 | Well Services | 8 | 0 | 8 |  |  | 2019-03-28 | 2019-03-29 | PRODLNR2, CSGCMT | A_Others | -1032 | 4.1458 | 4.1458 | 2019 | 2019
388 | AWI 8-3 | Well Services | 9 | 0 | 9 |  |  | 2019-03-29 | 2019-03-30 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
389 | MBD-8 | Drill and Complete | 5 | 1032 | 4.8542 | 0 | 0 | 2019-03-29 | 2019-03-30 | INTCSG1, CSGCMT | WW - 2018 | 1032 | -4.1458 | 0 | 2019 | 2019
390 | AWI 8-3 | Well Services | 10 | 0 | 10 |  |  | 2019-03-30 | 2019-03-31 | PRODLNR2, CSGCMT | A_Others | -1032 | 5.1458 | 5.1458 | 2019 | 2019
391 | MBD-8 | Drill and Complete | 6 | 1032 | 5.8542 | 0 | 0 | 2019-03-30 | 2019-03-31 | INTCSG1, CSGCMT | WW - 2018 | 1032 | -4.1458 | 0 | 2019 | 2019
392 | MBD-8 | Drill and Complete | 7 | 1032 | 6.8542 | 0 | 0 | 2019-03-31 | 2019-04-01 | INTCSG1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
393 | AWI 8-3 | Well Services | 11 | 0 | 11 |  |  | 2019-03-31 | 2019-04-01 | PRODLNR2, CSGCMT | A_Others | -1032 | 4.1458 | 4.1458 | 2019 | 2019
394 | AWI 8-3 | Well Services | 12 | 0 | 12 |  |  | 2019-04-01 | 2019-04-02 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
395 | MBD-8 | Drill and Complete | 8 | 1730 | 7.8542 | 409 | 409 | 2019-04-01 | 2019-04-02 | INTCSG1, CSGCMT | WW - 2018 | 1730 | -4.1458 | 0 | 2019 | 2019
396 | MBD-8 | Drill and Complete | 9 | 2222 | 8.8542 | 492 | 492 | 2019-04-02 | 2019-04-03 | INTCSG1, CSGCMT | WW - 2018 | 492 | 1 | 0 | 2019 | 2019
397 | AWI 8-3 | Well Services | 13 | 0 | 13 |  |  | 2019-04-02 | 2019-04-03 | PRODLNR2, CSGCMT | A_Others | -2222 | 4.1458 | 4.1458 | 2019 | 2019
398 | AWI 8-3 | Well Services | 14 | 0 | 14 |  |  | 2019-04-03 | 2019-04-04 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2019 | 2019
399 | MBD-8 | Drill and Complete | 10 | 2222 | 9.8542 | 0 | 0 | 2019-04-03 | 2019-04-04 | DRLGLNR1, CSGCMT | WW - 2018 | 2222 | -4.1458 | 0 | 2019 | 2019
400 | MBD-8 | Drill and Complete | 11 | 2222 | 10.8542 | 0 | 0 | 2019-04-04 | 2019-04-05 | DRLGLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
401 | AWI 8-3 | Well Services | 15 | 0 | 14.3958 |  |  | 2019-04-04 | 2019-04-05 09:30 | PRODLNR2, CSGCMT | A_Others | -2222 | 3.5417 | 3.5417 | 2019 | 2019
402 | AWI 10-4 | Well Services | 1 | 0 | 0.60417 |  |  | 2019-04-04 09:30 | 2019-04-05 | PRODLNR3, CSGCMT | A_Others | 0 | 0.60417 | 0.60417 | 2019 | 2019
403 | MBD-8 | Drill and Complete | 12 | 2222 | 11.8542 | 0 | 0 | 2019-04-05 | 2019-04-06 | DRLGLNR, TB | WW - 2018 | 2222 | 11.25 | 0 | 2019 | 2019
404 | AWI 10-4 | Well Services | 2 | 0 | 1.6042 |  |  | 2019-04-05 | 2019-04-06 | PRODLNR3, CSGCMT | A_Others | -2222 | -10.25 | -10.25 | 2019 | 2019
405 | MBD-8 | Drill and Complete | 13 | 2222 | 12.8542 | 0 | 0 | 2019-04-06 | 2019-04-07 | DRLGLNR, TB | WW - 2018 | 2222 | 11.25 | 0 | 2019 | 2019
406 | AWI 10-4 | Well Services | 3 | 0 | 2.6042 |  |  | 2019-04-06 | 2019-04-07 | PRODLNR3, CSGCMT | A_Others | -2222 | -10.25 | -10.25 | 2019 | 2019
407 | MBD-8 | Drill and Complete | 14 | 2364 | 13.8542 | 142 | 142 | 2019-04-07 | 2019-04-08 | DRLGLNR, TB | WW - 2018 | 2364 | 11.25 | 0 | 2019 | 2019
408 | AWI 10-4 | Well Services | 4 | 0 | 3.6042 |  |  | 2019-04-07 | 2019-04-08 | PRODLNR3, CSGCMT | A_Others | -2364 | -10.25 | -10.25 | 2019 | 2019
409 | MBD-8 | Drill and Complete | 15 | 3085 | 14.8542 | 721 | 721 | 2019-04-08 | 2019-04-09 | DRLGLNR, TB | WW - 2018 | 3085 | 11.25 | 0 | 2019 | 2019
410 | MBD-8 | Drill and Complete | 16 | 3559 | 15.8542 | 474 | 474 | 2019-04-09 | 2019-04-10 | DRLGLNR, TB | WW - 2018 | 474 | 1 | 0 | 2019 | 2019
411 | MBD-8 | Drill and Complete | 17 | 3998 | 16.8542 | 439 | 439 | 2019-04-10 | 2019-04-11 | DRLGLNR, TB | WW - 2018 | 439 | 1 | 0 | 2019 | 2019
412 | MBD-8 | Drill and Complete | 18 | 3998 | 17.8542 | 0 | 0 | 2019-04-11 | 2019-04-12 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
413 | MBD-8 | Drill and Complete | 19 | 3998 | 18.8542 | 0 | 0 | 2019-04-12 | 2019-04-13 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
414 | MBD-8 | Drill and Complete | 20 | 3998 | 19.8542 | 0 | 0 | 2019-04-13 | 2019-04-14 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
415 | MBD-8 | Drill and Complete | 21 | 3998 | 20.8542 | 0 | 0 | 2019-04-14 | 2019-04-15 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
416 | MBD-8 | Drill and Complete | 22 | 3998 | 21.8542 | 0 | 0 | 2019-04-15 | 2019-04-16 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
417 | MBD-8 | Drill and Complete | 23 | 3998 | 22.8542 | 0 | 0 | 2019-04-16 | 2019-04-17 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
418 | MBD-8 | Drill and Complete | 24 | 3998 | 23.8542 | 0 | 0 | 2019-04-17 | 2019-04-18 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
419 | MBD-8 | Drill and Complete | 25 | 3998 | 24.8542 | 0 | 0 | 2019-04-18 | 2019-04-19 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
420 | MBD-8 | Drill and Complete | 26 | 3998 | 25.8542 | 0 | 0 | 2019-04-19 | 2019-04-20 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
421 | MBD-8 | Drill and Complete | 27 | 3998 | 26.8542 | 0 | 0 | 2019-04-20 | 2019-04-21 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
422 | MBD-8 | Drill and Complete | 28 | 3998 | 27.8542 | 0 | 0 | 2019-04-21 | 2019-04-22 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
423 | MBD-8 | Drill and Complete | 29 | 3998 | 28.8542 | 0 | 0 | 2019-04-22 | 2019-04-23 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
424 | MBD-8 | Drill and Complete | 30 | 3998 | 29.8542 | 0 | 0 | 2019-04-23 | 2019-04-24 | DRLGLNR, TB | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
425 | MBD-8 | Drill and Complete | 31 | 3998 | 30.8542 | 0 | 0 | 2019-04-24 | 2019-04-25 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
426 | MBD-8 | Drill and Complete | 32 | 2449 | 31.8542 | 156 | 156 | 2019-04-25 | 2019-04-26 |  | WW - 2018 | -1549 | 1 | 1 | 2019 | 2019
427 | MBD-8 | Drill and Complete | 33 | 2920 | 32.8542 | 471 | 471 | 2019-04-26 | 2019-04-27 |  | WW - 2018 | 471 | 1 | 0 | 2019 | 2019
428 | MBD-8 | Drill and Complete | 34 | 3360 | 33.8542 | 440 | 440 | 2019-04-27 | 2019-04-28 |  | WW - 2018 | 440 | 1 | 0 | 2019 | 2019
429 | MBD-8 | Drill and Complete | 35 | 3517 | 34.8542 | 157 | 157 | 2019-04-28 | 2019-04-29 |  | WW - 2018 | 157 | 1 | 0 | 2019 | 2019
430 | MBD-8 | Drill and Complete | 36 | 3591 | 35.8542 | 74 | 74 | 2019-04-29 | 2019-04-30 |  | WW - 2018 | 74 | 1 | 0 | 2019 | 2019
431 | DRJ-16 | Well Services | 1 | 0 |  |  |  | 2019-04-29 06:00 | 2019-04-30 | PRODLNR1, CSGCMT | A_Others | 0 | 0 | 0 | 2019 | 2019
432 | MBD-8 | Drill and Complete | 37 | 3591 | 36.8542 | 0 | 0 | 2019-04-30 | 2019-05-01 |  | WW - 2018 | 3591 | 36.8542 | 0 | 2019 | 2019
433 | MBD-8 | Drill and Complete | 38 | 3591 | 37.8542 | 0 | 0 | 2019-05-01 | 2019-05-02 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
434 | MBD-8 | Drill and Complete | 39 | 3591 | 38.8542 | 0 | 0 | 2019-05-02 | 2019-05-03 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
435 | MBD-8 | Drill and Complete | 40 | 3764 | 39.8542 | 173 | 173 | 2019-05-03 | 2019-05-04 |  | WW - 2018 | 173 | 1 | 0 | 2019 | 2019
436 | MBD-8 | Drill and Complete | 41 | 4022 | 40.8542 | 258 | 258 | 2019-05-04 | 2019-05-05 |  | WW - 2018 | 258 | 1 | 0 | 2019 | 2019
437 | MBD-8 | Drill and Complete | 42 | 4024 | 41.8542 | 2 | 2 | 2019-05-05 | 2019-05-06 |  | WW - 2018 | 2 | 1 | 1 | 2019 | 2019
438 | MBD-8 | Drill and Complete | 43 | 4052 | 42.8542 | 28 | 28 | 2019-05-06 | 2019-05-07 |  | WW - 2018 | 28 | 1 | 1 | 2019 | 2019
439 | MBD-8 | Drill and Complete | 44 | 4052 | 43.8542 | 0 | 0 | 2019-05-07 | 2019-05-08 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
440 | MBD-8 | Drill and Complete | 45 | 4083 | 44.8542 | 31 | 31 | 2019-05-08 | 2019-05-09 |  | WW - 2018 | 31 | 1 | 1 | 2019 | 2019
441 | MBD-8 | Drill and Complete | 46 | 4083 | 45.8542 | 0 | 0 | 2019-05-09 | 2019-05-10 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
442 | MBD-8 | Drill and Complete | 47 | 4083 | 46.8542 | 0 | 0 | 2019-05-10 | 2019-05-11 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
443 | MBD-8 | Drill and Complete | 48 | 4083 | 47.8542 | 0 | 0 | 2019-05-11 | 2019-05-12 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
444 | MBD-8 | Drill and Complete | 49 | 4083 | 48.8542 | 0 | 0 | 2019-05-12 | 2019-05-13 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
445 | MBD-8 | Drill and Complete | 50 | 4083 | 49.8542 | 0 | 0 | 2019-05-13 | 2019-05-14 |  | WW - 2018 | 0 | 1 | 1 | 2019 | 2019
446 | MBD-8 | Drill and Complete | 51 | 4083 | 50.6042 | 0 | 0 | 2019-05-14 | 2019-05-14 18:00 |  | WW - 2018 | 0 | 0.75 | 0.75 | 2019 | 2019
447 | DRJ-44 | Drill and Complete | 1 | 275 | 0.375 | 95 | 95 | 2019-06-24 15:00 | 2019-06-25 | SURF, DRILL | DRJ - 2019 | 275 | 0.375 | 0 | 2019 | 2019
448 | DRJ-44 | Drill and Complete | 2 | 418 | 1.375 | 143 | 143 | 2019-06-25 | 2019-06-26 | SURF, DRILL | DRJ - 2019 | 143 | 1 | 0 | 2019 | 2019
449 | DRJ-44 | Drill and Complete | 3 | 730 | 2.375 | 312 | 312 | 2019-06-26 | 2019-06-27 | SURF, DRILL | DRJ - 2019 | 312 | 1 | 0 | 2019 | 2019
450 | DRJ-44 | Drill and Complete | 4 | 969 | 3.375 | 239 | 239 | 2019-06-27 | 2019-06-28 | SURF, DRILL | DRJ - 2019 | 239 | 1 | 0 | 2019 | 2019
451 | DRJ-44 | Drill and Complete | 5 | 1398 | 4.375 | 429 | 429 | 2019-06-28 | 2019-06-29 | SURF, DRILL | DRJ - 2019 | 429 | 1 | 0 | 2019 | 2019
452 | DRJ-44 | Drill and Complete | 6 | 1398 | 5.375 | 0 | 0 | 2019-06-29 | 2019-06-30 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
453 | DRJ-44 | Drill and Complete | 7 | 1398 | 6.375 | 0 | 0 | 2019-06-30 | 2019-07-01 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
454 | DRJ-44 | Drill and Complete | 8 | 1529 | 7.375 | 121 | 121 | 2019-07-01 | 2019-07-02 | SURF, DRILL | DRJ - 2019 | 131 | 1 | 0 | 2019 | 2019
455 | DRJ-44 | Drill and Complete | 9 | 2172 | 8.375 | 643 | 643 | 2019-07-02 | 2019-07-03 | SURF, DRILL | DRJ - 2019 | 643 | 1 | 0 | 2019 | 2019
456 | DRJ-44 | Drill and Complete | 10 | 2538 | 9.375 | 366 | 366 | 2019-07-03 | 2019-07-04 | SURF, DRILL | DRJ - 2019 | 366 | 1 | 0 | 2019 | 2019
457 | DRJ-44 | Drill and Complete | 11 | 2696 | 10.375 | 158 | 158 | 2019-07-04 | 2019-07-05 | SURF, DRILL | DRJ - 2019 | 158 | 1 | 0 | 2019 | 2019
458 | DRJ-44 | Drill and Complete | 12 | 2873 | 11.375 | 177 | 177 | 2019-07-05 | 2019-07-06 | SURF, DRILL | DRJ - 2019 | 177 | 1 | 0 | 2019 | 2019
459 | DRJ-44 | Drill and Complete | 13 | 2899 | 12.375 | 26 | 26 | 2019-07-06 | 2019-07-07 | SURF, DRILL | DRJ - 2019 | 26 | 1 | 1 | 2019 | 2019
460 | DRJ-44 | Drill and Complete | 14 | 2899 | 13.375 | 0 | 0 | 2019-07-07 | 2019-07-08 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
461 | DRJ-44 | Drill and Complete | 15 | 2899 | 14.375 | 0 | 0 | 2019-07-08 | 2019-07-09 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
462 | DRJ-44 | Drill and Complete | 16 | 3028 | 15.375 | 129 | 129 | 2019-07-09 | 2019-07-10 | SURF, DRILL | DRJ - 2019 | 129 | 1 | 0 | 2019 | 2019
463 | DRJ-44 | Drill and Complete | 17 | 3187 | 16.375 | 159 | 159 | 2019-07-10 | 2019-07-11 | SURF, DRILL | DRJ - 2019 | 159 | 1 | 0 | 2019 | 2019
464 | DRJ-44 | Drill and Complete | 18 | 3230 | 17.375 | 43 | 43 | 2019-07-11 | 2019-07-12 | SURF, DRILL | DRJ - 2019 | 43 | 1 | 1 | 2019 | 2019
465 | DRJ-44 | Drill and Complete | 19 | 3230 | 18.375 | 0 | 0 | 2019-07-12 | 2019-07-13 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
466 | DRJ-44 | Drill and Complete | 20 | 3230 | 19.375 | 0 | 0 | 2019-07-13 | 2019-07-14 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
467 | DRJ-44 | Drill and Complete | 21 | 3230 | 20.375 | 0 | 0 | 2019-07-14 | 2019-07-15 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
468 | DRJ-44 | Drill and Complete | 22 | 3230 | 21.375 | 0 | 0 | 2019-07-15 | 2019-07-16 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
469 | DRJ-44 | Drill and Complete | 23 | 3230 | 22.375 | 0 | 0 | 2019-07-16 | 2019-07-17 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
470 | DRJ-44 | Drill and Complete | 24 | 3230 | 23.375 | 0 | 0 | 2019-07-17 | 2019-07-18 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
471 | DRJ-44 | Drill and Complete | 25 | 3230 | 24.375 | 0 | 0 | 2019-07-18 | 2019-07-19 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
472 | DRJ-44 | Drill and Complete | 26 | 3479 | 25.375 | 249 | 249 | 2019-07-19 | 2019-07-20 | DRLGLNR, TB | DRJ - 2019 | 249 | 1 | 0 | 2019 | 2019
473 | DRJ-44 | Drill and Complete | 27 | 3809 | 26.375 | 330 | 330 | 2019-07-20 | 2019-07-21 | DRLGLNR, TB | DRJ - 2019 | 330 | 1 | 0 | 2019 | 2019
474 | DRJ-44 | Drill and Complete | 28 | 4080 | 27.375 | 271 | 271 | 2019-07-21 | 2019-07-22 | DRLGLNR, TB | DRJ - 2019 | 271 | 1 | 0 | 2019 | 2019
475 | DRJ-44 | Drill and Complete | 29 | 4139 | 28.375 | 59 | 59 | 2019-07-22 | 2019-07-23 | DRLGLNR, TB | DRJ - 2019 | 59 | 1 | 0 | 2019 | 2019
476 | DRJ-44 | Drill and Complete | 30 | 4327 | 29.375 | 188 | 188 | 2019-07-23 | 2019-07-24 | DRLGLNR, TB | DRJ - 2019 | 188 | 1 | 0 | 2019 | 2019
477 | DRJ-44 | Drill and Complete | 31 | 4830 | 30.375 | 503 | 503 | 2019-07-24 | 2019-07-25 | DRLGLNR, TB | DRJ - 2019 | 503 | 1 | 0 | 2019 | 2019
478 | DRJ-44 | Drill and Complete | 32 | 5273 | 31.375 | 443 | 443 | 2019-07-25 | 2019-07-26 | DRLGLNR, TB | DRJ - 2019 | 443 | 1 | 0 | 2019 | 2019
479 | DRJ-44 | Drill and Complete | 33 | 5522 | 32.375 | 249 | 249 | 2019-07-26 | 2019-07-27 | DRLGLNR, TB | DRJ - 2019 | 249 | 1 | 0 | 2019 | 2019
480 | DRJ-44 | Drill and Complete | 34 | 5703 | 33.375 | 181 | 181 | 2019-07-27 | 2019-07-28 | DRLGLNR, TB | DRJ - 2019 | 181 | 1 | 0 | 2019 | 2019
481 | DRJ-44 | Drill and Complete | 35 | 5860 | 34.375 | 157 | 157 | 2019-07-28 | 2019-07-29 | PRODLNR1, CSGCMT | DRJ - 2019 | 157 | 1 | 0 | 2019 | 2019
482 | DRJ-44 | Drill and Complete | 36 | 5860 | 35.375 | 0 | 0 | 2019-07-29 | 2019-07-30 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
483 | DRJ-44 | Drill and Complete | 37 | 5860 | 36.0417 | 0 | 0 | 2019-07-30 | 2019-07-30 18:00 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 0.66667 | 0.66667 | 2019 | 2019
484 | DRJ-45 | Drill and Complete | 1 | 296 | 0.22917 | 96 | 96 | 2019-08-15 18:30 | 2019-08-16 | SURF, DRILL | DRJ - 2019 | 296 | 0.22917 | 0 | 2019 | 2019
485 | DRJ-45 | Drill and Complete | 2 | 576 | 1.2292 | 280 | 280 | 2019-08-16 | 2019-08-17 | SURF, DRILL | DRJ - 2019 | 280 | 1 | 0 | 2019 | 2019
486 | DRJ-45 | Drill and Complete | 3 | 599 | 2.2292 | 23 | 23 | 2019-08-17 | 2019-08-18 | SURF, DRILL | DRJ - 2019 | 23 | 1 | 1 | 2019 | 2019
487 | DRJ-45 | Drill and Complete | 4 | 599 | 3.2292 | 0 | 0 | 2019-08-18 | 2019-08-19 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
488 | DRJ-45 | Drill and Complete | 5 | 841 | 4.2292 | 191 | 191 | 2019-08-19 | 2019-08-20 | SURF, DRILL | DRJ - 2019 | 242 | 1 | 0 | 2019 | 2019
489 | DRJ-45 | Drill and Complete | 6 | 1193 | 5.2292 | 352 | 352 | 2019-08-20 | 2019-08-21 | SURF, DRILL | DRJ - 2019 | 352 | 1 | 0 | 2019 | 2019
490 | DRJ-45 | Drill and Complete | 7 | 1378 | 6.2292 | 185 | 185 | 2019-08-21 | 2019-08-22 | SURF, DRILL | DRJ - 2019 | 185 | 1 | 0 | 2019 | 2019
491 | DRJ-45 | Drill and Complete | 8 | 1500 | 7.2292 | 122 | 122 | 2019-08-22 | 2019-08-23 | SURF, DRILL | DRJ - 2019 | 122 | 1 | 0 | 2019 | 2019
492 | DRJ-45 | Drill and Complete | 9 | 1500 | 8.2292 | 0 | 0 | 2019-08-23 | 2019-08-24 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
493 | DRJ-45 | Drill and Complete | 10 | 1500 | 9.2292 | 0 | 0 | 2019-08-24 | 2019-08-25 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
494 | DRJ-45 | Drill and Complete | 11 | 1500 | 10.2292 | 0 | 0 | 2019-08-25 | 2019-08-26 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
495 | DRJ-45 | Drill and Complete | 12 | 1500 | 11.2292 | 0 | 0 | 2019-08-26 | 2019-08-27 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
496 | DRJ-45 | Drill and Complete | 13 | 1500 | 12.2292 | 0 | 0 | 2019-08-27 | 2019-08-28 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
497 | DRJ-45 | Drill and Complete | 14 | 1500 | 13.2292 |  |  | 2019-08-28 | 2019-08-29 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
498 | DRJ-45 | Drill and Complete | 15 | 1500 | 14.2292 |  |  | 2019-08-29 | 2019-08-30 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
499 | DRJ-45 | Drill and Complete | 16 | 1500 | 15.2292 |  |  | 2019-08-30 | 2019-08-31 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
500 | DRJ-45 | Drill and Complete | 17 | 1500 | 16.2292 |  |  | 2019-08-31 | 2019-09-01 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
501 | DRJ-45 | Drill and Complete | 18 | 1500 | 17.2292 |  |  | 2019-09-01 | 2019-09-02 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
502 | DRJ-45 | Drill and Complete | 19 | 1500 | 18.2292 |  |  | 2019-09-02 | 2019-09-03 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
503 | DRJ-45 | Drill and Complete | 20 | 1728 | 19.2292 | 228 | 228 | 2019-09-03 | 2019-09-04 | SURF, CSGCMT | DRJ - 2019 | 228 | 1 | 0 | 2019 | 2019
504 | DRJ-45 | Drill and Complete | 21 | 2024 | 20.2292 | 296 | 296 | 2019-09-04 | 2019-09-05 | SURF, CSGCMT | DRJ - 2019 | 296 | 1 | 0 | 2019 | 2019
505 | DRJ-45 | Drill and Complete | 22 | 2285 | 21.2292 | 261 | 261 | 2019-09-05 | 2019-09-06 | SURF, CSGCMT | DRJ - 2019 | 261 | 1 | 0 | 2019 | 2019
506 | DRJ-45 | Drill and Complete | 23 | 2514 | 22.2292 | 229 | 229 | 2019-09-06 | 2019-09-07 | SURF, CSGCMT | DRJ - 2019 | 229 | 1 | 0 | 2019 | 2019
507 | DRJ-45 | Drill and Complete | 24 | 2514 | 23.2292 | 0 | 0 | 2019-09-07 | 2019-09-08 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
508 | DRJ-45 | Drill and Complete | 25 | 2514 | 24.2292 | 0 | 0 | 2019-09-08 | 2019-09-09 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
509 | DRJ-45 | Drill and Complete | 26 | 2514 | 25.2292 | 0 | 0 | 2019-09-09 | 2019-09-10 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
510 | DRJ-45 | Drill and Complete | 27 | 2514 | 26.2292 | 0 | 0 | 2019-09-10 | 2019-09-11 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
511 | DRJ-45 | Drill and Complete | 28 | 2514 | 27.2292 | 0 | 0 | 2019-09-11 | 2019-09-12 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
512 | DRJ-45 | Drill and Complete | 29 | 2514 | 28.2292 | 0 | 0 | 2019-09-12 | 2019-09-13 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
513 | DRJ-45 | Drill and Complete | 30 | 2514 | 29.2292 | 0 | 0 | 2019-09-13 | 2019-09-14 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
514 | DRJ-45 | Drill and Complete | 31 | 2514 | 30.2292 | 0 | 0 | 2019-09-14 | 2019-09-15 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
515 | DRJ-45 | Drill and Complete | 32 | 2514 | 31.2292 | 0 | 0 | 2019-09-15 | 2019-09-16 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
516 | DRJ-45 | Drill and Complete | 33 | 2514 | 32.2292 | 0 | 0 | 2019-09-16 | 2019-09-17 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
517 | DRJ-45 | Drill and Complete | 34 | 2514 | 33.2292 | 0 | 0 | 2019-09-17 | 2019-09-18 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
518 | DRJ-45 | Drill and Complete | 35 | 2514 | 34.2292 | 0 | 0 | 2019-09-18 | 2019-09-19 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
519 | DRJ-45 | Drill and Complete | 36 | 2514 | 35.2292 | 0 | 0 | 2019-09-19 | 2019-09-20 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
520 | DRJ-45 | Drill and Complete | 37 | 2514 | 36.2292 | 0 | 0 | 2019-09-20 | 2019-09-21 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
521 | DRJ-45 | Drill and Complete | 38 | 2514 | 37.2292 | 0 | 0 | 2019-09-21 | 2019-09-22 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
522 | DRJ-45 | Drill and Complete | 39 | 2514 | 38.2292 | 0 | 0 | 2019-09-22 | 2019-09-23 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
523 | DRJ-45 | Drill and Complete | 40 | 2514 | 39.2292 | 0 | 0 | 2019-09-23 | 2019-09-24 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
524 | DRJ-45 | Drill and Complete | 41 | 2514 | 40.2292 | 0 | 0 | 2019-09-24 | 2019-09-25 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
525 | DRJ-45 | Drill and Complete | 42 | 2514 | 41.2292 | 0 | 0 | 2019-09-25 | 2019-09-26 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
526 | DRJ-45 | Drill and Complete | 43 | 2514 | 42.2292 | 0 | 0 | 2019-09-26 | 2019-09-27 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
527 | DRJ-45 | Drill and Complete | 44 | 2514 | 43.2292 | 0 | 0 | 2019-09-27 | 2019-09-28 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
528 | DRJ-45 | Drill and Complete | 45 | 2514 | 44.2292 | 0 | 0 | 2019-09-28 | 2019-09-29 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
529 | DRJ-45 | Drill and Complete | 46 | 2514 | 45.2292 | 0 | 0 | 2019-09-29 | 2019-09-30 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
530 | DRJ-45 | Drill and Complete | 47 | 2104 | 46.2292 | 145 | 145 | 2019-09-30 | 2019-10-01 | DRLGLNR1, CSGCMT | DRJ - 2019 | -410 | 1 | 1 | 2019 | 2019
531 | DRJ-45 | Drill and Complete | 48 | 2519 | 47.2292 | 415 | 415 | 2019-10-01 | 2019-10-02 | DRLGLNR1, CSGCMT | DRJ - 2019 | 415 | 1 | 0 | 2019 | 2019
532 | DRJ-45 | Drill and Complete | 49 | 2976 | 48.2292 | 457 | 457 | 2019-10-02 | 2019-10-03 | DRLGLNR1, CSGCMT | DRJ - 2019 | 457 | 1 | 0 | 2019 | 2019
533 | DRJ-45 | Drill and Complete | 50 | 3446 | 49.2292 | 470 | 470 | 2019-10-03 | 2019-10-04 | DRLGLNR1, CSGCMT | DRJ - 2019 | 470 | 1 | 0 | 2019 | 2019
534 | DRJ-45 | Drill and Complete | 51 | 3446 | 50.2292 | 0 | 0 | 2019-10-04 | 2019-10-05 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
535 | DRJ-45 | Drill and Complete | 52 | 3446 | 51.2292 |  |  | 2019-10-05 | 2019-10-06 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
536 | DRJ-45 | Drill and Complete | 53 | 3446 | 52.2292 |  |  | 2019-10-06 | 2019-10-07 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
537 | DRJ-45 | Drill and Complete | 54 | 3446 | 53.2292 |  |  | 2019-10-07 | 2019-10-08 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
538 | DRJ-45 | Drill and Complete | 55 | 3446 | 54.2292 |  |  | 2019-10-08 | 2019-10-09 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
539 | DRJ-45 | Drill and Complete | 56 | 3446 | 55.2292 |  |  | 2019-10-09 | 2019-10-10 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
540 | DRJ-45 | Drill and Complete | 57 | 3446 | 56.2292 |  |  | 2019-10-10 | 2019-10-11 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
541 | DRJ-45 | Drill and Complete | 58 | 3780 | 57.2292 | 334 | 334 | 2019-10-11 | 2019-10-12 | DRLGLNR, TB | DRJ - 2019 | 334 | 1 | 0 | 2019 | 2019
542 | DRJ-45 | Drill and Complete | 59 | 4149 | 58.2292 | 369 | 369 | 2019-10-12 | 2019-10-13 | DRLGLNR, TB | DRJ - 2019 | 369 | 1 | 0 | 2019 | 2019
543 | DRJ-45 | Drill and Complete | 60 | 4410 | 59.2292 | 261 | 261 | 2019-10-13 | 2019-10-14 | DRLGLNR, TB | DRJ - 2019 | 261 | 1 | 0 | 2019 | 2019
544 | DRJ-45 | Drill and Complete | 61 | 4599 | 60.2292 | 189 | 189 | 2019-10-14 | 2019-10-15 | DRLGLNR, TB | DRJ - 2019 | 189 | 1 | 0 | 2019 | 2019
545 | DRJ-45 | Drill and Complete | 62 | 4969 | 61.2292 | 370 | 370 | 2019-10-15 | 2019-10-16 | DRLGLNR, TB | DRJ - 2019 | 370 | 1 | 0 | 2019 | 2019
546 | DRJ-45 | Drill and Complete | 63 | 4975 | 62.2292 | 6 | 6 | 2019-10-16 | 2019-10-17 | DRLGLNR1, CSGCMT | DRJ - 2019 | 6 | 1 | 1 | 2019 | 2019
547 | DRJ-45 | Drill and Complete | 64 | 5242 | 63.2292 | 267 | 267 | 2019-10-17 | 2019-10-18 | DRLGLNR, TB | DRJ - 2019 | 267 | 1 | 0 | 2019 | 2019
548 | DRJ-45 | Drill and Complete | 65 | 5604 | 64.2292 | 362 | 362 | 2019-10-18 | 2019-10-19 | DRLGLNR, TB | DRJ - 2019 | 362 | 1 | 0 | 2019 | 2019
549 | DRJ-45 | Drill and Complete | 66 | 5950 | 65.2292 | 346 | 346 | 2019-10-19 | 2019-10-20 | DRLGLNR, TB | DRJ - 2019 | 346 | 1 | 0 | 2019 | 2019
550 | DRJ-45 | Drill and Complete | 67 | 5977 | 66.2292 | 27 | 27 | 2019-10-20 | 2019-10-21 | DRLGLNR, TB | DRJ - 2019 | 27 | 1 | 1 | 2019 | 2019
551 | DRJ-45 | Drill and Complete | 68 | 5977 | 67.2292 | 0 | 0 | 2019-10-21 | 2019-10-22 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
552 | DRJ-45 | Drill and Complete | 69 | 5977 | 68.2292 | 0 | 0 | 2019-10-22 | 2019-10-23 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
553 | DRJ-45 | Drill and Complete | 70 | 5977 | 69.2292 | 0 | 0 | 2019-10-23 | 2019-10-24 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
554 | DRJ-45 | Drill and Complete | 71 | 5977 | 70.2292 | 0 | 0 | 2019-10-24 | 2019-10-25 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
555 | DRJ-45 | Drill and Complete | 72 | 5977 | 71.2292 | 0 | 0 | 2019-10-25 | 2019-10-26 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
556 | DRJ-45 | Drill and Complete | 73 | 5977 | 72.2292 | 0 | 0 | 2019-10-26 | 2019-10-27 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
557 | DRJ-45 | Drill and Complete | 74 | 5977 | 73.2292 | 0 | 0 | 2019-10-27 | 2019-10-28 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
558 | DRJ-45 | Drill and Complete | 75 | 5977 | 74.2292 | 0 | 0 | 2019-10-28 | 2019-10-29 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
559 | DRJ-45 | Drill and Complete | 76 | 5977 | 75.2292 | 0 | 0 | 2019-10-29 | 2019-10-30 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
560 | DRJ-45 | Drill and Complete | 77 | 5977 | 76.2292 | 0 | 0 | 2019-10-30 | 2019-10-31 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
561 | DRJ-45 | Drill and Complete | 78 | 5977 | 77.2292 | 0 | 0 | 2019-10-31 | 2019-11-01 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
562 | DRJ-45 | Drill and Complete | 79 | 5977 | 78.2292 | 0 | 0 | 2019-11-01 | 2019-11-02 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
563 | DRJ-45 | Drill and Complete | 80 | 5977 | 79.2292 | 0 | 0 | 2019-11-02 | 2019-11-03 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
564 | DRJ-45 | Drill and Complete | 81 | 5977 | 80.2292 | 0 | 0 | 2019-11-03 | 2019-11-04 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
565 | DRJ-45 | Drill and Complete | 82 | 5977 | 80.4792 | 0 | 0 | 2019-11-04 | 2019-11-04 06:00 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 0.25 | 0.25 | 2019 | 2019
566 | DRJ-46 | Drill and Complete | 1 | 230 | 0.0625 | 15 | 15 | 2019-11-06 22:30 | 2019-11-07 | SURF, DRILL | DRJ - 2019 | 230 | 0.0625 | 0 | 2019 | 2019
567 | DRJ-46 | Drill and Complete | 2 | 288 | 1.0625 | 58 | 58 | 2019-11-07 | 2019-11-08 | SURF, DRILL | DRJ - 2019 | 58 | 1 | 0 | 2019 | 2019
568 | DRJ-46 | Drill and Complete | 3 | 347 | 2.0625 | 59 | 59 | 2019-11-08 | 2019-11-09 | SURF, DRILL | DRJ - 2019 | 59 | 1 | 0 | 2019 | 2019
569 | DRJ-46 | Drill and Complete | 4 | 347 | 3.0625 | 0 | 0 | 2019-11-09 | 2019-11-10 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
570 | DRJ-46 | Drill and Complete | 5 | 435 | 4.0625 | 88 | 88 | 2019-11-10 | 2019-11-11 | SURF, DRILL | DRJ - 2019 | 88 | 1 | 0 | 2019 | 2019
571 | DRJ-46 | Drill and Complete | 6 | 610 | 5.0625 | 175 | 175 | 2019-11-11 | 2019-11-12 | SURF, DRILL | DRJ - 2019 | 175 | 1 | 0 | 2019 | 2019
572 | DRJ-46 | Drill and Complete | 7 | 610 | 6.0625 | 0 | 0 | 2019-11-12 | 2019-11-13 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
573 | DRJ-46 | Drill and Complete | 8 | 610 | 7.0625 | 0 | 0 | 2019-11-13 | 2019-11-14 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
574 | DRJ-46 | Drill and Complete | 9 | 662 | 8.0625 | 52 | 52 | 2019-11-14 | 2019-11-15 | SURF, DRILL | DRJ - 2019 | 52 | 1 | 0 | 2019 | 2019
575 | DRJ-46 | Drill and Complete | 10 | 960 | 9.0625 | 298 | 298 | 2019-11-15 | 2019-11-16 | SURF, DRILL | DRJ - 2019 | 298 | 1 | 0 | 2019 | 2019
576 | DRJ-46 | Drill and Complete | 11 | 1292 | 10.0625 | 332 | 332 | 2019-11-16 | 2019-11-17 | SURF, DRILL | DRJ - 2019 | 332 | 1 | 0 | 2019 | 2019
577 | DRJ-46 | Drill and Complete | 12 | 1325 | 11.0625 | 33 | 33 | 2019-11-17 | 2019-11-18 | SURF, DRILL | DRJ - 2019 | 33 | 1 | 1 | 2019 | 2019
578 | DRJ-46 | Drill and Complete | 13 | 1581 | 12.0625 | 256 | 256 | 2019-11-18 | 2019-11-19 | SURF, DRILL | DRJ - 2019 | 256 | 1 | 0 | 2019 | 2019
579 | DRJ-46 | Drill and Complete | 14 | 1620 | 13.0625 | 39 | 39 | 2019-11-19 | 2019-11-20 | SURF, DRILL | DRJ - 2019 | 39 | 1 | 1 | 2019 | 2019
580 | DRJ-46 | Drill and Complete | 15 | 1620 | 14.0625 | 0 | 0 | 2019-11-20 | 2019-11-21 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
581 | DRJ-46 | Drill and Complete | 16 | 1620 | 15.0625 | 0 | 0 | 2019-11-21 | 2019-11-22 | SURF, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
582 | DRJ-46 | Drill and Complete | 17 | 1620 | 16.0625 | 0 | 0 | 2019-11-22 | 2019-11-23 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
583 | DRJ-46 | Drill and Complete | 18 | 1620 | 17.0625 | 0 | 0 | 2019-11-23 | 2019-11-24 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
584 | DRJ-46 | Drill and Complete | 19 | 1620 | 18.0625 | 0 | 0 | 2019-11-24 | 2019-11-25 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
585 | DRJ-46 | Drill and Complete | 20 | 1620 | 19.0625 | 0 | 0 | 2019-11-25 | 2019-11-26 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
586 | DRJ-46 | Drill and Complete | 21 | 1620 | 20.0625 | 0 | 0 | 2019-11-26 | 2019-11-27 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
587 | DRJ-46 | Drill and Complete | 22 | 1620 | 21.0625 | 0 | 0 | 2019-11-27 | 2019-11-28 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
588 | DRJ-46 | Drill and Complete | 23 | 1620 | 22.0625 | 0 | 0 | 2019-11-28 | 2019-11-29 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
589 | DRJ-46 | Drill and Complete | 24 | 1620 | 23.0625 | 0 | 0 | 2019-11-29 | 2019-11-30 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
590 | DRJ-46 | Drill and Complete | 25 | 1837 | 24.0625 | 217 | 217 | 2019-11-30 | 2019-12-01 | SURF, CSGCMT | DRJ - 2019 | 217 | 1 | 0 | 2019 | 2019
591 | DRJ-46 | Drill and Complete | 26 | 2350 | 25.0625 | 513 | 513 | 2019-12-01 | 2019-12-02 | SURF, CSGCMT | DRJ - 2019 | 513 | 1 | 0 | 2019 | 2019
592 | DRJ-46 | Drill and Complete | 27 | 2601 | 26.0625 | 251 | 251 | 2019-12-02 | 2019-12-03 | SURF, CSGCMT | DRJ - 2019 | 251 | 1 | 0 | 2019 | 2019
593 | DRJ-46 | Drill and Complete | 28 | 2822 | 27.0625 | 221 | 221 | 2019-12-03 | 2019-12-04 | SURF, CSGCMT | DRJ - 2019 | 221 | 1 | 0 | 2019 | 2019
594 | DRJ-46 | Drill and Complete | 29 | 2822 | 28.0625 | 0 | 0 | 2019-12-04 | 2019-12-05 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
595 | DRJ-46 | Drill and Complete | 30 | 3129 | 29.0625 | 307 | 307 | 2019-12-05 | 2019-12-06 | SURF, CSGCMT | DRJ - 2019 | 307 | 1 | 0 | 2019 | 2019
596 | DRJ-46 | Drill and Complete | 31 | 3550 | 30.0625 | 421 | 421 | 2019-12-06 | 2019-12-07 | SURF, CSGCMT | DRJ - 2019 | 421 | 1 | 0 | 2019 | 2019
597 | DRJ-46 | Drill and Complete | 32 | 3550 | 31.0625 | 0 | 0 | 2019-12-07 | 2019-12-08 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
598 | DRJ-46 | Drill and Complete | 33 | 3550 | 32.0625 | 0 | 0 | 2019-12-08 | 2019-12-09 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
599 | DRJ-46 | Drill and Complete | 34 | 3550 | 33.0625 | 0 | 0 | 2019-12-09 | 2019-12-10 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
600 | DRJ-46 | Drill and Complete | 35 | 3550 | 34.0625 | 0 | 0 | 2019-12-10 | 2019-12-11 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
601 | DRJ-46 | Drill and Complete | 36 | 3550 | 35.0625 | 0 | 0 | 2019-12-11 | 2019-12-12 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
602 | DRJ-46 | Drill and Complete | 37 | 3550 | 36.0625 | 0 | 0 | 2019-12-12 | 2019-12-13 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
603 | DRJ-46 | Drill and Complete | 38 | 3550 | 37.0625 | 0 | 0 | 2019-12-13 | 2019-12-14 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
604 | DRJ-46 | Drill and Complete | 39 | 3550 | 38.0625 | 0 | 0 | 2019-12-14 | 2019-12-15 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
605 | DRJ-46 | Drill and Complete | 40 | 3550 | 39.0625 | 0 | 0 | 2019-12-15 | 2019-12-16 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
606 | DRJ-46 | Drill and Complete | 41 | 3550 | 40.0625 | 0 | 0 | 2019-12-16 | 2019-12-17 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
607 | DRJ-46 | Drill and Complete | 42 | 3769 | 41.0625 | 219 | 219 | 2019-12-17 | 2019-12-18 | DRLGLNR1, CSGCMT | DRJ - 2019 | 219 | 1 | 0 | 2019 | 2019
608 | DRJ-46 | Drill and Complete | 43 | 4273 | 42.0625 | 504 | 504 | 2019-12-18 | 2019-12-19 | DRLGLNR1, CSGCMT | DRJ - 2019 | 504 | 1 | 0 | 2019 | 2019
609 | DRJ-46 | Drill and Complete | 44 | 4851 | 43.0625 | 578 | 578 | 2019-12-19 | 2019-12-20 | DRLGLNR1, CSGCMT | DRJ - 2019 | 578 | 1 | 0 | 2019 | 2019
610 | DRJ-46 | Drill and Complete | 45 | 5205 | 44.0625 | 354 | 354 | 2019-12-20 | 2019-12-21 | DRLGLNR1, CSGCMT | DRJ - 2019 | 354 | 1 | 0 | 2019 | 2019
611 | DRJ-46 | Drill and Complete | 46 | 5501 | 45.0625 | 296 | 296 | 2019-12-21 | 2019-12-22 | DRLGLNR1, CSGCMT | DRJ - 2019 | 296 | 1 | 0 | 2019 | 2019
612 | DRJ-46 | Drill and Complete | 47 | 5836 | 46.0625 | 335 | 335 | 2019-12-22 | 2019-12-23 | DRLGLNR1, CSGCMT | DRJ - 2019 | 335 | 1 | 0 | 2019 | 2019
613 | DRJ-46 | Drill and Complete | 48 | 5836 | 47.0625 | 0 | 0 | 2019-12-23 | 2019-12-24 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2019 | 2019
614 | DRJ-46 | Drill and Complete | 49 | 5836 | 47.4792 | 0 | 0 | 2019-12-24 | 2019-12-25 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 0.41667 | 0.41667 | 2019 | 2019
615 | DRJ-47 | Drill and Complete | 1 | 301 | 0.33333 | 88 | 88 | 2019-12-27 16:00 | 2019-12-28 |  | DRJ - 2019 | 301 | 0.33333 | 0 | 2019 | 2019
616 | DRJ-47 | Drill and Complete | 2 | 583 | 1.3333 | 282 | 282 | 2019-12-28 | 2019-12-29 |  | DRJ - 2019 | 282 | 1 | 0 | 2019 | 2019
617 | DRJ-47 | Drill and Complete | 3 | 773 | 2.3333 | 190 | 190 | 2019-12-29 | 2019-12-30 |  | DRJ - 2019 | 190 | 1 | 0 | 2019 | 2019
618 | DRJ-47 | Drill and Complete | 4 | 1043 | 3.3333 | 270 | 270 | 2019-12-30 | 2019-12-31 |  | DRJ - 2019 | 270 | 1 | 0 | 2019 | 2019
619 | DRJ-47 | Drill and Complete | 5 | 1324 | 4.3333 | 281 | 281 | 2019-12-31 | 2020-01-01 |  | DRJ - 2019 | 281 | 1 | 0 | 2019 | 2019
620 | DRJ-47 | Drill and Complete | 6 | 1524 | 5.3333 | 200 | 200 | 2020-01-01 | 2020-01-02 |  | DRJ - 2019 | 200 | 1 | 0 | 2020 | 2020
621 | DRJ-47 | Drill and Complete | 7 | 1620 | 6.3333 | 96 | 96 | 2020-01-02 | 2020-01-03 |  | DRJ - 2019 | 96 | 1 | 0 | 2020 | 2020
622 | DRJ-47 | Drill and Complete | 8 | 1620 | 7.3333 | 0 | 0 | 2020-01-03 | 2020-01-04 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
623 | DRJ-47 | Drill and Complete | 9 | 1620 | 8.3333 | 0 | 0 | 2020-01-04 | 2020-01-05 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
624 | DRJ-47 | Drill and Complete | 10 | 1620 | 9.3333 | 0 | 0 | 2020-01-05 | 2020-01-06 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
625 | DRJ-47 | Drill and Complete | 11 | 1620 | 10.3333 | 0 | 0 | 2020-01-06 | 2020-01-07 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
626 | DRJ-47 | Drill and Complete | 12 | 1620 | 11.3333 | 0 | 0 | 2020-01-07 | 2020-01-08 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
627 | DRJ-47 | Drill and Complete | 13 | 1620 | 12.3333 | 0 | 0 | 2020-01-08 | 2020-01-09 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
628 | DRJ-47 | Drill and Complete | 14 | 1620 | 13.3333 | 0 | 0 | 2020-01-09 | 2020-01-10 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
629 | DRJ-47 | Drill and Complete | 15 | 1620 | 14.3333 | 0 | 0 | 2020-01-10 | 2020-01-11 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
630 | DRJ-47 | Drill and Complete | 16 | 1620 | 15.3333 | 0 | 0 | 2020-01-11 | 2020-01-12 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
631 | DRJ-47 | Drill and Complete | 17 | 1620 | 16.3333 | 0 | 0 | 2020-01-12 | 2020-01-13 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
632 | DRJ-47 | Drill and Complete | 18 | 1620 | 17.3333 | 0 | 0 | 2020-01-13 | 2020-01-14 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
633 | DRJ-47 | Drill and Complete | 19 | 1620 | 18.3333 | 0 | 0 | 2020-01-14 | 2020-01-15 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
634 | DRJ-47 | Drill and Complete | 20 | 1865 | 19.3333 | 245 | 245 | 2020-01-15 | 2020-01-16 |  | DRJ - 2019 | 245 | 1 | 0 | 2020 | 2020
635 | DRJ-47 | Drill and Complete | 21 | 2576 | 20.3333 | 711 | 711 | 2020-01-16 | 2020-01-17 |  | DRJ - 2019 | 711 | 1 | 0 | 2020 | 2020
636 | DRJ-47 | Drill and Complete | 22 | 3120 | 21.3333 | 544 | 544 | 2020-01-17 | 2020-01-18 |  | DRJ - 2019 | 544 | 1 | 0 | 2020 | 2020
637 | DRJ-47 | Drill and Complete | 23 | 3200 | 22.3333 | 80 | 80 | 2020-01-18 | 2020-01-19 |  | DRJ - 2019 | 80 | 1 | 0 | 2020 | 2020
638 | DRJ-47 | Drill and Complete | 24 | 3200 | 23.3333 | 0 | 0 | 2020-01-19 | 2020-01-20 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
639 | DRJ-47 | Drill and Complete | 25 | 3200 | 24.3333 | 0 | 0 | 2020-01-20 | 2020-01-21 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
640 | DRJ-47 | Drill and Complete | 26 | 3200 | 25.3333 | 0 | 0 | 2020-01-21 | 2020-01-22 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
641 | DRJ-47 | Drill and Complete | 27 | 3402 | 26.3333 | 202 | 202 | 2020-01-22 | 2020-01-23 |  | DRJ - 2019 | 202 | 1 | 0 | 2020 | 2020
642 | DRJ-47 | Drill and Complete | 28 | 3864 | 27.3333 | 462 | 462 | 2020-01-23 | 2020-01-24 |  | DRJ - 2019 | 462 | 1 | 0 | 2020 | 2020
643 | DRJ-47 | Drill and Complete | 29 | 4480 | 28.3333 | 616 | 616 | 2020-01-24 | 2020-01-25 |  | DRJ - 2019 | 616 | 1 | 0 | 2020 | 2020
644 | DRJ-47 | Drill and Complete | 30 | 5054 | 29.3333 | 574 | 574 | 2020-01-25 | 2020-01-26 |  | DRJ - 2019 | 574 | 1 | 0 | 2020 | 2020
645 | DRJ-47 | Drill and Complete | 31 | 5603 | 30.3333 | 549 | 549 | 2020-01-26 | 2020-01-27 |  | DRJ - 2019 | 549 | 1 | 0 | 2020 | 2020
646 | DRJ-47 | Drill and Complete | 32 | 5902 | 31.3333 | 299 | 299 | 2020-01-27 | 2020-01-28 |  | DRJ - 2019 | 299 | 1 | 0 | 2020 | 2020
647 | DRJ-47 | Drill and Complete | 33 | 5902 | 32.3333 | 0 | 0 | 2020-01-28 | 2020-01-29 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
648 | DRJ-47 | Drill and Complete | 34 | 5902 | 33.3333 | 0 | 0 | 2020-01-29 | 2020-01-30 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
649 | DRJ-47 | Drill and Complete | 35 | 5902 | 34.3333 | 0 | 0 | 2020-01-30 | 2020-01-31 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
650 | DRJ-47 | Drill and Complete | 36 | 5902 | 35.3333 | 0 | 0 | 2020-01-31 | 2020-02-01 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
651 | DRJ-47 | Drill and Complete | 37 | 5902 | 35.8333 | 0 | 0 | 2020-02-01 | 2020-02-01 12:00 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 0.5 | 0.5 | 2020 | 2020
652 | DRJ-48 | Drill and Complete | 1 | 393 | 0.52083 | 219 | 219 | 2020-02-15 11:30 | 2020-02-16 |  | DRJ - 2019 | 393 | 0.52083 | 0 | 2020 | 2020
653 | DRJ-48 | Drill and Complete | 2 | 812 | 1.5208 | 419 | 419 | 2020-02-16 | 2020-02-17 |  | DRJ - 2019 | 419 | 1 | 0 | 2020 | 2020
654 | DRJ-48 | Drill and Complete | 3 | 812 | 2.5208 | 0 | 0 | 2020-02-17 | 2020-02-18 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
655 | DRJ-48 | Drill and Complete | 4 | 1206 | 3.5208 | 394 | 394 | 2020-02-18 | 2020-02-19 |  | DRJ - 2019 | 394 | 1 | 0 | 2020 | 2020
656 | DRJ-48 | Drill and Complete | 5 | 1422 | 4.5208 | 216 | 216 | 2020-02-19 | 2020-02-20 |  | DRJ - 2019 | 216 | 1 | 0 | 2020 | 2020
657 | DRJ-48 | Drill and Complete | 6 | 1422 | 5.5208 | 0 | 0 | 2020-02-20 | 2020-02-21 |  | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
658 | DRJ-48 | Drill and Complete | 7 | 1422 | 6.5208 | 0 | 0 | 2020-02-21 | 2020-02-22 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
659 | DRJ-48 | Drill and Complete | 8 | 1422 | 7.5208 | 0 | 0 | 2020-02-22 | 2020-02-23 | SURF, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
660 | DRJ-48 | Drill and Complete | 9 | 2179 | 8.5208 | 757 | 757 | 2020-02-23 | 2020-02-24 | SURF, CSGCMT | DRJ - 2019 | 757 | 1 | 0 | 2020 | 2020
661 | DRJ-48 | Drill and Complete | 10 | 2797 | 9.5208 | 618 | 618 | 2020-02-24 | 2020-02-25 | SURF, CSGCMT | DRJ - 2019 | 618 | 1 | 0 | 2020 | 2020
662 | DRJ-48 | Drill and Complete | 11 | 3232 | 10.5208 | 435 | 435 | 2020-02-25 | 2020-02-26 | SURF, CSGCMT | DRJ - 2019 | 435 | 1 | 0 | 2020 | 2020
663 | DRJ-48 | Drill and Complete | 12 | 3350 | 11.5208 | 118 | 118 | 2020-02-26 | 2020-02-27 | SURF, CSGCMT | DRJ - 2019 | 118 | 1 | 0 | 2020 | 2020
664 | DRJ-48 | Drill and Complete | 13 | 3350 | 12.5208 | 0 | 0 | 2020-02-27 | 2020-02-28 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
665 | DRJ-48 | Drill and Complete | 14 | 3350 | 13.5208 | 0 | 0 | 2020-02-28 | 2020-02-29 | DRLGLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
666 | DRJ-48 | Drill and Complete | 15 | 3350 | 14.5208 | 0 | 0 | 2020-02-29 | 2020-03-01 | DRLGLNR, TB | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
667 | DRJ-48 | Drill and Complete | 16 | 1121 | 15.5208 | 108 | 108 | 2020-03-01 | 2020-03-02 | DRLGLNR, TB | DRJ - 2019 | -2229 | 1 | 1 | 2020 | 2020
668 | DRJ-48 | Drill and Complete | 17 | 3665 | 16.5208 | 315 | 315 | 2020-03-02 | 2020-03-03 | DRLGLNR, TB | DRJ - 2019 | 2544 | 1 | 0 | 2020 | 2020
669 | DRJ-48 | Drill and Complete | 18 | 4247 | 17.5208 | 582 | 582 | 2020-03-03 | 2020-03-04 | DRLGLNR, TB | DRJ - 2019 | 582 | 1 | 0 | 2020 | 2020
670 | DRJ-48 | Drill and Complete | 19 | 4661 | 18.5208 | 414 | 414 | 2020-03-04 | 2020-03-05 | DRLGLNR, TB | DRJ - 2019 | 414 | 1 | 0 | 2020 | 2020
671 | DRJ-48 | Drill and Complete | 20 | 4859 | 19.5208 | 198 | 198 | 2020-03-05 | 2020-03-06 | DRLGLNR, TB | DRJ - 2019 | 198 | 1 | 0 | 2020 | 2020
672 | DRJ-48 | Drill and Complete | 21 | 4949 | 20.5208 | 90 | 90 | 2020-03-06 | 2020-03-07 | DRLGLNR, TB | DRJ - 2019 | 90 | 1 | 0 | 2020 | 2020
673 | DRJ-48 | Drill and Complete | 22 | 4949 | 21.5208 | 0 | 0 | 2020-03-07 | 2020-03-08 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
674 | DRJ-48 | Drill and Complete | 23 | 4949 | 22.5208 | 0 | 0 | 2020-03-08 | 2020-03-09 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
675 | DRJ-48 | Drill and Complete | 24 | 4949 | 23.5208 | 0 | 0 | 2020-03-09 | 2020-03-10 | PRODLNR1, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
676 | DRJ-48 | Drill and Complete | 25 | 4949 | 24.5208 | 0 | 0 | 2020-03-10 | 2020-03-11 | PRODLNR2, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
677 | DRJ-48 | Drill and Complete | 26 | 4949 | 25.5208 | 0 | 0 | 2020-03-11 | 2020-03-12 | PRODLNR2, CSGCMT | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
678 | DRJ-48 | Drill and Complete | 27 | 5183 | 26.5208 | 234 | 234 | 2020-03-12 | 2020-03-13 | PRODLNR2, CSGCMT | DRJ - 2019 | 234 | 1 | 0 | 2020 | 2020
679 | DRJ-48 | Drill and Complete | 28 | 5399.5 | 27.5208 | 216.5 | 216.5 | 2020-03-13 | 2020-03-14 | PRODLNR2, CSGCMT | DRJ - 2019 | 216.5 | 1 | 0 | 2020 | 2020
680 | DRJ-48 | Drill and Complete | 29 | 5399.5 | 28.5208 | 0 | 0 | 2020-03-14 | 2020-03-15 | PRODLNR3, DRILL | DRJ - 2019 | 0 | 1 | 1 | 2020 | 2020
681 | DRJ-48 | Drill and Complete | 30 | 5399.5 | 28.9375 | 0 | 0 | 2020-03-15 | 2020-03-15 10:00 | PRODLNR3, DRILL | DRJ - 2019 | 0 | 0.41667 | 0.41667 | 2020 | 2020
682 | MBD-8 | Sidetrack | 1 | 0 | 0.16667 |  |  | 2020-11-06 20:00 | 2020-11-07 |  | WW - 2018 | 0 | 0.16667 | 0.16667 | 2020 | 2020
683 | MBD-8 | Sidetrack | 2 | 0 | 1.1667 |  |  | 2020-11-07 | 2020-11-08 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
684 | MBD-8 | Sidetrack | 3 | 0 | 2.1667 |  |  | 2020-11-08 | 2020-11-09 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
685 | MBD-8 | Sidetrack | 4 | 0 | 3.1667 |  |  | 2020-11-09 | 2020-11-10 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
686 | MBD-8 | Sidetrack | 5 | 0 | 4.1667 |  |  | 2020-11-10 | 2020-11-11 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
687 | MBD-8 | Sidetrack | 6 | 0 | 5.1667 |  |  | 2020-11-11 | 2020-11-12 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
688 | MBD-8 | Sidetrack | 7 | 0 | 6.1667 |  |  | 2020-11-12 | 2020-11-13 |  | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
689 | MBD-8 | Sidetrack | 8 | 2010 | 7.1667 | 34 | 34 | 2020-11-13 | 2020-11-14 |  | WW - 2018 | 2010 | 1 | 0 | 2020 | 2020
690 | MBD-8 | Sidetrack | 9 | 2132 | 8.1667 | 92 | 92 | 2020-11-14 | 2020-11-15 |  | WW - 2018 | 122 | 1 | 0 | 2020 | 2020
691 | MBD-8 | Sidetrack | 10 | 2706 | 9.1667 | 574 | 574 | 2020-11-15 | 2020-11-16 |  | WW - 2018 | 574 | 1 | 0 | 2020 | 2020
692 | MBD-8 | Sidetrack | 11 | 3100 | 10.1667 | 394 | 394 | 2020-11-16 | 2020-11-17 |  | WW - 2018 | 394 | 1 | 0 | 2020 | 2020
693 | MBD-8 | Sidetrack | 12 | 2791 | 11.1667 | 0 | 0 | 2020-11-17 | 2020-11-18 | PRODLNR1, CSGCMT | WW - 2018 | -309 | 1 | 1 | 2020 | 2020
694 | MBD-8 | Sidetrack | 13 | 2927 | 12.1667 | 136 | 136 | 2020-11-18 | 2020-11-19 | PRODLNR1, CSGCMT | WW - 2018 | 136 | 1 | 0 | 2020 | 2020
695 | MBD-8 | Sidetrack | 14 | 3350 | 13.1667 | 500 | 250 | 2020-11-19 | 2020-11-20 | PRODLNR1, CSGCMT | WW - 2018 | 423 | 1 | 0 | 2020 | 2020
696 | MBD-8 | Sidetrack | 15 | 3575 | 14.1667 | 450 | 225 | 2020-11-20 | 2020-11-21 | PRODLNR1, CSGCMT | WW - 2018 | 225 | 1 | 0 | 2020 | 2020
697 | MBD-8 | Sidetrack | 16 | 4140 | 15.1667 | 1130 | 565 | 2020-11-21 | 2020-11-22 | PRODLNR1, CSGCMT | WW - 2018 | 565 | 1 | 0 | 2020 | 2020
698 | MBD-8 | Sidetrack | 17 | 4140 | 16.1667 | 0 | 0 | 2020-11-22 | 2020-11-23 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
699 | MBD-8 | Sidetrack | 18 | 4140 | 17.1667 | 0 | 0 | 2020-11-23 | 2020-11-24 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
700 | MBD-8 | Sidetrack | 19 | 4140 | 18.1667 | 0 | 0 | 2020-11-24 | 2020-11-25 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
701 | MBD-8 | Sidetrack | 20 | 4140 | 19.1667 | 0 | 0 | 2020-11-25 | 2020-11-26 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
702 | MBD-8 | Sidetrack | 21 | 4140 | 20.1667 | 0 | 0 | 2020-11-26 | 2020-11-27 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
703 | MBD-8 | Sidetrack | 22 | 4140 | 21.1667 | 0 | 0 | 2020-11-27 | 2020-11-28 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
704 | MBD-8 | Sidetrack | 23 | 4140 | 22.1667 | 0 | 0 | 2020-11-28 | 2020-11-29 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
705 | MBD-8 | Sidetrack | 24 | 4140 | 23.1667 | 0 | 0 | 2020-11-29 | 2020-11-30 | PRODLNR1, CSGCMT | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
706 | MBD-8 | Sidetrack | 25 | 4140 | 24.1667 | 0 | 0 | 2020-11-30 | 2020-12-01 | PRODLNR2, DRILL | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
707 | MBD-8 | Sidetrack | 26 | 4140 | 25.1667 | 0 | 0 | 2020-12-01 | 2020-12-02 | PRODLNR2, DRILL | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
708 | MBD-8 | Sidetrack | 27 | 4140 | 26.1667 | 0 | 0 | 2020-12-02 | 2020-12-03 | PRODLNR2, DRILL | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
709 | MBD-8 | Sidetrack | 28 | 4140 | 27.1667 | 0 | 0 | 2020-12-03 | 2020-12-04 | PRODLNR2, DRILL | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
710 | MBD-8 | Sidetrack | 29 | 4140 | 28.1667 | 0 | 0 | 2020-12-04 | 2020-12-05 | PRODLNR2, DRILL | WW - 2018 | 0 | 1 | 1 | 2020 | 2020
711 | MBD-8 | Sidetrack | 30 | 4140 | 28.2292 | 0 | 0 | 2020-12-05 | 2020-12-05 01:30 | PRODLNR2, DRILL | WW - 2018 | 0 | 0.0625 | 0.0625 | 2020 | 2020
712 | MBE-6 | Drill and Complete | 1 | 520 | 0.77083 | 330 | 330 | 2020-12-20 05:30 | 2020-12-21 |  | WW - 2021 | 520 | 0.77083 | 0 | 2020 | 2020
713 | MBE-6 | Drill and Complete | 2 | 1170 | 1.7708 | 650 | 650 | 2020-12-21 | 2020-12-22 |  | WW - 2021 | 650 | 1 | 0 | 2020 | 2020
714 | MBE-6 | Drill and Complete | 3 | 1246 | 2.7708 | 76 | 76 | 2020-12-22 | 2020-12-23 | SURF, CSGCMT | WW - 2021 | 76 | 1 | 0 | 2020 | 2020
715 | MBE-6 | Drill and Complete | 4 | 1246 | 3.7708 | 0 | 0 | 2020-12-23 | 2020-12-24 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2020 | 2020
716 | MBE-6 | Drill and Complete | 5 | 1246 | 4.7708 | 0 | 0 | 2020-12-24 | 2020-12-25 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2020 | 2020
717 | MBE-6 | Drill and Complete | 6 | 1298 | 5.7708 | 52 | 52 | 2020-12-25 | 2020-12-26 | SURF, CSGCMT | WW - 2021 | 52 | 1 | 0 | 2020 | 2020
718 | MBE-6 | Drill and Complete | 7 | 2032 | 6.7708 | 712 | 734 | 2020-12-26 | 2020-12-27 | SURF, CSGCMT | WW - 2021 | 734 | 1 | 0 | 2020 | 2020
719 | MBE-6 | Drill and Complete | 8 | 2354 | 7.7708 | 299 | 322 | 2020-12-27 | 2020-12-28 | SURF, CSGCMT | WW - 2021 | 322 | 1 | 0 | 2020 | 2020
720 | MBE-6 | Drill and Complete | 9 | 2860 | 8.7708 | 506 | 506 | 2020-12-28 | 2020-12-29 | SURF, CSGCMT | WW - 2021 | 506 | 1 | 0 | 2020 | 2020
721 | MBE-6 | Drill and Complete | 10 | 2860 | 9.7708 | 0 | 0 | 2020-12-29 | 2020-12-30 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2020 | 2020
722 | MBE-6 | Drill and Complete | 11 | 2860 | 10.7708 | 0 | 0 | 2020-12-30 | 2020-12-31 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2020 | 2020
723 | MBE-6 | Drill and Complete | 12 | 2860 | 11.7708 | 0 | 0 | 2020-12-31 | 2021-01-01 | PROD, TB | WW - 2021 | 0 | 1 | 1 | 2020 | 2020
724 | MBE-6 | Drill and Complete | 13 | 2926 | 12.7708 | 66 | 66 | 2021-01-01 | 2021-01-02 | PROD, TB | WW - 2021 | 66 | 1 | 0 | 2021 | 2021
725 | MBE-6 | Drill and Complete | 14 | 3884 | 13.7708 | 933 | 958 | 2021-01-02 | 2021-01-03 | PROD, TB | WW - 2021 | 958 | 1 | 0 | 2021 | 2021
726 | MBE-6 | Drill and Complete | 15 | 4500 | 14.7708 | 616 | 616 | 2021-01-03 | 2021-01-04 | PRODLNR1, CSGCMT | WW - 2021 | 616 | 1 | 0 | 2021 | 2021
727 | MBE-6 | Drill and Complete | 16 | 4500 | 15.2292 | 0 | 0 | 2021-01-04 | 2021-01-05 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 0.45833 | 0.45833 | 2021 | 2021
728 | MBE-7 | Drill and Complete | 1 | 245 | 0.10417 | 17 | 17 | 2021-01-08 21:30 | 2021-01-09 |  | WW - 2021 | 245 | 0.10417 | 0 | 2021 | 2021
729 | MBE-7 | Drill and Complete | 2 | 457 | 1.1042 | 212 | 212 | 2021-01-09 | 2021-01-10 |  | WW - 2021 | 212 | 1 | 0 | 2021 | 2021
730 | MBE-7 | Drill and Complete | 3 | 1265 | 2.1042 | 808 | 808 | 2021-01-10 | 2021-01-11 |  | WW - 2021 | 808 | 1 | 0 | 2021 | 2021
731 | MBE-7 | Drill and Complete | 4 | 1265 | 3.1042 | 0 | 0 | 2021-01-11 | 2021-01-12 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
732 | MBE-7 | Drill and Complete | 5 | 1265 | 4.1042 | 0 | 0 | 2021-01-12 | 2021-01-13 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
733 | MBE-7 | Drill and Complete | 6 | 2110 | 5.1042 | 845 | 845 | 2021-01-13 | 2021-01-14 | SURF, CSGCMT | WW - 2021 | 845 | 1 | 0 | 2021 | 2021
734 | MBE-7 | Drill and Complete | 7 | 2746 | 6.1042 | 636 | 636 | 2021-01-14 | 2021-01-15 | SURF, CSGCMT | WW - 2021 | 636 | 1 | 0 | 2021 | 2021
735 | MBE-7 | Drill and Complete | 8 | 2746 | 7.1042 | 0 | 0 | 2021-01-15 | 2021-01-16 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
736 | MBE-7 | Drill and Complete | 9 | 2746 | 8.1042 | 0 | 0 | 2021-01-16 | 2021-01-17 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
737 | MBE-7 | Drill and Complete | 10 | 2746 | 9.1042 | 0 | 0 | 2021-01-17 | 2021-01-18 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
738 | MBE-7 | Drill and Complete | 11 | 2746 | 10.1042 | 0 | 0 | 2021-01-18 | 2021-01-19 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
739 | MBE-7 | Drill and Complete | 12 | 2746 | 11.1042 | 0 | 0 | 2021-01-19 | 2021-01-20 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
740 | MBE-7 | Drill and Complete | 13 | 2746 | 12.1042 | 0 | 0 | 2021-01-20 | 2021-01-21 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
741 | MBE-7 | Drill and Complete | 14 | 3414 | 13.1042 | 668 | 668 | 2021-01-21 | 2021-01-22 | DRLGLNR, TB | WW - 2021 | 668 | 1 | 0 | 2021 | 2021
742 | MBE-7 | Drill and Complete | 15 | 4625 | 14.1042 | 1211 | 1211 | 2021-01-22 | 2021-01-23 | DRLGLNR, TB | WW - 2021 | 1211 | 1 | 0 | 2021 | 2021
743 | MBE-7 | Drill and Complete | 16 | 5128 | 15.1042 | 503 | 503 | 2021-01-23 | 2021-01-24 | PRODLNR1, CSGCMT | WW - 2021 | 503 | 1 | 0 | 2021 | 2021
744 | MBE-7 | Drill and Complete | 17 | 5128 | 16.1042 | 0 | 0 | 2021-01-24 | 2021-01-25 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
745 | MBE-7 | Drill and Complete | 18 | 5128 | 17.1042 | 0 | 0 | 2021-01-25 | 2021-01-26 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
746 | MBE-7 | Drill and Complete | 19 | 5133 | 18.1042 | 5 | 5 | 2021-01-26 | 2021-01-27 | PRODLNR1, CSGCMT | WW - 2021 | 5 | 1 | 1 | 2021 | 2021
747 | MBE-7 | Drill and Complete | 20 | 5873 | 19.1042 | 740 | 740 | 2021-01-27 | 2021-01-28 | PRODLNR1, CSGCMT | WW - 2021 | 740 | 1 | 0 | 2021 | 2021
748 | MBE-7 | Drill and Complete | 21 | 6251 | 20.1042 | 378 | 378 | 2021-01-28 | 2021-01-29 | PRODLNR1, CSGCMT | WW - 2021 | 378 | 1 | 0 | 2021 | 2021
749 | MBE-7 | Drill and Complete | 22 | 7065 | 21.1042 | 814 | 814 | 2021-01-29 | 2021-01-30 | PRODLNR1, CSGCMT | WW - 2021 | 814 | 1 | 0 | 2021 | 2021
750 | MBE-7 | Drill and Complete | 23 | 7065 | 22.1042 | 0 | 0 | 2021-01-30 | 2021-01-31 | PRODLNR2, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
751 | MBE-7 | Drill and Complete | 24 | 7065 | 23.1042 | 0 | 0 | 2021-01-31 | 2021-02-01 | PRODLNR3, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
752 | MBE-7 | Drill and Complete | 25 | 7065 | 24.1042 | 0 | 0 | 2021-02-01 | 2021-02-02 | PRODLNR3, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
753 | WWA-9 | Drill and Complete | 1 | 182 | 0.083333 | 0 | 0 | 2021-03-03 22:00 | 2021-03-04 |  | WW - 2021 | 182 | 0.083333 | 0 | 2021 | 2021
754 | WWA-9 | Drill and Complete | 2 | 810 | 1.0833 | 628 | 628 | 2021-03-04 | 2021-03-05 |  | WW - 2021 | 628 | 1 | 0 | 2021 | 2021
755 | WWA-9 | Drill and Complete | 3 | 1434 | 2.0833 | 624 | 624 | 2021-03-05 | 2021-03-06 |  | WW - 2021 | 624 | 1 | 0 | 2021 | 2021
756 | WWA-9 | Drill and Complete | 4 | 1434 | 3.0833 | 0 | 0 | 2021-03-06 | 2021-03-07 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
757 | WWA-9 | Drill and Complete | 5 | 1434 | 4.0833 | 0 | 0 | 2021-03-07 | 2021-03-08 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
758 | WWA-9 | Drill and Complete | 6 | 1600 | 5.0833 | 166 | 166 | 2021-03-08 | 2021-03-09 | SURF, CSGCMT | WW - 2021 | 166 | 1 | 0 | 2021 | 2021
759 | WWA-9 | Drill and Complete | 7 | 2614 | 6.0833 | 1014 | 1014 | 2021-03-09 | 2021-03-10 | SURF, CSGCMT | WW - 2021 | 1014 | 1 | 0 | 2021 | 2021
760 | WWA-9 | Drill and Complete | 8 | 3200 | 7.0833 | 586 | 586 | 2021-03-10 | 2021-03-11 | SURF, CSGCMT | WW - 2021 | 586 | 1 | 0 | 2021 | 2021
761 | WWA-9 | Drill and Complete | 9 | 3200 | 8.0833 | 0 | 0 | 2021-03-11 | 2021-03-12 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
762 | WWA-9 | Drill and Complete | 10 | 3200 | 9.0833 | 0 | 0 | 2021-03-12 | 2021-03-13 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
763 | WWA-9 | Drill and Complete | 11 | 3200 | 10.0833 | 0 | 0 | 2021-03-13 | 2021-03-14 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
764 | WWA-9 | Drill and Complete | 12 | 3200 | 11.0833 | 0 | 0 | 2021-03-14 | 2021-03-15 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
765 | WWA-9 | Drill and Complete | 13 | 3485 | 12.0833 | 285 | 285 | 2021-03-15 | 2021-03-16 | DRLGLNR, TB | WW - 2021 | 285 | 1 | 0 | 2021 | 2021
766 | WWA-9 | Drill and Complete | 14 | 4805 | 13.0833 | 1320 | 1320 | 2021-03-16 | 2021-03-17 | DRLGLNR, TB | WW - 2021 | 1320 | 1 | 0 | 2021 | 2021
767 | WWA-9 | Drill and Complete | 15 | 5246 | 14.0833 | 441 | 441 | 2021-03-17 | 2021-03-18 | PRODLNR1, CSGCMT | WW - 2021 | 441 | 1 | 0 | 2021 | 2021
768 | WWA-9 | Drill and Complete | 16 | 5246 | 15.0833 |  |  | 2021-03-18 | 2021-03-19 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
769 | WWA-9 | Drill and Complete | 17 | 6214 | 16.0833 | 968 | 968 | 2021-03-19 | 2021-03-20 | PRODLNR1, CSGCMT | WW - 2021 | 968 | 1 | 0 | 2021 | 2021
770 | WWA-9 | Drill and Complete | 18 | 7158 | 17.0833 | 944 | 944 | 2021-03-20 | 2021-03-21 | PRODLNR1, CSGCMT | WW - 2021 | 944 | 1 | 0 | 2021 | 2021
771 | WWA-9 | Drill and Complete | 19 | 7158 | 18.0833 | 0 | 0 | 2021-03-21 | 2021-03-22 | PRODLNR2, DRILL | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
772 | WWA-9 | Drill and Complete | 20 | 7158 | 18.4583 | 0 | 0 | 2021-03-22 | 2021-03-23 | PRODLNR2, DRILL | WW - 2021 | 0 | 0.375 | 0.375 | 2021 | 2021
773 | WWA-8 | Drill and Complete | 1 | 735 | 1 | 554 | 554 | 2021-03-25 | 2021-03-26 |  | WW - 2021 | 735 | 1 | 0 | 2021 | 2021
774 | WWA-8 | Drill and Complete | 2 | 1274 | 2 | 539 | 539 | 2021-03-26 | 2021-03-27 |  | WW - 2021 | 539 | 1 | 0 | 2021 | 2021
775 | WWA-8 | Drill and Complete | 3 | 1274 | 3 | 0 | 0 | 2021-03-27 | 2021-03-28 |  | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
776 | WWA-8 | Drill and Complete | 4 | 1274 | 4 | 0 | 0 | 2021-03-28 | 2021-03-29 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
777 | WWA-8 | Drill and Complete | 5 | 1274 | 5 | 0 | 0 | 2021-03-29 | 2021-03-30 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
778 | WWA-8 | Drill and Complete | 6 | 1324 | 6 | 50 | 50 | 2021-03-30 | 2021-03-31 | SURF, CSGCMT | WW - 2021 | 50 | 1 | 1 | 2021 | 2021
779 | WWA-8 | Drill and Complete | 7 | 2378 | 7 | -11946 | 1054 | 2021-03-31 | 2021-04-01 | SURF, CSGCMT | WW - 2021 | 1054 | 1 | 0 | 2021 | 2021
780 | WWA-8 | Drill and Complete | 8 | 3087 | 8 | 709 | 709 | 2021-04-01 | 2021-04-02 | SURF, CSGCMT | WW - 2021 | 709 | 1 | 0 | 2021 | 2021
781 | WWA-8 | Drill and Complete | 9 | 3087 | 9 | 0 | 0 | 2021-04-02 | 2021-04-03 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
782 | WWA-8 | Drill and Complete | 10 | 3087 | 10 | 0 | 0 | 2021-04-03 | 2021-04-04 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
783 | WWA-8 | Drill and Complete | 11 | 3087 | 11 | 0 | 0 | 2021-04-04 | 2021-04-05 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
784 | WWA-8 | Drill and Complete | 12 | 3087 | 12 | 0 | 0 | 2021-04-05 | 2021-04-06 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
785 | WWA-8 | Drill and Complete | 13 | 3087 | 13 | 0 | 0 | 2021-04-06 | 2021-04-07 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
786 | WWA-8 | Drill and Complete | 14 | 3087 | 14 | 0 | 0 | 2021-04-07 | 2021-04-08 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
787 | WWA-8 | Drill and Complete | 15 | 3943 | 15 | 856 | 856 | 2021-04-08 | 2021-04-09 | DRLGLNR, TB | WW - 2021 | 856 | 1 | 0 | 2021 | 2021
788 | WWA-8 | Drill and Complete | 16 | 5075 | 16 | 1132 | 1132 | 2021-04-09 | 2021-04-10 | DRLGLNR, TB | WW - 2021 | 1132 | 1 | 0 | 2021 | 2021
789 | WWA-8 | Drill and Complete | 17 | 5263 | 17 | 188 | 188 | 2021-04-10 | 2021-04-11 | DRLGLNR, TB | WW - 2021 | 188 | 1 | 0 | 2021 | 2021
790 | WWA-8 | Drill and Complete | 18 | 5263 | 18 | 0 | 0 | 2021-04-11 | 2021-04-12 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
791 | WWA-8 | Drill and Complete | 19 | 5263 | 19 | 0 | 0 | 2021-04-12 | 2021-04-13 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
792 | WWA-8 | Drill and Complete | 20 | 5263 | 20 | 0 | 0 | 2021-04-13 | 2021-04-14 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
793 | WWA-8 | Drill and Complete | 21 | 5263 | 21 | 0 | 0 | 2021-04-14 | 2021-04-15 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
794 | WWA-8 | Drill and Complete | 22 | 5263 | 22 |  |  | 2021-04-15 | 2021-04-16 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
795 | WWA-8 | Drill and Complete | 23 | 5263 | 23 | 0 | 0 | 2021-04-16 | 2021-04-17 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
796 | WWA-8 | Drill and Complete | 24 | 5263 | 24 |  |  | 2021-04-17 | 2021-04-18 | DRLGLNR, TB | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
797 | WWA-8 | Drill and Complete | 25 | 3396 | 25 | 198 | 198 | 2021-04-18 | 2021-04-19 |  | WW - 2021 | -1867 | 1 | 1 | 2021 | 2021
798 | WWA-8 | Drill and Complete | 26 | 3940 | 26 | 544 | 544 | 2021-04-19 | 2021-04-20 |  | WW - 2021 | 544 | 1 | 0 | 2021 | 2021
799 | WWA-8 | Drill and Complete | 27 | 4317 | 27 | 377 | 377 | 2021-04-20 | 2021-04-21 |  | WW - 2021 | 377 | 1 | 0 | 2021 | 2021
800 | WWA-8 | Drill and Complete | 28 | 4317 | 28 | 0 | 0 | 2021-04-21 | 2021-04-22 |  | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
801 | WWA-8 | Drill and Complete | 29 | 4317 | 29 | 0 | 0 | 2021-04-22 | 2021-04-23 |  | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
802 | WWA-8 | Drill and Complete | 30 | 4317 | 30 | 0 | 0 | 2021-04-23 | 2021-04-24 |  | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
803 | WWA-8 | Drill and Complete | 31 | 4317 | 31 | 0 | 0 | 2021-04-24 | 2021-04-25 |  | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
804 | WWA-8 | Drill and Complete | 32 | 0 | 32 |  |  | 2021-04-25 | 2021-04-26 |  | WW - 2021 | -4317 | 1 | 1 | 2021 | 2021
805 | WWA-8 | Drill and Complete | 33 | 2874 | 33 | 13 | 13 | 2021-04-26 | 2021-04-27 |  | WW - 2021 | 2874 | 1 | 0 | 2021 | 2021
806 | WWA-8 | Drill and Complete | 34 | 2878 | 34 | 4 | 4 | 2021-04-27 | 2021-04-28 |  | WW - 2021 | 4 | 1 | 1 | 2021 | 2021
807 | WWA-8 | Drill and Complete | 35 | 2881 | 35 | 3 | 3 | 2021-04-28 | 2021-04-29 |  | WW - 2021 | 3 | 1 | 1 | 2021 | 2021
808 | WWA-8 | Drill and Complete | 36 | 2883.6 | 36 | 1.2 | 1.2 | 2021-04-29 | 2021-04-30 |  | WW - 2021 | 2.6 | 1 | 1 | 2021 | 2021
809 | WWA-8 | Drill and Complete | 37 | 2924 | 37 | 40.4 | 40.4 | 2021-04-30 | 2021-05-01 |  | WW - 2021 | 40.4 | 1 | 1 | 2021 | 2021
810 | WWA-8 | Drill and Complete | 38 | 3700 | 38 | 776 | 776 | 2021-05-01 | 2021-05-02 |  | WW - 2021 | 776 | 1 | 0 | 2021 | 2021
811 | WWA-8 | Drill and Complete | 39 | 3921 | 39 | 221 | 221 | 2021-05-02 | 2021-05-03 | PRODLNR1, CSGCMT | WW - 2021 | 221 | 1 | 0 | 2021 | 2021
812 | WWA-8 | Drill and Complete | 40 | 4125 | 40 | 204 | 204 | 2021-05-03 | 2021-05-04 | PRODLNR1, CSGCMT | WW - 2021 | 204 | 1 | 0 | 2021 | 2021
813 | WWA-8 | Drill and Complete | 41 | 4125 | 41 | 0 | 0 | 2021-05-04 | 2021-05-05 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
814 | WWA-8 | Drill and Complete | 42 | 4287 | 42 | 162 | 162 | 2021-05-05 | 2021-05-06 | PRODLNR1, CSGCMT | WW - 2021 | 162 | 1 | 0 | 2021 | 2021
815 | WWA-8 | Drill and Complete | 43 | 4287 | 43 | 0 | 0 | 2021-05-06 | 2021-05-07 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
816 | WWA-8 | Drill and Complete | 44 | 4287 | 44 | 0 | 0 | 2021-05-07 | 2021-05-08 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
817 | WWA-8 | Drill and Complete | 45 | 4287 | 45 | 0 | 0 | 2021-05-08 | 2021-05-09 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
818 | WWA-8 | Drill and Complete | 46 | 4287 | 45.2292 | 0 | 0 | 2021-05-09 | 2021-05-10 05:30 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 0.22917 | 0.22917 | 2021 | 2021
819 | MBI-1 | Drill and Complete | 1 | 449 | 0.41667 | 222 | 222 | 2021-05-27 14:00 | 2021-05-28 |  | WW - 2021 | 449 | 0.41667 | 0 | 2021 | 2021
820 | MBI-1 | Drill and Complete | 2 | 1030 | 1.4167 | 581 | 581 | 2021-05-28 | 2021-05-29 |  | WW - 2021 | 581 | 1 | 0 | 2021 | 2021
821 | MBI-1 | Drill and Complete | 3 | 1030 | 2.4167 | 0 | 0 | 2021-05-29 | 2021-05-30 | SURF, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
822 | MBI-1 | Drill and Complete | 4 | 1137 | 3.4167 | 107 | 107 | 2021-05-30 | 2021-05-31 | SURF, CSGCMT | WW - 2021 | 107 | 1 | 0 | 2021 | 2021
823 | MBI-1 | Drill and Complete | 5 | 2043 | 4.4167 | 906 | 906 | 2021-05-31 | 2021-06-01 | SURF, CSGCMT | WW - 2021 | 906 | 1 | 0 | 2021 | 2021
824 | MBI-1 | Drill and Complete | 6 | 2260 | 5.4167 | 217 | 217 | 2021-06-01 | 2021-06-02 | DRLGLNR1, CSGCMT | WW - 2021 | 217 | 1 | 0 | 2021 | 2021
825 | MBI-1 | Drill and Complete | 7 | 2260 | 6.4167 | 0 | 0 | 2021-06-02 | 2021-06-03 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
826 | MBI-1 | Drill and Complete | 8 | 2260 | 7.4167 | 0 | 0 | 2021-06-03 | 2021-06-04 | DRLGLNR1, CSGCMT | WW - 2021 | 0 | 1 | 1 | 2021 | 2021
827 | MBI-1 | Drill and Complete | 9 | 2869 | 8.4167 | 609 | 609 | 2021-06-04 | 2021-06-05 | DRLGLNR1, CSGCMT | WW - 2021 | 609 | 1 | 0 | 2021 | 2021
828 | MBI-1 | Drill and Complete | 10 | 4224 | 9.4167 | 1355 | 1355 | 2021-06-05 | 2021-06-06 | DRLGLNR1, CSGCMT | WW - 2021 | 1355 | 1 | 0 | 2021 | 2021
829 | MBI-1 | Drill and Complete | 11 | 4325 | 10.4167 | 101 | 101 | 2021-06-06 | 2021-06-07 | PRODLNR1, CSGCMT | WW - 2021 | 101 | 1 | 0 | 2021 | 2021
830 | MBI-1 | Drill and Complete | 12 | 4325 | 10.9167 | 0 | 0 | 2021-06-07 | 2021-06-07 12:00 | PRODLNR1, CSGCMT | WW - 2021 | 0 | 0.5 | 0.5 | 2021 | 2021
831 | AWI 21-5 | Drill and Complete | 1 | 182 | 0.10417 | 2 | 2 | 2021-07-07 21:30 | 2021-07-08 | SURF, DRILL | SLK - 2021 | 182 | 0.10417 | 0 | 2021 | 2021
832 | AWI 21-5 | Drill and Complete | 2 | 678 | 1.1042 | 496 | 496 | 2021-07-08 | 2021-07-09 | SURF, DRILL | SLK - 2021 | 496 | 1 | 0 | 2021 | 2021
833 | AWI 21-5 | Drill and Complete | 3 | 1250 | 2.1042 | 572 | 572 | 2021-07-09 | 2021-07-10 | SURF, DRILL | SLK - 2021 | 572 | 1 | 0 | 2021 | 2021
834 | AWI 21-5 | Drill and Complete | 4 | 1250 | 3.1042 | 0 | 0 | 2021-07-10 | 2021-07-11 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
835 | AWI 21-5 | Drill and Complete | 5 | 1260 | 4.1042 | 10 | 10 | 2021-07-11 | 2021-07-12 | SURF, CSGCMT | SLK - 2021 | 10 | 1 | 1 | 2021 | 2021
836 | AWI 21-5 | Drill and Complete | 6 | 2094 | 5.1042 | 834 | 834 | 2021-07-12 | 2021-07-13 | SURF, CSGCMT | SLK - 2021 | 834 | 1 | 0 | 2021 | 2021
837 | AWI 21-5 | Drill and Complete | 7 | 2842 | 6.1042 | 711 | 711 | 2021-07-13 | 2021-07-14 | SURF, CSGCMT | SLK - 2021 | 748 | 1 | 0 | 2021 | 2021
838 | AWI 21-5 | Drill and Complete | 8 | 2937 | 7.1042 | 95 | 95 | 2021-07-14 | 2021-07-15 | DRLGLNR1, CSGCMT | SLK - 2021 | 95 | 1 | 0 | 2021 | 2021
839 | AWI 21-5 | Drill and Complete | 9 | 2937 | 8.1042 | 0 | 0 | 2021-07-15 | 2021-07-16 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
840 | AWI 21-5 | Drill and Complete | 10 | 2937 | 9.1042 | 0 | 0 | 2021-07-16 | 2021-07-17 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
841 | AWI 21-5 | Drill and Complete | 11 | 2937 | 10.1042 | 0 | 0 | 2021-07-17 | 2021-07-18 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
842 | AWI 21-5 | Drill and Complete | 12 | 2937 | 11.1042 | 0 | 0 | 2021-07-18 | 2021-07-19 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
843 | AWI 21-5 | Drill and Complete | 13 | 2937 | 12.1042 | 0 | 0 | 2021-07-19 | 2021-07-20 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
844 | AWI 21-5 | Drill and Complete | 14 | 2937 | 13.1042 | 0 | 0 | 2021-07-20 | 2021-07-21 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
845 | AWI 21-5 | Drill and Complete | 15 | 2937 | 14.1042 | 0 | 0 | 2021-07-21 | 2021-07-22 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
846 | AWI 21-5 | Drill and Complete | 16 | 2937 | 15.1042 | 0 | 0 | 2021-07-22 | 2021-07-23 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
847 | AWI 21-5 | Drill and Complete | 17 | 2937 | 16.1042 | 0 | 0 | 2021-07-23 | 2021-07-24 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
848 | AWI 21-5 | Drill and Complete | 18 | 2937 | 17.1042 | 0 | 0 | 2021-07-24 | 2021-07-25 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
849 | AWI 21-5 | Drill and Complete | 19 | 3473 | 18.1042 | 536 | 536 | 2021-07-25 | 2021-07-26 | DRLGLNR, TB | SLK - 2021 | 536 | 1 | 0 | 2021 | 2021
850 | AWI 21-5 | Drill and Complete | 20 | 4243 | 19.1042 | 770 | 770 | 2021-07-26 | 2021-07-27 | DRLGLNR, TB | SLK - 2021 | 770 | 1 | 0 | 2021 | 2021
851 | AWI 21-5 | Drill and Complete | 21 | 4685 | 20.1042 | 442 | 442 | 2021-07-27 | 2021-07-28 | DRLGLNR, TB | SLK - 2021 | 442 | 1 | 0 | 2021 | 2021
852 | AWI 21-5 | Drill and Complete | 22 | 4685 | 21.1042 | 0 | 0 | 2021-07-28 | 2021-07-29 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
853 | AWI 21-5 | Drill and Complete | 23 | 4685 | 22.0625 | 0 | 0 | 2021-07-29 | 2021-07-29 23:00 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 0.95833 | 0.95833 | 2021 | 2021
854 | AWI 21-6 | Drill and Complete | 1 | 369 | 0.5 | 178 | 178 | 2021-08-01 12:00 | 2021-08-02 | SURF, DRILL | SLK - 2021 | 369 | 0.5 | 0 | 2021 | 2021
855 | AWI 21-6 | Drill and Complete | 2 | 881 | 1.5 | 512 | 512 | 2021-08-02 | 2021-08-03 | SURF, DRILL | SLK - 2021 | 512 | 1 | 0 | 2021 | 2021
856 | AWI 21-6 | Drill and Complete | 3 | 1365 | 2.5 | 484 | 484 | 2021-08-03 | 2021-08-04 | SURF, DRILL | SLK - 2021 | 484 | 1 | 0 | 2021 | 2021
857 | AWI 21-6 | Drill and Complete | 4 | 1365 | 3.5 | 0 | 0 | 2021-08-04 | 2021-08-05 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
858 | AWI 21-6 | Drill and Complete | 5 | 1485 | 4.5 | 120 | 120 | 2021-08-05 | 2021-08-06 | SURF, CSGCMT | SLK - 2021 | 120 | 1 | 0 | 2021 | 2021
859 | AWI 21-6 | Drill and Complete | 6 | 2307 | 5.5 | 822 | 822 | 2021-08-06 | 2021-08-07 | SURF, CSGCMT | SLK - 2021 | 822 | 1 | 0 | 2021 | 2021
860 | AWI 21-6 | Drill and Complete | 7 | 2936 | 6.5 | 629 | 629 | 2021-08-07 | 2021-08-08 | DRLGLNR1, CSGCMT | SLK - 2021 | 629 | 1 | 0 | 2021 | 2021
861 | AWI 21-6 | Drill and Complete | 8 | 2936 | 7.5 | 0 | 0 | 2021-08-08 | 2021-08-09 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
862 | AWI 21-6 | Drill and Complete | 9 | 2936 | 8.5 |  |  | 2021-08-09 | 2021-08-10 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
863 | AWI 21-6 | Drill and Complete | 10 | 2936 | 9.5 |  |  | 2021-08-10 | 2021-08-11 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
864 | AWI 21-6 | Drill and Complete | 11 | 4265 | 10.5 | 1329 | 1329 | 2021-08-11 | 2021-08-12 | DRLGLNR, TB | SLK - 2021 | 1329 | 1 | 0 | 2021 | 2021
865 | AWI 21-6 | Drill and Complete | 12 | 4918 | 11.5 | 653 | 653 | 2021-08-12 | 2021-08-13 | PRODLNR1, CSGCMT | SLK - 2021 | 653 | 1 | 0 | 2021 | 2021
866 | AWI 21-6 | Drill and Complete | 13 | 4918 | 12.5 | 0 | 0 | 2021-08-13 | 2021-08-14 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
867 | AWI 16-8 | Drill and Complete | 1 | 0 | 0.041667 |  |  | 2021-08-27 23:00 | 2021-08-28 | SURF, DRILL | SLK - 2021 | 0 | 0.041667 | 0.041667 | 2021 | 2021
868 | AWI 16-8 | Drill and Complete | 2 | 543 | 1.0417 | 352 | 352 | 2021-08-28 | 2021-08-29 | SURF, DRILL | SLK - 2021 | 543 | 1 | 0 | 2021 | 2021
869 | AWI 16-8 | Drill and Complete | 3 | 1140 | 2.0417 | 597 | 597 | 2021-08-29 | 2021-08-30 | SURF, DRILL | SLK - 2021 | 597 | 1 | 0 | 2021 | 2021
870 | AWI 16-8 | Drill and Complete | 4 | 1140 | 3.0417 | 0 | 0 | 2021-08-30 | 2021-08-31 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
871 | AWI 16-8 | Drill and Complete | 5 | 1320 | 4.0417 | 180 | 180 | 2021-08-31 | 2021-09-01 | SURF, CSGCMT | SLK - 2021 | 180 | 1 | 0 | 2021 | 2021
872 | AWI 16-8 | Drill and Complete | 6 | 2259 | 5.0417 | 939 | 939 | 2021-09-01 | 2021-09-02 | SURF, CSGCMT | SLK - 2021 | 939 | 1 | 0 | 2021 | 2021
873 | AWI 16-8 | Drill and Complete | 7 | 2919 | 6.0417 | 660 | 660 | 2021-09-02 | 2021-09-03 | SURF, CSGCMT | SLK - 2021 | 660 | 1 | 0 | 2021 | 2021
874 | AWI 16-8 | Drill and Complete | 8 | 3211 | 7.0417 | 292 | 292 | 2021-09-03 | 2021-09-04 | SURF, CSGCMT | SLK - 2021 | 292 | 1 | 0 | 2021 | 2021
875 | AWI 16-8 | Drill and Complete | 9 | 3211 | 8.0417 | 0 | 0 | 2021-09-04 | 2021-09-05 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
876 | AWI 16-8 | Drill and Complete | 10 | 3211 | 9.0417 | 0 | 0 | 2021-09-05 | 2021-09-06 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
877 | AWI 16-8 | Drill and Complete | 11 | 3211 | 10.0417 | 0 | 0 | 2021-09-06 | 2021-09-07 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
878 | AWI 16-8 | Drill and Complete | 12 | 3211 | 11.0417 | 0 | 0 | 2021-09-07 | 2021-09-08 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
879 | AWI 16-8 | Drill and Complete | 13 | 3211 | 12.0417 | 0 | 0 | 2021-09-08 | 2021-09-09 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
880 | AWI 16-8 | Drill and Complete | 14 | 3211 | 13.0417 | 0 | 0 | 2021-09-09 | 2021-09-10 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
881 | AWI 16-8 | Drill and Complete | 15 | 3211 | 14.0417 | 0 | 0 | 2021-09-10 | 2021-09-11 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
882 | AWI 16-8 | Drill and Complete | 16 | 3211 | 15.0417 | 0 | 0 | 2021-09-11 | 2021-09-12 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
883 | AWI 16-8 | Drill and Complete | 17 | 3211 | 16.0417 | 0 | 0 | 2021-09-12 | 2021-09-13 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
884 | AWI 16-8 | Drill and Complete | 18 | 3211 | 17.0417 | 0 | 0 | 2021-09-13 | 2021-09-14 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
885 | AWI 16-8 | Drill and Complete | 19 | 3211 | 18.0417 | 0 | 0 | 2021-09-14 | 2021-09-15 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
886 | AWI 16-8 | Drill and Complete | 20 | 3625 | 19.0417 | 414 | 414 | 2021-09-15 | 2021-09-16 | DRLGLNR1, CSGCMT | SLK - 2021 | 414 | 1 | 0 | 2021 | 2021
887 | AWI 16-8 | Drill and Complete | 21 | 3625 | 20.0417 | 0 | 0 | 2021-09-16 | 2021-09-17 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
888 | AWI 16-8 | Drill and Complete | 22 | 3625 | 21.0417 | 0 | 0 | 2021-09-17 | 2021-09-18 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
889 | AWI 16-8 | Drill and Complete | 23 | 3625 | 22.0417 | 0 | 0 | 2021-09-18 | 2021-09-19 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
890 | AWI 16-8 | Drill and Complete | 24 | 3625 | 23.0417 | 0 | 0 | 2021-09-19 | 2021-09-20 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
891 | AWI 16-8 | Drill and Complete | 25 | 3988 | 24.0417 | 363 | 363 | 2021-09-20 | 2021-09-21 | PRODLNR1, CSGCMT | SLK - 2021 | 363 | 1 | 0 | 2021 | 2021
892 | AWI 16-8 | Drill and Complete | 26 | 4114 | 25.0417 | 126 | 126 | 2021-09-21 | 2021-09-22 | PRODLNR1, CSGCMT | SLK - 2021 | 126 | 1 | 0 | 2021 | 2021
893 | AWI 16-8 | Drill and Complete | 27 | 4114 | 26.0417 | 0 | 0 | 2021-09-22 | 2021-09-23 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
894 | AWI 16-8 | Drill and Complete | 28 | 4114 | 27.0417 | 0 | 0 | 2021-09-23 | 2021-09-24 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
895 | AWI 16-8 | Drill and Complete | 29 | 4114 | 28.0417 | 0 | 0 | 2021-09-24 | 2021-09-25 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
896 | AWI 16-8 | Drill and Complete | 30 | 4114 | 29.0417 | 0 | 0 | 2021-09-25 | 2021-09-26 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
897 | AWI 16-8 | Drill and Complete | 31 | 4114 | 30.0417 | 0 | 0 | 2021-09-26 | 2021-09-27 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
898 | AWI 16-8 | Drill and Complete | 32 | 4114 | 31.0417 | 0 | 0 | 2021-09-27 | 2021-09-28 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
899 | AWI 16-8 | Drill and Complete | 33 | 4114 | 32.0417 | 0 | 0 | 2021-09-28 | 2021-09-29 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
900 | AWI 16-8 | Drill and Complete | 34 | 4114 | 33.0417 | 0 | 0 | 2021-09-29 | 2021-09-30 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
901 | AWI 16-8 | Drill and Complete | 35 | 4114 | 34.0417 | 0 | 0 | 2021-09-30 | 2021-10-01 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
902 | AWI 16-8 | Drill and Complete | 36 | 4114 | 35.0417 | 0 | 0 | 2021-10-01 | 2021-10-02 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
903 | AWI 16-8 | Drill and Complete | 37 | 4114 | 36.0417 | 0 | 0 | 2021-10-02 | 2021-10-03 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
904 | AWI 16-8 | Drill and Complete | 38 | 4114 | 37.0417 | 0 | 0 | 2021-10-03 | 2021-10-04 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
905 | AWI 16-8 | Drill and Complete | 39 | 4114 | 38.0417 | 0 | 0 | 2021-10-04 | 2021-10-05 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
906 | AWI 16-8 | Drill and Complete | 40 | 4114 | 38.5417 | 0 | 0 | 2021-10-05 | 2021-10-06 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 0.5 | 0.5 | 2021 | 2021
907 | AWI 16-9 | Drill and Complete | 1 | 570 | 1 | 380 | 380 | 2021-10-08 | 2021-10-09 |  | SLK - 2021 | 570 | 1 | 0 | 2021 | 2021
908 | AWI 16-9 | Drill and Complete | 2 | 747 | 2 | 177 | 177 | 2021-10-09 | 2021-10-10 |  | SLK - 2021 | 177 | 1 | 0 | 2021 | 2021
909 | AWI 16-9 | Drill and Complete | 3 | 1388 | 3 | 641 | 641 | 2021-10-10 | 2021-10-11 |  | SLK - 2021 | 641 | 1 | 0 | 2021 | 2021
910 | AWI 16-9 | Drill and Complete | 4 | 1470 | 4 | 82 | 82 | 2021-10-11 | 2021-10-12 | SURF, CSGCMT | SLK - 2021 | 82 | 1 | 0 | 2021 | 2021
911 | AWI 16-9 | Drill and Complete | 5 | 1470 | 5 | 0 | 0 | 2021-10-12 | 2021-10-13 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
912 | AWI 16-9 | Drill and Complete | 6 | 2211 | 6 | 741 | 741 | 2021-10-13 | 2021-10-14 | SURF, CSGCMT | SLK - 2021 | 741 | 1 | 0 | 2021 | 2021
913 | AWI 16-9 | Drill and Complete | 7 | 3092 | 7 | 881 | 881 | 2021-10-14 | 2021-10-15 | SURF, CSGCMT | SLK - 2021 | 881 | 1 | 0 | 2021 | 2021
914 | AWI 16-9 | Drill and Complete | 8 | 3344 | 8 | 252 | 252 | 2021-10-15 | 2021-10-16 | DRLGLNR1, CSGCMT | SLK - 2021 | 252 | 1 | 0 | 2021 | 2021
915 | AWI 16-9 | Drill and Complete | 9 | 3344 | 9 | 0 | 0 | 2021-10-16 | 2021-10-17 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
916 | AWI 16-9 | Drill and Complete | 10 | 3344 | 10 | 0 | 0 | 2021-10-17 | 2021-10-18 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
917 | AWI 16-9 | Drill and Complete | 11 | 3344 | 11 | 0 | 0 | 2021-10-18 | 2021-10-19 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
918 | AWI 16-9 | Drill and Complete | 12 | 3344 | 12 | 0 | 0 | 2021-10-19 | 2021-10-20 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
919 | AWI 16-9 | Drill and Complete | 13 | 3998 | 13 | 654 | 654 | 2021-10-20 | 2021-10-21 | DRLGLNR, TB | SLK - 2021 | 654 | 1 | 0 | 2021 | 2021
920 | AWI 16-9 | Drill and Complete | 14 | 4585 | 14 | 587 | 587 | 2021-10-21 | 2021-10-22 | DRLGLNR, TB | SLK - 2021 | 587 | 1 | 0 | 2021 | 2021
921 | AWI 16-9 | Drill and Complete | 15 | 5025 | 15 | 440 | 440 | 2021-10-22 | 2021-10-23 | DRLGLNR, TB | SLK - 2021 | 440 | 1 | 0 | 2021 | 2021
922 | AWI 16-9 | Drill and Complete | 16 | 5047 | 16 | 22 | 22 | 2021-10-23 | 2021-10-24 | PRODLNR1, CSGCMT | SLK - 2021 | 22 | 1 | 1 | 2021 | 2021
923 | AWI 16-9 | Drill and Complete | 17 | 5379 | 17 | 332 | 332 | 2021-10-24 | 2021-10-25 | PRODLNR2, CSGCMT | SLK - 2021 | 332 | 1 | 0 | 2021 | 2021
924 | AWI 16-9 | Drill and Complete | 18 | 5379 | 18 | 0 | 0 | 2021-10-25 | 2021-10-26 | PRODLNR2, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
925 | AWI 16-9 | Drill and Complete | 19 | 5379 | 18.2708 | 0 | 0 | 2021-10-26 | 2021-10-26 06:30 | PRODLNR2, CSGCMT | SLK - 2021 | 0 | 0.27083 | 0.27083 | 2021 | 2021
926 | AWI 9-10 | Drill and Complete | 1 | 0 | 0.041667 |  |  | 2021-11-19 23:00 | 2021-11-20 | SURF, DRILL | SLK - 2021 | 0 | 0.041667 | 0.041667 | 2021 | 2021
927 | AWI 9-10 | Drill and Complete | 2 | 1109 | 1.0417 | 918 | 918 | 2021-11-20 | 2021-11-21 | SURF, DRILL | SLK - 2021 | 1109 | 1 | 0 | 2021 | 2021
928 | AWI 9-10 | Drill and Complete | 3 | 1750 | 2.0417 | 641 | 641 | 2021-11-21 | 2021-11-22 | SURF, DRILL | SLK - 2021 | 641 | 1 | 0 | 2021 | 2021
929 | AWI 9-10 | Drill and Complete | 4 | 1750 | 3.0417 | 0 | 0 | 2021-11-22 | 2021-11-23 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
930 | AWI 9-10 | Drill and Complete | 5 | 1750 | 4.0417 | 0 | 0 | 2021-11-23 | 2021-11-24 | SURF, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
931 | AWI 9-10 | Drill and Complete | 6 | 2195 | 5.0417 | 445 | 445 | 2021-11-24 | 2021-11-25 | SURF, CSGCMT | SLK - 2021 | 445 | 1 | 0 | 2021 | 2021
932 | AWI 9-10 | Drill and Complete | 7 | 3164 | 6.0417 | 969 | 969 | 2021-11-25 | 2021-11-26 | SURF, CSGCMT | SLK - 2021 | 969 | 1 | 0 | 2021 | 2021
933 | AWI 9-10 | Drill and Complete | 8 | 3863 | 7.0417 | 699 | 699 | 2021-11-26 | 2021-11-27 | SURF, CSGCMT | SLK - 2021 | 699 | 1 | 0 | 2021 | 2021
934 | AWI 9-10 | Drill and Complete | 9 | 4554 | 8.0417 | 691 | 691 | 2021-11-27 | 2021-11-28 | SURF, CSGCMT | SLK - 2021 | 691 | 1 | 0 | 2021 | 2021
935 | AWI 9-10 | Drill and Complete | 10 | 4554 | 9.0417 | 0 | 0 | 2021-11-28 | 2021-11-29 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
936 | AWI 9-10 | Drill and Complete | 11 | 4554 | 10.0417 | 0 | 0 | 2021-11-29 | 2021-11-30 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
937 | AWI 9-10 | Drill and Complete | 12 | 4554 | 11.0417 | 0 | 0 | 2021-11-30 | 2021-12-01 | DRLGLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
938 | AWI 9-10 | Drill and Complete | 13 | 4554 | 12.0417 | 0 | 0 | 2021-12-01 | 2021-12-02 | DRLGLNR, TB | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
939 | AWI 9-10 | Drill and Complete | 14 | 4642 | 13.0417 | 88 | 88 | 2021-12-02 | 2021-12-03 | DRLGLNR, TB | SLK - 2021 | 88 | 1 | 0 | 2021 | 2021
940 | AWI 9-10 | Drill and Complete | 15 | 5424 | 14.0417 | 782 | 782 | 2021-12-03 | 2021-12-04 | DRLGLNR, TB | SLK - 2021 | 782 | 1 | 0 | 2021 | 2021
941 | AWI 9-10 | Drill and Complete | 16 | 6650 | 15.0417 | 1226 | 1226 | 2021-12-04 | 2021-12-05 | DRLGLNR, TB | SLK - 2021 | 1226 | 1 | 0 | 2021 | 2021
942 | AWI 9-10 | Drill and Complete | 17 | 7532 | 16.0417 | 882 | 882 | 2021-12-05 | 2021-12-06 | DRLGLNR, TB | SLK - 2021 | 882 | 1 | 0 | 2021 | 2021
943 | AWI 9-10 | Drill and Complete | 18 | 7532 | 17.0417 | 0 | 0 | 2021-12-06 | 2021-12-07 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
944 | AWI 9-10 | Drill and Complete | 19 | 8118 | 18.0417 | 586 | 586 | 2021-12-07 | 2021-12-08 | PRODLNR1, CSGCMT | SLK - 2021 | 586 | 1 | 0 | 2021 | 2021
945 | AWI 9-10 | Drill and Complete | 20 | 8825 | 19.0417 | 707 | 707 | 2021-12-08 | 2021-12-09 | PRODLNR1, CSGCMT | SLK - 2021 | 707 | 1 | 0 | 2021 | 2021
946 | AWI 9-10 | Drill and Complete | 21 | 8919 | 20.0417 | 94 | 94 | 2021-12-09 | 2021-12-10 | PRODLNR2, CSGCMT | SLK - 2021 | 94 | 1 | 0 | 2021 | 2021
947 | AWI 9-10 | Drill and Complete | 22 | 8919 | 21.0417 | 0 | 0 | 2021-12-10 | 2021-12-11 | PRODLNR2, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
948 | AWI 9-10 | Drill and Complete | 23 | 8919 | 22 | 0 | 0 | 2021-12-11 | 2021-12-12 | PRODLNR2, CSGCMT | SLK - 2021 | 0 | 0.95833 | 0.95833 | 2021 | 2021
949 | AWI 16-8 | Sidetrack | 1 | 0 | 0.64583 |  |  | 2021-12-26 08:30 | 2021-12-27 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 0.64583 | 0.64583 | 2021 | 2021
950 | AWI 16-8 | Sidetrack | 2 | 0 | 1.6458 |  |  | 2021-12-27 | 2021-12-28 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
951 | AWI 16-8 | Sidetrack | 3 | 0 | 2.6458 |  |  | 2021-12-28 | 2021-12-29 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
952 | AWI 16-8 | Sidetrack | 4 | 0 | 3.6458 |  |  | 2021-12-29 | 2021-12-30 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
953 | AWI 16-8 | Sidetrack | 5 | 0 | 4.6458 |  |  | 2021-12-30 | 2021-12-31 | PRODLNR1, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2021 | 2021
954 | AWI 16-8 | Sidetrack | 6 | 3144 | 5.6458 | 55 | 55 | 2021-12-31 | 2022-01-01 | PRODLNR1, CSGCMT | SLK - 2021 | 3144 | 1 | 0 | 2021 | 2021
955 | AWI 16-8 | Sidetrack | 7 | 3387 | 6.6458 | 243 | 243 | 2022-01-01 | 2022-01-02 | PRODLNR1, CSGCMT | SLK - 2021 | 243 | 1 | 0 | 2022 | 2022
956 | AWI 16-8 | Sidetrack | 8 | 4052 | 7.6458 | 665 | 665 | 2022-01-02 | 2022-01-03 | PRODLNR1, CSGCMT | SLK - 2021 | 665 | 1 | 0 | 2022 | 2022
957 | AWI 16-8 | Sidetrack | 9 | 4341 | 8.6458 | 289 | 289 | 2022-01-03 | 2022-01-04 | PRODLNR1, CSGCMT | SLK - 2021 | 289 | 1 | 0 | 2022 | 2022
958 | AWI 16-8 | Sidetrack | 10 | 4617 | 9.6458 | 276 | 276 | 2022-01-04 | 2022-01-05 | PRODLNR1, CSGCMT | SLK - 2021 | 276 | 1 | 0 | 2022 | 2022
959 | AWI 16-8 | Sidetrack | 11 | 5000 | 10.6458 | 383 | 383 | 2022-01-05 | 2022-01-06 | PRODLNR1, CSGCMT | SLK - 2021 | 383 | 1 | 0 | 2022 | 2022
960 | AWI 16-8 | Sidetrack | 12 | 5000 | 11.6458 | 0 | 0 | 2022-01-06 | 2022-01-07 | DRLGLNR2, CSGCMT | SLK - 2021 | 0 | 1 | 1 | 2022 | 2022
961 | AWI 16-8 | Sidetrack | 13 | 5000 | 12.5625 | 0 | 0 | 2022-01-07 | 2022-01-08 | DRLGLNR2, CSGCMT | SLK - 2021 | 0 | 0.91667 | 0.91667 | 2022 | 2022
962 | DRJ-38RD | Sidetrack | 1 | 3806 | 0.5 | 33 | 33 | 2022-02-01 12:00 | 2022-02-02 | PRODLNR3, CSGCMT | DRJ - 2022 | 3806 | 0.5 | 0 | 2022 | 2022
963 | DRJ-38RD | Sidetrack | 2 | 4678 | 1.5 | 127 | 127 | 2022-02-02 | 2022-02-03 | PRODLNR3, CSGCMT | DRJ - 2022 | 872 | 1 | 0 | 2022 | 2022
964 | DRJ-38RD | Sidetrack | 3 | 5685 | 2.5 | 1007 | 1007 | 2022-02-03 | 2022-02-04 | PRODLNR3, CSGCMT | DRJ - 2022 | 1007 | 1 | 0 | 2022 | 2022
965 | DRJ-38RD | Sidetrack | 4 | 5685 | 3.5 | 0 | 0 | 2022-02-04 | 2022-02-05 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
966 | DRJ-38RD | Sidetrack | 5 | 5685 | 4.5 |  |  | 2022-02-05 | 2022-02-06 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
967 | DRJ-38RD | Sidetrack | 6 | 5685 | 5.5 |  |  | 2022-02-06 | 2022-02-07 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
968 | DRJ-38RD | Sidetrack | 7 | 5685 | 6.5 |  |  | 2022-02-07 | 2022-02-08 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
969 | DRJ-38RD | Sidetrack | 8 | 5685 | 7.5 |  |  | 2022-02-08 | 2022-02-09 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
970 | DRJ-38RD | Sidetrack | 9 | 5685 | 8.5 |  |  | 2022-02-09 | 2022-02-10 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
971 | DRJ-38RD | Sidetrack | 10 | 1986 | 9.5 | 31 | 31 | 2022-02-10 | 2022-02-11 | PRODLNR3, CSGCMT | DRJ - 2022 | -3699 | 1 | 1 | 2022 | 2022
972 | DRJ-38RD | Sidetrack | 11 | 1986 | 10.5 | 0 | 0 | 2022-02-11 | 2022-02-12 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
973 | DRJ-38RD | Sidetrack | 12 | 1986 | 11.5 | 0 | 0 | 2022-02-12 | 2022-02-13 | PRODLNR3, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
974 | DRJ-38RD | Sidetrack | 13 | 2201 | 12.5 | 215 | 215 | 2022-02-13 | 2022-02-14 | DRLGLNR, TB | DRJ - 2022 | 215 | 1 | 0 | 2022 | 2022
975 | DRJ-38RD | Sidetrack | 14 | 2834 | 13.5 | 653 | 633 | 2022-02-14 | 2022-02-15 | DRLGLNR, TB | DRJ - 2022 | 633 | 1 | 0 | 2022 | 2022
976 | DRJ-38RD | Sidetrack | 15 | 3401 | 14.5 | 567 | 567 | 2022-02-15 | 2022-02-16 | DRLGLNR, TB | DRJ - 2022 | 567 | 1 | 0 | 2022 | 2022
977 | DRJ-38RD | Sidetrack | 16 | 3902 | 15.5 | 501 | 501 | 2022-02-16 | 2022-02-17 | DRLGLNR, TB | DRJ - 2022 | 501 | 1 | 0 | 2022 | 2022
978 | DRJ-38RD | Sidetrack | 17 | 4525 | 16.5 | 623 | 623 | 2022-02-17 | 2022-02-18 | DRLGLNR, TB | DRJ - 2022 | 623 | 1 | 0 | 2022 | 2022
979 | DRJ-38RD | Sidetrack | 18 | 4525 | 17.5 | 0 | 0 | 2022-02-18 | 2022-02-19 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
980 | DRJ-38RD | Sidetrack | 19 | 4525 | 18.5 | 0 | 0 | 2022-02-19 | 2022-02-20 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
981 | DRJ-38RD | Sidetrack | 20 | 4525 | 19.5 | 0 | 0 | 2022-02-20 | 2022-02-21 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
982 | DRJ-38RD | Sidetrack | 21 | 4525 | 20.5 | 0 | 0 | 2022-02-21 | 2022-02-22 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
983 | DRJ-38RD | Sidetrack | 22 | 4880 | 21.5 | 355 | 355 | 2022-02-22 | 2022-02-23 | DRLGLNR1, CSGCMT | DRJ - 2022 | 355 | 1 | 0 | 2022 | 2022
984 | DRJ-38RD | Sidetrack | 23 | 5258 | 22.5 | 378 | 378 | 2022-02-23 | 2022-02-24 | DRLGLNR1, CSGCMT | DRJ - 2022 | 378 | 1 | 0 | 2022 | 2022
985 | DRJ-38RD | Sidetrack | 24 | 5508 | 23.5 | 250 | 250 | 2022-02-24 | 2022-02-25 | DRLGLNR1, CSGCMT | DRJ - 2022 | 250 | 1 | 0 | 2022 | 2022
986 | DRJ-38RD | Sidetrack | 25 | 5743 | 24.5 | 235 | 235 | 2022-02-25 | 2022-02-26 | DRLGLNR1, CSGCMT | DRJ - 2022 | 235 | 1 | 0 | 2022 | 2022
987 | DRJ-38RD | Sidetrack | 26 | 6045 | 25.5 | 302 | 302 | 2022-02-26 | 2022-02-27 | DRLGLNR1, CSGCMT | DRJ - 2022 | 302 | 1 | 0 | 2022 | 2022
988 | DRJ-38RD | Sidetrack | 27 | 6295 | 26.5 | 250 | 250 | 2022-02-27 | 2022-02-28 | DRLGLNR1, CSGCMT | DRJ - 2022 | 250 | 1 | 0 | 2022 | 2022
989 | DRJ-38RD | Sidetrack | 28 | 6371 | 27.5 | 76 | 76 | 2022-02-28 | 2022-03-01 | DRLGLNR1, CSGCMT | DRJ - 2022 | 76 | 1 | 0 | 2022 | 2022
990 | DRJ-38RD | Sidetrack | 29 | 6639 | 28.5 | 268 | 268 | 2022-03-01 | 2022-03-02 | DRLGLNR1, CSGCMT | DRJ - 2022 | 268 | 1 | 0 | 2022 | 2022
991 | DRJ-38RD | Sidetrack | 30 | 6748 | 29.5 | 109 | 109 | 2022-03-02 | 2022-03-03 | PRODLNR1, CSGMILL | DRJ - 2022 | 109 | 1 | 0 | 2022 | 2022
992 | DRJ-38RD | Sidetrack | 31 | 6748 | 30 | 0 | 0 | 2022-03-03 | 2022-03-03 12:00 | PRODLNR1, CSGMILL | DRJ - 2022 | 0 | 0.5 | 0.5 | 2022 | 2022
993 | DRJ-49 | Drill and Complete | 1 | 335 | 0.54167 | 103 | 103 | 2022-03-06 11:00 | 2022-03-07 |  | DRJ - 2022 | 335 | 0.54167 | 0 | 2022 | 2022
994 | DRJ-49 | Drill and Complete | 2 | 360 | 1.5417 | 25 | 25 | 2022-03-07 | 2022-03-08 |  | DRJ - 2022 | 25 | 1 | 1 | 2022 | 2022
995 | DRJ-49 | Drill and Complete | 3 | 365 | 2.5417 | 5 | 5 | 2022-03-08 | 2022-03-09 |  | DRJ - 2022 | 5 | 1 | 1 | 2022 | 2022
996 | DRJ-49 | Drill and Complete | 4 | 378 | 3.5417 | 13 | 13 | 2022-03-09 | 2022-03-10 |  | DRJ - 2022 | 13 | 1 | 1 | 2022 | 2022
997 | DRJ-49 | Drill and Complete | 5 | 378 | 4.5417 | 0 | 0 | 2022-03-10 | 2022-03-11 |  | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
998 | DRJ-49 | Drill and Complete | 6 | 378 | 5.5417 | 0 | 0 | 2022-03-11 | 2022-03-12 |  | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
999 | DRJ-49 | Drill and Complete | 7 | 305 | 6.5417 | 138 | 138 | 2022-03-12 | 2022-03-13 |  | DRJ - 2022 | -73 | 1 | 1 | 2022 | 2022
1000 | DRJ-49 | Drill and Complete | 8 | 305 | 7.5417 | 0 | 0 | 2022-03-13 | 2022-03-14 |  | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1001 | DRJ-49 | Drill and Complete | 9 | 394 | 8.5417 | 7 | 7 | 2022-03-14 | 2022-03-15 |  | DRJ - 2022 | 89 | 1 | 0 | 2022 | 2022
1002 | DRJ-49 | Drill and Complete | 10 | 490 | 9.5417 | 96 | 96 | 2022-03-15 | 2022-03-16 |  | DRJ - 2022 | 96 | 1 | 0 | 2022 | 2022
1003 | DRJ-49 | Drill and Complete | 11 | 903 | 10.5417 | 413 | 413 | 2022-03-16 | 2022-03-17 |  | DRJ - 2022 | 413 | 1 | 0 | 2022 | 2022
1004 | DRJ-49 | Drill and Complete | 12 | 1335 | 11.5417 | 432 | 432 | 2022-03-17 | 2022-03-18 |  | DRJ - 2022 | 432 | 1 | 0 | 2022 | 2022
1005 | DRJ-49 | Drill and Complete | 13 | 1851 | 12.5417 | 516 | 516 | 2022-03-18 | 2022-03-19 |  | DRJ - 2022 | 516 | 1 | 0 | 2022 | 2022
1006 | DRJ-49 | Drill and Complete | 14 | 1952 | 13.5417 | 101 | 101 | 2022-03-19 | 2022-03-20 |  | DRJ - 2022 | 101 | 1 | 0 | 2022 | 2022
1007 | DRJ-49 | Drill and Complete | 15 | 1952 | 14.5417 | 0 | 0 | 2022-03-20 | 2022-03-21 |  | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1008 | DRJ-49 | Drill and Complete | 16 | 1952 | 15.5417 | 0 | 0 | 2022-03-21 | 2022-03-22 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1009 | DRJ-49 | Drill and Complete | 17 | 1952 | 16.5417 | 0 | 0 | 2022-03-22 | 2022-03-23 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1010 | DRJ-49 | Drill and Complete | 18 | 2496 | 17.5417 | 544 | 544 | 2022-03-23 | 2022-03-24 | SURF, CSGCMT | DRJ - 2022 | 544 | 1 | 0 | 2022 | 2022
1011 | DRJ-49 | Drill and Complete | 19 | 3000 | 18.5417 | 504 | 504 | 2022-03-24 | 2022-03-25 | SURF, CSGCMT | DRJ - 2022 | 504 | 1 | 0 | 2022 | 2022
1012 | DRJ-49 | Drill and Complete | 20 | 3454 | 19.5417 | 454 | 454 | 2022-03-25 | 2022-03-26 | SURF, CSGCMT | DRJ - 2022 | 454 | 1 | 0 | 2022 | 2022
1013 | DRJ-49 | Drill and Complete | 21 | 3631 | 20.5417 | 177 | 177 | 2022-03-26 | 2022-03-27 | SURF, CSGCMT | DRJ - 2022 | 177 | 1 | 0 | 2022 | 2022
1014 | DRJ-49 | Drill and Complete | 22 | 4108 | 21.5417 | 477 | 477 | 2022-03-27 | 2022-03-28 | SURF, CSGCMT | DRJ - 2022 | 477 | 1 | 0 | 2022 | 2022
1015 | DRJ-49 | Drill and Complete | 23 | 4433 | 22.5417 | 325 | 325 | 2022-03-28 | 2022-03-29 | SURF, CSGCMT | DRJ - 2022 | 325 | 1 | 0 | 2022 | 2022
1016 | DRJ-49 | Drill and Complete | 24 | 4433 | 23.5417 | 0 | 0 | 2022-03-29 | 2022-03-30 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1017 | DRJ-49 | Drill and Complete | 25 | 4433 | 24.5417 | 0 | 0 | 2022-03-30 | 2022-03-31 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1018 | DRJ-49 | Drill and Complete | 26 | 4433 | 25.5417 | 0 | 0 | 2022-03-31 | 2022-04-01 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1019 | DRJ-49 | Drill and Complete | 27 | 4433 | 26.5417 | 0 | 0 | 2022-04-01 | 2022-04-02 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1020 | DRJ-49 | Drill and Complete | 28 | 4433 | 27.5417 | 0 | 0 | 2022-04-02 | 2022-04-03 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1021 | DRJ-49 | Drill and Complete | 29 | 4940 | 28.5417 | 507 | 507 | 2022-04-03 | 2022-04-04 | DRLGLNR, TB | DRJ - 2022 | 507 | 1 | 0 | 2022 | 2022
1022 | DRJ-49 | Drill and Complete | 30 | 5433 | 29.5417 | 493 | 493 | 2022-04-04 | 2022-04-05 | DRLGLNR, TB | DRJ - 2022 | 493 | 1 | 0 | 2022 | 2022
1023 | DRJ-49 | Drill and Complete | 31 | 5602 | 30.5417 | 169 | 169 | 2022-04-05 | 2022-04-06 | DRLGLNR, TB | DRJ - 2022 | 169 | 1 | 0 | 2022 | 2022
1024 | DRJ-49 | Drill and Complete | 32 | 5862 | 31.5417 | 260 | 260 | 2022-04-06 | 2022-04-07 | DRLGLNR, TB | DRJ - 2022 | 260 | 1 | 0 | 2022 | 2022
1025 | DRJ-49 | Drill and Complete | 33 | 5935 | 32.5417 | 73 | 73 | 2022-04-07 | 2022-04-08 | PRODLNR1, CSGCMT | DRJ - 2022 | 73 | 1 | 0 | 2022 | 2022
1026 | DRJ-49 | Drill and Complete | 34 | 6070 | 33.5417 | 135 | 135 | 2022-04-08 | 2022-04-09 | PRODLNR1, CSGCMT | DRJ - 2022 | 135 | 1 | 0 | 2022 | 2022
1027 | DRJ-49 | Drill and Complete | 35 | 6310 | 34.5417 | 240 | 240 | 2022-04-09 | 2022-04-10 | PRODLNR2, DRILL | DRJ - 2022 | 240 | 1 | 0 | 2022 | 2022
1028 | DRJ-49 | Drill and Complete | 36 | 6310 | 35.0208 | 0 | 0 | 2022-04-10 | 2022-04-10 11:30 | PRODLNR2, DRILL | DRJ - 2022 | 0 | 0.47917 | 0.47917 | 2022 | 2022
1029 | DRJ-50 | Drill and Complete | 1 | 365 | 0.72917 | 133 | 133 | 2022-04-23 06:30 | 2022-04-24 |  | DRJ - 2022 | 365 | 0.72917 | 0 | 2022 | 2022
1030 | DRJ-50 | Drill and Complete | 2 | 845 | 1.7292 | 480 | 480 | 2022-04-24 | 2022-04-25 |  | DRJ - 2022 | 480 | 1 | 0 | 2022 | 2022
1031 | DRJ-50 | Drill and Complete | 3 | 1384 | 2.7292 | 539 | 539 | 2022-04-25 | 2022-04-26 |  | DRJ - 2022 | 539 | 1 | 0 | 2022 | 2022
1032 | DRJ-50 | Drill and Complete | 4 | 1384 | 3.7292 | 0 | 0 | 2022-04-26 | 2022-04-27 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1033 | DRJ-50 | Drill and Complete | 5 | 1435 | 4.7292 | 51 | 51 | 2022-04-27 | 2022-04-28 | SURF, CSGCMT | DRJ - 2022 | 51 | 1 | 0 | 2022 | 2022
1034 | DRJ-50 | Drill and Complete | 6 | 2350 | 5.7292 | 915 | 915 | 2022-04-28 | 2022-04-29 | SURF, CSGCMT | DRJ - 2022 | 915 | 1 | 0 | 2022 | 2022
1035 | DRJ-50 | Drill and Complete | 7 | 2844 | 6.7292 | 484 | 494 | 2022-04-29 | 2022-04-30 | SURF, CSGCMT | DRJ - 2022 | 494 | 1 | 0 | 2022 | 2022
1036 | DRJ-50 | Drill and Complete | 8 | 3050 | 7.7292 | 206 | 206 | 2022-04-30 | 2022-05-01 | SURF, CSGCMT | DRJ - 2022 | 206 | 1 | 0 | 2022 | 2022
1037 | DRJ-50 | Drill and Complete | 9 | 3151 | 8.7292 | 101 | 101 | 2022-05-01 | 2022-05-02 | SURF, CSGCMT | DRJ - 2022 | 101 | 1 | 0 | 2022 | 2022
1038 | DRJ-50 | Drill and Complete | 10 | 3151 | 9.7292 | 0 | 0 | 2022-05-02 | 2022-05-03 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1039 | DRJ-50 | Drill and Complete | 11 | 3151 | 10.7292 | 0 | 0 | 2022-05-03 | 2022-05-04 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1040 | DRJ-50 | Drill and Complete | 12 | 3151 | 11.7292 | 0 | 0 | 2022-05-04 | 2022-05-05 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1041 | DRJ-50 | Drill and Complete | 13 | 3195 | 12.7292 | 44 | 44 | 2022-05-05 | 2022-05-06 | DRLGLNR1, CSGCMT | DRJ - 2022 | 44 | 1 | 1 | 2022 | 2022
1042 | DRJ-50 | Drill and Complete | 14 | 3421 | 13.7292 | 226 | 226 | 2022-05-06 | 2022-05-07 | DRLGLNR1, CSGCMT | DRJ - 2022 | 226 | 1 | 0 | 2022 | 2022
1043 | DRJ-50 | Drill and Complete | 15 | 3642 | 14.7292 | 221 | 221 | 2022-05-07 | 2022-05-08 | DRLGLNR1, CSGCMT | DRJ - 2022 | 221 | 1 | 0 | 2022 | 2022
1044 | DRJ-50 | Drill and Complete | 16 | 3836 | 15.7292 | 194 | 194 | 2022-05-08 | 2022-05-09 | DRLGLNR1, CSGCMT | DRJ - 2022 | 194 | 1 | 0 | 2022 | 2022
1045 | DRJ-50 | Drill and Complete | 17 | 3946 | 16.7292 | 110 | 110 | 2022-05-09 | 2022-05-10 | DRLGLNR1, CSGCMT | DRJ - 2022 | 110 | 1 | 0 | 2022 | 2022
1046 | DRJ-50 | Drill and Complete | 18 | 4167 | 17.7292 | 221 | 221 | 2022-05-10 | 2022-05-11 | DRLGLNR1, CSGCMT | DRJ - 2022 | 221 | 1 | 0 | 2022 | 2022
1047 | DRJ-50 | Drill and Complete | 19 | 4382 | 18.7292 | 215 | 215 | 2022-05-11 | 2022-05-12 | DRLGLNR1, CSGCMT | DRJ - 2022 | 215 | 1 | 0 | 2022 | 2022
1048 | DRJ-50 | Drill and Complete | 20 | 4582 | 19.7292 | 200 | 200 | 2022-05-12 | 2022-05-13 | DRLGLNR1, CSGCMT | DRJ - 2022 | 200 | 1 | 0 | 2022 | 2022
1049 | DRJ-50 | Drill and Complete | 21 | 4705 | 20.7292 | 123 | 123 | 2022-05-13 | 2022-05-14 | DRLGLNR1, CSGCMT | DRJ - 2022 | 123 | 1 | 0 | 2022 | 2022
1050 | DRJ-50 | Drill and Complete | 22 | 4705 | 21.7292 | 0 | 0 | 2022-05-14 | 2022-05-15 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1051 | DRJ-50 | Drill and Complete | 23 | 4992 | 22.7292 | 287 | 287 | 2022-05-15 | 2022-05-16 | DRLGLNR1, CSGCMT | DRJ - 2022 | 287 | 1 | 0 | 2022 | 2022
1052 | DRJ-50 | Drill and Complete | 24 | 5402 | 23.7292 | 410 | 410 | 2022-05-16 | 2022-05-17 | DRLGLNR1, CSGCMT | DRJ - 2022 | 410 | 1 | 0 | 2022 | 2022
1053 | DRJ-50 | Drill and Complete | 25 | 5488 | 24.7292 | 86 | 86 | 2022-05-17 | 2022-05-18 | PRODLNR1, CSGCMT | DRJ - 2022 | 86 | 1 | 0 | 2022 | 2022
1054 | DRJ-50 | Drill and Complete | 26 | 5575 | 25.7292 | 87 | 87 | 2022-05-18 | 2022-05-19 | PRODLNR1, CSGCMT | DRJ - 2022 | 87 | 1 | 0 | 2022 | 2022
1055 | DRJ-50 | Drill and Complete | 27 | 5749 | 26.7292 | 174 | 174 | 2022-05-19 | 2022-05-20 | PRODLNR1, CSGCMT | DRJ - 2022 | 174 | 1 | 0 | 2022 | 2022
1056 | DRJ-50 | Drill and Complete | 28 | 5749 | 27.7292 | 0 | 0 | 2022-05-20 | 2022-05-21 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1057 | DRJ-50 | Drill and Complete | 29 | 5749 | 28.7292 | 0 | 0 | 2022-05-21 | 2022-05-22 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1058 | DRJ-50 | Drill and Complete | 30 | 5749 | 29.2292 | 0 | 0 | 2022-05-22 | 2022-05-22 12:00 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 0.5 | 0.5 | 2022 | 2022
1059 | DRJ-51 | Drill and Complete | 1 | 470 | 0.64583 | 238 | 238 | 2022-06-06 08:30 | 2022-06-07 |  | DRJ - 2022 | 470 | 0.64583 | 0 | 2022 | 2022
1060 | DRJ-51 | Drill and Complete | 2 | 1066 | 1.6458 | 596 | 596 | 2022-06-07 | 2022-06-08 |  | DRJ - 2022 | 596 | 1 | 0 | 2022 | 2022
1061 | DRJ-51 | Drill and Complete | 3 | 1327 | 2.6458 | 261 | 261 | 2022-06-08 | 2022-06-09 |  | DRJ - 2022 | 261 | 1 | 0 | 2022 | 2022
1062 | DRJ-51 | Drill and Complete | 4 | 1405 | 3.6458 | 78 | 78 | 2022-06-09 | 2022-06-10 | SURF, CSGCMT | DRJ - 2022 | 78 | 1 | 0 | 2022 | 2022
1063 | DRJ-51 | Drill and Complete | 5 | 1405 | 4.6458 | 0 | 0 | 2022-06-10 | 2022-06-11 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1064 | DRJ-51 | Drill and Complete | 6 | 1405 | 5.6458 | 0 | 0 | 2022-06-11 | 2022-06-12 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1065 | DRJ-51 | Drill and Complete | 7 | 1405 | 6.6458 | 0 | 0 | 2022-06-12 | 2022-06-13 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1066 | DRJ-51 | Drill and Complete | 8 | 1405 | 7.6458 | 0 | 0 | 2022-06-13 | 2022-06-14 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1067 | DRJ-51 | Drill and Complete | 9 | 1943 | 8.6458 | 538 | 538 | 2022-06-14 | 2022-06-15 | SURF, CSGCMT | DRJ - 2022 | 538 | 1 | 0 | 2022 | 2022
1068 | DRJ-51 | Drill and Complete | 10 | 2444 | 9.6458 | 501 | 501 | 2022-06-15 | 2022-06-16 | SURF, CSGCMT | DRJ - 2022 | 501 | 1 | 0 | 2022 | 2022
1069 | DRJ-51 | Drill and Complete | 11 | 2674 | 10.6458 | 230 | 230 | 2022-06-16 | 2022-06-17 | SURF, CSGCMT | DRJ - 2022 | 230 | 1 | 0 | 2022 | 2022
1070 | DRJ-51 | Drill and Complete | 12 | 3036 | 11.6458 | 362 | 362 | 2022-06-17 | 2022-06-18 | SURF, CSGCMT | DRJ - 2022 | 362 | 1 | 0 | 2022 | 2022
1071 | DRJ-51 | Drill and Complete | 13 | 3212 | 12.6458 | 176 | 176 | 2022-06-18 | 2022-06-19 | SURF, CSGCMT | DRJ - 2022 | 176 | 1 | 0 | 2022 | 2022
1072 | DRJ-51 | Drill and Complete | 14 | 3212 | 13.6458 | 0 | 0 | 2022-06-19 | 2022-06-20 | PRODCSG, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1073 | DRJ-51 | Drill and Complete | 15 | 3212 | 14.6458 | 0 | 0 | 2022-06-20 | 2022-06-21 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1074 | DRJ-51 | Drill and Complete | 16 | 3212 | 15.6458 | 0 | 0 | 2022-06-21 | 2022-06-22 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1075 | DRJ-51 | Drill and Complete | 17 | 3425 | 16.6458 | 213 | 213 | 2022-06-22 | 2022-06-23 | DRLGLNR, TB | DRJ - 2022 | 213 | 1 | 0 | 2022 | 2022
1076 | DRJ-51 | Drill and Complete | 18 | 3825 | 17.6458 | 400 | 400 | 2022-06-23 | 2022-06-24 | DRLGLNR, TB | DRJ - 2022 | 400 | 1 | 0 | 2022 | 2022
1077 | DRJ-51 | Drill and Complete | 19 | 4115 | 18.6458 | 290 | 290 | 2022-06-24 | 2022-06-25 | DRLGLNR, TB | DRJ - 2022 | 290 | 1 | 0 | 2022 | 2022
1078 | DRJ-51 | Drill and Complete | 20 | 4358 | 19.6458 | 243 | 243 | 2022-06-25 | 2022-06-26 | DRLGLNR, TB | DRJ - 2022 | 243 | 1 | 0 | 2022 | 2022
1079 | DRJ-51 | Drill and Complete | 21 | 4894 | 20.6458 | 536 | 536 | 2022-06-26 | 2022-06-27 | DRLGLNR, TB | DRJ - 2022 | 536 | 1 | 0 | 2022 | 2022
1080 | DRJ-51 | Drill and Complete | 22 | 4993 | 21.6458 | 99 | 99 | 2022-06-27 | 2022-06-28 | DRLGLNR, TB | DRJ - 2022 | 99 | 1 | 0 | 2022 | 2022
1081 | DRJ-51 | Drill and Complete | 23 | 4993 | 22.6458 | 0 | 0 | 2022-06-28 | 2022-06-29 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1082 | DRJ-51 | Drill and Complete | 24 | 4993 | 23.6458 | 0 | 0 | 2022-06-29 | 2022-06-30 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1083 | DRJ-51 | Drill and Complete | 25 | 4993 | 24.6458 | 0 | 0 | 2022-06-30 | 2022-07-01 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1084 | DRJ-51 | Drill and Complete | 26 | 4993 | 25.6458 | 0 | 0 | 2022-07-01 | 2022-07-02 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1085 | DRJ-51 | Drill and Complete | 27 | 4993 | 26.6458 | 0 | 0 | 2022-07-02 | 2022-07-03 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1086 | DRJ-51 | Drill and Complete | 28 | 4993 | 27.6458 | 0 | 0 | 2022-07-03 | 2022-07-04 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1087 | DRJ-51 | Drill and Complete | 29 | 4993 | 28.6458 | 0 | 0 | 2022-07-04 | 2022-07-05 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1088 | DRJ-51 | Drill and Complete | 30 | 4993 | 29.4375 | 0 | 0 | 2022-07-05 | 2022-07-05 19:00 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 0.79167 | 0.79167 | 2022 | 2022
1089 | DRJ-52 | Drill and Complete | 1 | 482 | 0.625 | 250 | 250 | 2022-07-08 09:00 | 2022-07-09 | SURF, DRILL | DRJ - 2022 | 482 | 0.625 | 0 | 2022 | 2022
1090 | DRJ-52 | Drill and Complete | 2 | 1286 | 1.625 | 804 | 804 | 2022-07-09 | 2022-07-10 | SURF, DRILL | DRJ - 2022 | 804 | 1 | 0 | 2022 | 2022
1091 | DRJ-52 | Drill and Complete | 3 | 1423 | 2.625 | 137 | 137 | 2022-07-10 | 2022-07-11 | SURF, CSGCMT | DRJ - 2022 | 137 | 1 | 0 | 2022 | 2022
1092 | DRJ-52 | Drill and Complete | 4 | 1423 | 3.625 | 0 | 0 | 2022-07-11 | 2022-07-12 | SURF, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1093 | DRJ-52 | Drill and Complete | 5 | 1815 | 4.625 | 392 | 392 | 2022-07-12 | 2022-07-13 | SURF, CSGCMT | DRJ - 2022 | 392 | 1 | 0 | 2022 | 2022
1094 | DRJ-52 | Drill and Complete | 6 | 2511 | 5.625 | 696 | 696 | 2022-07-13 | 2022-07-14 | SURF, CSGCMT | DRJ - 2022 | 696 | 1 | 0 | 2022 | 2022
1095 | DRJ-52 | Drill and Complete | 7 | 2894 | 6.625 | 383 | 383 | 2022-07-14 | 2022-07-15 | SURF, CSGCMT | DRJ - 2022 | 383 | 1 | 0 | 2022 | 2022
1096 | DRJ-52 | Drill and Complete | 8 | 3200 | 7.625 | 306 | 306 | 2022-07-15 | 2022-07-16 | DRLGLNR1, CSGCMT | DRJ - 2022 | 306 | 1 | 0 | 2022 | 2022
1097 | DRJ-52 | Drill and Complete | 9 | 3200 | 8.625 | 0 | 0 | 2022-07-16 | 2022-07-17 | DRLGLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1098 | DRJ-52 | Drill and Complete | 10 | 3200 | 9.625 | 0 | 0 | 2022-07-17 | 2022-07-18 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1099 | DRJ-52 | Drill and Complete | 11 | 3200 | 10.625 | 0 | 0 | 2022-07-18 | 2022-07-19 | DRLGLNR, TB | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1100 | DRJ-52 | Drill and Complete | 12 | 3774 | 11.625 | 574 | 574 | 2022-07-19 | 2022-07-20 | DRLGLNR, TB | DRJ - 2022 | 574 | 1 | 0 | 2022 | 2022
1101 | DRJ-52 | Drill and Complete | 13 | 4208 | 12.625 | 434 | 434 | 2022-07-20 | 2022-07-21 | DRLGLNR, TB | DRJ - 2022 | 434 | 1 | 0 | 2022 | 2022
1102 | DRJ-52 | Drill and Complete | 14 | 4654 | 13.625 | 446 | 446 | 2022-07-21 | 2022-07-22 | DRLGLNR, TB | DRJ - 2022 | 446 | 1 | 0 | 2022 | 2022
1103 | DRJ-52 | Drill and Complete | 15 | 5000 | 14.625 | 346 | 346 | 2022-07-22 | 2022-07-23 | DRLGLNR, TB | DRJ - 2022 | 346 | 1 | 0 | 2022 | 2022
1104 | DRJ-52 | Drill and Complete | 16 | 5000 | 15.625 | 0 | 0 | 2022-07-23 | 2022-07-24 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1105 | DRJ-52 | Drill and Complete | 17 | 5000 | 16.625 | 0 | 0 | 2022-07-24 | 2022-07-25 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1106 | DRJ-52 | Drill and Complete | 18 | 5215 | 17.625 | 215 | 215 | 2022-07-25 | 2022-07-26 | PRODLNR1, CSGCMT | DRJ - 2022 | 215 | 1 | 0 | 2022 | 2022
1107 | DRJ-52 | Drill and Complete | 19 | 5765 | 18.625 | 550 | 550 | 2022-07-26 | 2022-07-27 | PRODLNR1, CSGCMT | DRJ - 2022 | 550 | 1 | 0 | 2022 | 2022
1108 | DRJ-52 | Drill and Complete | 20 | 5765 | 19.625 | 0 | 0 | 2022-07-27 | 2022-07-28 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 1 | 1 | 2022 | 2022
1109 | DRJ-52 | Drill and Complete | 21 | 5765 | 20.375 | 0 | 0 | 2022-07-28 | 2022-07-28 18:00 | PRODLNR1, CSGCMT | DRJ - 2022 | 0 | 0.75 | 0.75 | 2022 | 2022
1110 | DRJ-53 | Drill and Complete | 1 | 220 | 0.020833 | 220 | 220 | 2024-04-25 23:30 | 2024-04-26 |  | DRJ - 2024 | 220 | 0.020833 | 0 | 2024 | 2024
1111 | DRJ-53 | Drill and Complete | 2 | 641 | 1.0208 | 421 | 421 | 2024-04-26 | 2024-04-27 |  | DRJ - 2024 | 421 | 1 | 0 | 2024 | 2024
1112 | DRJ-53 | Drill and Complete | 3 | 1463 | 2.0208 | 822 | 822 | 2024-04-27 | 2024-04-28 |  | DRJ - 2024 | 822 | 1 | 0 | 2024 | 2024
1113 | DRJ-53 | Drill and Complete | 4 | 1463 | 3.0208 | 0 | 0 | 2024-04-28 | 2024-04-29 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1114 | DRJ-53 | Drill and Complete | 5 | 1463 | 4.0208 | 0 | 0 | 2024-04-29 | 2024-04-30 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1115 | DRJ-53 | Drill and Complete | 6 | 1463 | 5.0208 | 0 | 0 | 2024-04-30 | 2024-05-01 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1116 | DRJ-53 | Drill and Complete | 7 | 1803 | 6.0208 | 302 | 302 | 2024-05-01 | 2024-05-02 | SURF, CSGCMT | DRJ - 2024 | 340 | 1 | 0 | 2024 | 2024
1117 | DRJ-53 | Drill and Complete | 8 | 3026 | 7.0208 | 1223 | 1223 | 2024-05-02 | 2024-05-03 | SURF, CSGCMT | DRJ - 2024 | 1223 | 1 | 0 | 2024 | 2024
1118 | DRJ-53 | Drill and Complete | 9 | 3590 | 8.0208 | 874 | 564 | 2024-05-03 | 2024-05-04 | SURF, CSGCMT | DRJ - 2024 | 564 | 1 | 0 | 2024 | 2024
1119 | DRJ-53 | Drill and Complete | 10 | 3900 | 9.0208 | 310 | 310 | 2024-05-04 | 2024-05-05 | DRLGLNR1, CSGCMT | DRJ - 2024 | 310 | 1 | 0 | 2024 | 2024
1120 | DRJ-53 | Drill and Complete | 11 | 3900 | 10.0208 | 0 | 0 | 2024-05-05 | 2024-05-06 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1121 | DRJ-53 | Drill and Complete | 12 | 3900 | 11.0208 | 0 | 0 | 2024-05-06 | 2024-05-07 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1122 | DRJ-53 | Drill and Complete | 13 | 3900 | 12.0208 | 0 | 0 | 2024-05-07 | 2024-05-08 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1123 | DRJ-53 | Drill and Complete | 14 | 3900 | 13.0208 | 0 | 0 | 2024-05-08 | 2024-05-09 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1124 | DRJ-53 | Drill and Complete | 15 | 4196 | 14.0208 | 296 | 296 | 2024-05-09 | 2024-05-10 | DRLGLNR, TB | DRJ - 2024 | 296 | 1 | 0 | 2024 | 2024
1125 | DRJ-53 | Drill and Complete | 16 | 4561 | 15.0208 | 365 | 365 | 2024-05-10 | 2024-05-11 | DRLGLNR, TB | DRJ - 2024 | 365 | 1 | 0 | 2024 | 2024
1126 | DRJ-53 | Drill and Complete | 17 | 4718 | 16.0208 | 157 | 157 | 2024-05-11 | 2024-05-12 | DRLGLNR, TB | DRJ - 2024 | 157 | 1 | 0 | 2024 | 2024
1127 | DRJ-53 | Drill and Complete | 18 | 5073 | 17.0208 | 355 | 355 | 2024-05-12 | 2024-05-13 | DRLGLNR, TB | DRJ - 2024 | 355 | 1 | 0 | 2024 | 2024
1128 | DRJ-53 | Drill and Complete | 19 | 5527 | 18.0208 | 454 | 454 | 2024-05-13 | 2024-05-14 | DRLGLNR, TB | DRJ - 2024 | 454 | 1 | 0 | 2024 | 2024
1129 | DRJ-53 | Drill and Complete | 20 | 5968 | 19.0208 | 441 | 441 | 2024-05-14 | 2024-05-15 | DRLGLNR, TB | DRJ - 2024 | 441 | 1 | 0 | 2024 | 2024
1130 | DRJ-53 | Drill and Complete | 21 | 6271 | 20.0208 | 303 | 303 | 2024-05-15 | 2024-05-16 | DRLGLNR, TB | DRJ - 2024 | 303 | 1 | 0 | 2024 | 2024
1131 | DRJ-53 | Drill and Complete | 22 | 6500 | 21.0208 | 229 | 229 | 2024-05-16 | 2024-05-17 | DRLGLNR, TB | DRJ - 2024 | 229 | 1 | 0 | 2024 | 2024
1132 | DRJ-53 | Drill and Complete | 23 | 6500 | 22.0208 | 0 | 0 | 2024-05-17 | 2024-05-18 | PRODLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1133 | DRJ-53 | Drill and Complete | 24 | 6500 | 22.7708 | 0 | 0 | 2024-05-18 | 2024-05-19 | PRODLNR1, CSGCMT | DRJ - 2024 | 0 | 0.75 | 0.75 | 2024 | 2024
1134 | DRJ-54 | Drill and Complete | 1 | 0 | 0.020833 |  |  | 2024-05-31 23:30 | 2024-06-01 |  | DRJ - 2024 | 0 | 0.020833 | 0.020833 | 2024 | 2024
1135 | DRJ-54 | Drill and Complete | 2 | 882 | 1.0208 | 650 | 650 | 2024-06-01 | 2024-06-02 |  | DRJ - 2024 | 882 | 1 | 0 | 2024 | 2024
1136 | DRJ-54 | Drill and Complete | 3 | 1381 | 2.0208 | 499 | 499 | 2024-06-02 | 2024-06-03 |  | DRJ - 2024 | 499 | 1 | 0 | 2024 | 2024
1137 | DRJ-54 | Drill and Complete | 4 | 1381 | 3.0208 | 0 | 0 | 2024-06-03 | 2024-06-04 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1138 | DRJ-54 | Drill and Complete | 5 | 1632 | 4.0208 | 251 | 251 | 2024-06-04 | 2024-06-05 | SURF, CSGCMT | DRJ - 2024 | 251 | 1 | 0 | 2024 | 2024
1139 | DRJ-54 | Drill and Complete | 6 | 2648 | 5.0208 | 1016 | 1016 | 2024-06-05 | 2024-06-06 | SURF, CSGCMT | DRJ - 2024 | 1016 | 1 | 0 | 2024 | 2024
1140 | DRJ-54 | Drill and Complete | 7 | 2900 | 6.0208 | 252 | 252 | 2024-06-06 | 2024-06-07 | DRLGLNR1, CSGCMT | DRJ - 2024 | 252 | 1 | 0 | 2024 | 2024
1141 | DRJ-54 | Drill and Complete | 8 | 2900 | 7.0208 | 0 | 0 | 2024-06-07 | 2024-06-08 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1142 | DRJ-54 | Drill and Complete | 9 | 2900 | 8.0208 | 0 | 0 | 2024-06-08 | 2024-06-09 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1143 | DRJ-54 | Drill and Complete | 10 | 2900 | 9.0208 | 0 | 0 | 2024-06-09 | 2024-06-10 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1144 | DRJ-54 | Drill and Complete | 11 | 3643 | 10.0208 | 743 | 743 | 2024-06-10 | 2024-06-11 | DRLGLNR, TB | DRJ - 2024 | 743 | 1 | 0 | 2024 | 2024
1145 | DRJ-54 | Drill and Complete | 12 | 3737 | 11.0208 | 94 | 94 | 2024-06-11 | 2024-06-12 | DRLGLNR, TB | DRJ - 2024 | 94 | 1 | 0 | 2024 | 2024
1146 | DRJ-54 | Drill and Complete | 13 | 3737 | 12.0208 | 0 | 0 | 2024-06-12 | 2024-06-13 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1147 | DRJ-54 | Drill and Complete | 14 | 3737 | 13.0208 | 0 | 0 | 2024-06-13 | 2024-06-14 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1148 | DRJ-54 | Drill and Complete | 15 | 3737 | 14.0208 | 0 | 0 | 2024-06-14 | 2024-06-15 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1149 | DRJ-54 | Drill and Complete | 16 | 3737 | 15.0208 |  |  | 2024-06-15 | 2024-06-16 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1150 | DRJ-54 | Drill and Complete | 17 | 3737 | 16.0208 | 0 | 0 | 2024-06-16 | 2024-06-17 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1151 | DRJ-54 | Drill and Complete | 18 | 3737 | 17.0208 | 0 | 0 | 2024-06-17 | 2024-06-18 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1152 | DRJ-54 | Drill and Complete | 19 | 3737 | 18.0208 | 0 | 0 | 2024-06-18 | 2024-06-19 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1153 | DRJ-54 | Drill and Complete | 20 | 3737 | 19.0208 | 0 | 0 | 2024-06-19 | 2024-06-20 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1154 | DRJ-54 | Drill and Complete | 21 | 2719 | 20.0208 | 11 | 11 | 2024-06-20 | 2024-06-21 | DRLGLNR, TB | DRJ - 2024 | -1018 | 1 | 1 | 2024 | 2024
1155 | DRJ-54 | Drill and Complete | 22 | 2773 | 21.0208 | 54 | 54 | 2024-06-21 | 2024-06-22 | DRLGLNR, TB | DRJ - 2024 | 54 | 1 | 0 | 2024 | 2024
1156 | DRJ-54 | Drill and Complete | 23 | 2972 | 22.0208 | 199 | 199 | 2024-06-22 | 2024-06-23 | DRLGLNR, TB | DRJ - 2024 | 199 | 1 | 0 | 2024 | 2024
1157 | DRJ-54 | Drill and Complete | 24 | 3530 | 23.0208 | 558 | 558 | 2024-06-23 | 2024-06-24 | DRLGLNR, TB | DRJ - 2024 | 558 | 1 | 0 | 2024 | 2024
1158 | DRJ-54 | Drill and Complete | 25 | 3822 | 24.0208 | 292 | 292 | 2024-06-24 | 2024-06-25 | DRLGLNR, TB | DRJ - 2024 | 292 | 1 | 0 | 2024 | 2024
1159 | DRJ-54 | Drill and Complete | 26 | 4389 | 25.0208 | 567 | 567 | 2024-06-25 | 2024-06-26 | DRLGLNR, TB | DRJ - 2024 | 567 | 1 | 0 | 2024 | 2024
1160 | DRJ-54 | Drill and Complete | 27 | 5026 | 26.0208 | 637 | 637 | 2024-06-26 | 2024-06-27 | DRLGLNR, TB | DRJ - 2024 | 637 | 1 | 0 | 2024 | 2024
1161 | DRJ-54 | Drill and Complete | 28 | 5026 | 27.0208 | 0 | 0 | 2024-06-27 | 2024-06-28 | PRODLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1162 | DRJ-54 | Drill and Complete | 29 | 5638 | 28.0208 | 612 | 612 | 2024-06-28 | 2024-06-29 | PRODLNR1, CSGCMT | DRJ - 2024 | 612 | 1 | 0 | 2024 | 2024
1163 | DRJ-54 | Drill and Complete | 30 | 6014 | 29.0208 | 376 | 376 | 2024-06-29 | 2024-06-30 | PRODLNR2, CSGCMT | DRJ - 2024 | 376 | 1 | 0 | 2024 | 2024
1164 | DRJ-54 | Drill and Complete | 31 | 6014 | 29.6875 | 0 | 0 | 2024-06-30 | 2024-07-01 | PRODLNR2, CSGCMT | DRJ - 2024 | 0 | 0.66667 | 0.66667 | 2024 | 2024
1165 | DRJ-55 | Drill and Complete | 1 | 292 | 0.1875 | 60 | 60 | 2024-07-03 19:30 | 2024-07-04 |  | DRJ - 2024 | 292 | 0.1875 | 0 | 2024 | 2024
1166 | DRJ-55 | Drill and Complete | 2 | 1025 | 1.1875 | 733 | 733 | 2024-07-04 | 2024-07-05 |  | DRJ - 2024 | 733 | 1 | 0 | 2024 | 2024
1167 | DRJ-55 | Drill and Complete | 3 | 1360 | 2.1875 | 335 | 335 | 2024-07-05 | 2024-07-06 | SURF, CSGCMT | DRJ - 2024 | 335 | 1 | 0 | 2024 | 2024
1168 | DRJ-55 | Drill and Complete | 4 | 1360 | 3.1875 | 0 | 0 | 2024-07-06 | 2024-07-07 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1169 | DRJ-55 | Drill and Complete | 5 | 1688 | 4.1875 | 328 | 328 | 2024-07-07 | 2024-07-08 | SURF, CSGCMT | DRJ - 2024 | 328 | 1 | 0 | 2024 | 2024
1170 | DRJ-55 | Drill and Complete | 6 | 2670 | 5.1875 | 982 | 982 | 2024-07-08 | 2024-07-09 | SURF, CSGCMT | DRJ - 2024 | 982 | 1 | 0 | 2024 | 2024
1171 | DRJ-55 | Drill and Complete | 7 | 2755 | 6.1875 | 85 | 85 | 2024-07-09 | 2024-07-10 | DRLGLNR1, CSGCMT | DRJ - 2024 | 85 | 1 | 0 | 2024 | 2024
1172 | DRJ-55 | Drill and Complete | 8 | 2755 | 7.1875 | 0 | 0 | 2024-07-10 | 2024-07-11 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1173 | DRJ-55 | Drill and Complete | 9 | 2755 | 8.1875 | 0 | 0 | 2024-07-11 | 2024-07-12 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1174 | DRJ-55 | Drill and Complete | 10 | 2755 | 9.1875 | 0 | 0 | 2024-07-12 | 2024-07-13 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1175 | DRJ-55 | Drill and Complete | 11 | 2755 | 10.1875 | 0 | 0 | 2024-07-13 | 2024-07-14 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1176 | DRJ-55 | Drill and Complete | 12 | 3116 | 11.1875 | 361 | 361 | 2024-07-14 | 2024-07-15 | DRLGLNR, TB | DRJ - 2024 | 361 | 1 | 0 | 2024 | 2024
1177 | DRJ-55 | Drill and Complete | 13 | 3964 | 12.1875 | 848 | 848 | 2024-07-15 | 2024-07-16 | DRLGLNR, TB | DRJ - 2024 | 848 | 1 | 0 | 2024 | 2024
1178 | DRJ-55 | Drill and Complete | 14 | 5058 | 13.1875 | 1094 | 1094 | 2024-07-16 | 2024-07-17 | DRLGLNR, TB | DRJ - 2024 | 1094 | 1 | 0 | 2024 | 2024
1179 | DRJ-55 | Drill and Complete | 15 | 5492 | 14.1875 | 434 | 434 | 2024-07-17 | 2024-07-18 | PRODLNR1, CSGCMT | DRJ - 2024 | 434 | 1 | 0 | 2024 | 2024
1180 | DRJ-55 | Drill and Complete | 16 | 5492 | 15.1875 | 0 | 0 | 2024-07-18 | 2024-07-19 | PRODLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1181 | DRJ-55 | Drill and Complete | 17 | 5668 | 16.1875 | 176 | 176 | 2024-07-19 | 2024-07-20 | PRODLNR1, CSGCMT | DRJ - 2024 | 176 | 1 | 0 | 2024 | 2024
1182 | DRJ-55 | Drill and Complete | 18 | 6000 | 17.1875 | 332 | 332 | 2024-07-20 | 2024-07-21 | PRODLNR2, CSGCMT | DRJ - 2024 | 332 | 1 | 0 | 2024 | 2024
1183 | DRJ-55 | Drill and Complete | 19 | 6000 | 18.1875 | 0 | 0 | 2024-07-21 | 2024-07-22 | PRODLNR2, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1184 | DRJ-55 | Drill and Complete | 20 | 6000 | 18.2292 | 0 | 0 | 2024-07-22 | 2024-07-22 01:00 | PRODLNR2, CSGCMT | DRJ - 2024 | 0 | 0.041667 | 0.041667 | 2024 | 2024
1185 | DRJ-56 | Drill and Complete | 1 | 231 | 0.020833 | 170 | 170 | 2024-08-02 23:30 | 2024-08-03 | SURF, DRILL | DRJ - 2024 | 231 | 0.020833 | 0 | 2024 | 2024
1186 | DRJ-56 | Drill and Complete | 2 | 744 | 1.0208 | 513 | 513 | 2024-08-03 | 2024-08-04 | SURF, DRILL | DRJ - 2024 | 513 | 1 | 0 | 2024 | 2024
1187 | DRJ-56 | Drill and Complete | 3 | 1300 | 2.0208 | 556 | 556 | 2024-08-04 | 2024-08-05 | SURF, DRILL | DRJ - 2024 | 556 | 1 | 0 | 2024 | 2024
1188 | DRJ-56 | Drill and Complete | 4 | 1300 | 3.0208 | 0 | 0 | 2024-08-05 | 2024-08-06 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1189 | DRJ-56 | Drill and Complete | 5 | 1469 | 4.0208 | 213 | 213 | 2024-08-06 | 2024-08-07 | SURF, CSGCMT | DRJ - 2024 | 169 | 1 | 0 | 2024 | 2024
1190 | DRJ-56 | Drill and Complete | 6 | 2724 | 5.0208 | 1255 | 1255 | 2024-08-07 | 2024-08-08 | SURF, CSGCMT | DRJ - 2024 | 1255 | 1 | 0 | 2024 | 2024
1191 | DRJ-56 | Drill and Complete | 7 | 3310 | 6.0208 | 586 | 586 | 2024-08-08 | 2024-08-09 | SURF, CSGCMT | DRJ - 2024 | 586 | 1 | 0 | 2024 | 2024
1192 | DRJ-56 | Drill and Complete | 8 | 3320 | 7.0208 | 10 | 10 | 2024-08-09 | 2024-08-10 | DRLGLNR1, CSGCMT | DRJ - 2024 | 10 | 1 | 1 | 2024 | 2024
1193 | DRJ-56 | Drill and Complete | 9 | 3320 | 8.0208 | 0 | 0 | 2024-08-10 | 2024-08-11 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1194 | DRJ-56 | Drill and Complete | 10 | 3320 | 9.0208 | 0 | 0 | 2024-08-11 | 2024-08-12 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1195 | DRJ-56 | Drill and Complete | 11 | 3320 | 10.0208 | 0 | 0 | 2024-08-12 | 2024-08-13 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1196 | DRJ-56 | Drill and Complete | 12 | 3394 | 11.0208 | 74 | 74 | 2024-08-13 | 2024-08-14 | DRLGLNR, TB | DRJ - 2024 | 74 | 1 | 0 | 2024 | 2024
1197 | DRJ-56 | Drill and Complete | 13 | 3394 | 12.0208 | 0 | 0 | 2024-08-14 | 2024-08-15 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1198 | DRJ-56 | Drill and Complete | 14 | 3394 | 13.0208 | 0 | 0 | 2024-08-15 | 2024-08-16 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1199 | DRJ-56 | Drill and Complete | 15 | 3394 | 14.0208 | 0 | 0 | 2024-08-16 | 2024-08-17 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1200 | DRJ-56 | Drill and Complete | 16 | 3394 | 15.0208 | 0 | 0 | 2024-08-17 | 2024-08-18 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1201 | DRJ-56 | Drill and Complete | 17 | 3394 | 16.0208 | 0 | 0 | 2024-08-18 | 2024-08-19 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1202 | DRJ-56 | Drill and Complete | 18 | 4017 | 17.0208 | 623 | 623 | 2024-08-19 | 2024-08-20 | DRLGLNR, TB | DRJ - 2024 | 623 | 1 | 0 | 2024 | 2024
1203 | DRJ-56 | Drill and Complete | 19 | 4229 | 18.0208 | 212 | 212 | 2024-08-20 | 2024-08-21 | DRLGLNR, TB | DRJ - 2024 | 212 | 1 | 0 | 2024 | 2024
1204 | DRJ-56 | Drill and Complete | 20 | 4597 | 19.0208 | 367 | 367 | 2024-08-21 | 2024-08-22 | DRLGLNR, TB | DRJ - 2024 | 368 | 1 | 0 | 2024 | 2024
1205 | DRJ-56 | Drill and Complete | 21 | 4816 | 20.0208 | 219 | 219 | 2024-08-22 | 2024-08-23 | DRLGLNR, TB | DRJ - 2024 | 219 | 1 | 0 | 2024 | 2024
1206 | DRJ-56 | Drill and Complete | 22 | 4816 | 21.0208 | 0 | 0 | 2024-08-23 | 2024-08-24 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1207 | DRJ-56 | Drill and Complete | 23 | 4816 | 22.0208 | 0 | 0 | 2024-08-24 | 2024-08-25 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1208 | DRJ-56 | Drill and Complete | 24 | 4816 | 23.0208 | 0 | 0 | 2024-08-25 | 2024-08-26 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1209 | DRJ-56 | Drill and Complete | 25 | 4816 | 24.0208 | 0 | 0 | 2024-08-26 | 2024-08-27 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1210 | DRJ-56 | Drill and Complete | 26 | 4816 | 25.0208 | 0 | 0 | 2024-08-27 | 2024-08-28 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1211 | DRJ-56 | Drill and Complete | 27 | 4816 | 26.0208 | 0 | 0 | 2024-08-28 | 2024-08-29 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1212 | DRJ-56 | Drill and Complete | 28 | 4816 | 27.0208 | 0 | 0 | 2024-08-29 | 2024-08-30 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1213 | DRJ-56 | Drill and Complete | 29 | 4816 | 28.0208 | 0 | 0 | 2024-08-30 | 2024-08-31 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1214 | DRJ-56 | Drill and Complete | 30 | 4816 | 29.0208 | 0 | 0 | 2024-08-31 | 2024-09-01 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1215 | DRJ-56 | Drill and Complete | 31 | 4816 | 30.0208 | 0 | 0 | 2024-09-01 | 2024-09-02 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1216 | DRJ-56 | Drill and Complete | 32 | 4816 | 31.0208 | 0 | 0 | 2024-09-02 | 2024-09-03 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1217 | DRJ-56 | Drill and Complete | 33 | 4816 | 32.0208 | 0 | 0 | 2024-09-03 | 2024-09-04 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1218 | DRJ-56 | Drill and Complete | 34 | 4816 | 33.0208 | 0 | 0 | 2024-09-04 | 2024-09-05 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1219 | DRJ-56 | Drill and Complete | 35 | 4816 | 34.0208 | 0 | 0 | 2024-09-05 | 2024-09-06 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1220 | DRJ-56 | Drill and Complete | 36 | 4816 | 35.0208 | 0 | 0 | 2024-09-06 | 2024-09-07 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1221 | DRJ-56 | Drill and Complete | 37 | 3040 | 36.0208 | 10 | 10 | 2024-09-07 | 2024-09-08 | DRLGLNR, TB | DRJ - 2024 | -1776 | 1 | 1 | 2024 | 2024
1222 | DRJ-56 | Drill and Complete | 38 | 3079 | 37.0208 | 39 | 39 | 2024-09-08 | 2024-09-09 | DRLGLNR, TB | DRJ - 2024 | 39 | 1 | 1 | 2024 | 2024
1223 | DRJ-56 | Drill and Complete | 39 | 3162 | 38.0208 | 83 | 83 | 2024-09-09 | 2024-09-10 | DRLGLNR, TB | DRJ - 2024 | 83 | 1 | 0 | 2024 | 2024
1224 | DRJ-56 | Drill and Complete | 40 | 3530 | 39.0208 | 368 | 368 | 2024-09-10 | 2024-09-11 | DRLGLNR, TB | DRJ - 2024 | 368 | 1 | 0 | 2024 | 2024
1225 | DRJ-56 | Drill and Complete | 41 | 3796 | 40.0208 | 266 | 266 | 2024-09-11 | 2024-09-12 | DRLGLNR, TB | DRJ - 2024 | 266 | 1 | 0 | 2024 | 2024
1226 | DRJ-56 | Drill and Complete | 42 | 3814 | 41.0208 | 18 | 18 | 2024-09-12 | 2024-09-13 | PRODLNR1, CSGCMT | DRJ - 2024 | 18 | 1 | 1 | 2024 | 2024
1227 | DRJ-56 | Drill and Complete | 43 | 4380 | 42.0208 | 566 | 566 | 2024-09-13 | 2024-09-14 | PRODLNR1, CSGCMT | DRJ - 2024 | 566 | 1 | 0 | 2024 | 2024
1228 | DRJ-56 | Drill and Complete | 44 | 4983 | 43.0208 | 603 | 603 | 2024-09-14 | 2024-09-15 | PRODLNR1, CSGCMT | DRJ - 2024 | 603 | 1 | 0 | 2024 | 2024
1229 | DRJ-56 | Drill and Complete | 45 | 5592 | 44.0208 | 609 | 609 | 2024-09-15 | 2024-09-16 | PRODLNR1, CSGCMT | DRJ - 2024 | 609 | 1 | 0 | 2024 | 2024
1230 | DRJ-56 | Drill and Complete | 46 | 5655 | 45.0208 | 63 | 63 | 2024-09-16 | 2024-09-17 | PRODLNR1, CSGCMT | DRJ - 2024 | 63 | 1 | 0 | 2024 | 2024
1231 | DRJ-56 | Drill and Complete | 47 | 6095 | 46.0208 | 440 | 440 | 2024-09-17 | 2024-09-18 | PRODLNR1, CSGCMT | DRJ - 2024 | 440 | 1 | 0 | 2024 | 2024
1232 | DRJ-56 | Drill and Complete | 48 | 6500 | 47.0208 | 405 | 405 | 2024-09-18 | 2024-09-19 | PRODLNR1, CSGCMT | DRJ - 2024 | 405 | 1 | 0 | 2024 | 2024
1233 | DRJ-56 | Drill and Complete | 49 | 6500 | 48.0208 | 0 | 0 | 2024-09-19 | 2024-09-20 | PRODLNR2, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1234 | DRJ-56 | Drill and Complete | 50 | 6500 | 49.0208 | 0 | 0 | 2024-09-20 | 2024-09-21 | PRODLNR2, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1235 | DRJ-56 | Drill and Complete | 51 | 6500 | 50.0208 | 0 | 0 | 2024-09-21 | 2024-09-22 | PRODLNR3, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1236 | DRJ-56 | Drill and Complete | 52 | 5464 | 50.3125 | 0 | 0 | 2024-09-22 | 2024-09-22 07:00 | PRODLNR3, CSGCMT | DRJ - 2024 | -1036 | 0.29167 | 0.29167 | 2024 | 2024
1237 | DRJ-57 | Drill and Complete | 1 | 251 | 0.10417 | 19 | 19 | 2024-10-02 21:30 | 2024-10-03 |  | DRJ - 2024 | 251 | 0.10417 | 0 | 2024 | 2024
1238 | DRJ-57 | Drill and Complete | 2 | 484 | 1.1042 | 233 | 233 | 2024-10-03 | 2024-10-04 |  | DRJ - 2024 | 233 | 1 | 0 | 2024 | 2024
1239 | DRJ-57 | Drill and Complete | 3 | 964 | 2.1042 | 480 | 480 | 2024-10-04 | 2024-10-05 |  | DRJ - 2024 | 480 | 1 | 0 | 2024 | 2024
1240 | DRJ-57 | Drill and Complete | 4 | 1430 | 3.1042 | 466 | 466 | 2024-10-05 | 2024-10-06 |  | DRJ - 2024 | 466 | 1 | 0 | 2024 | 2024
1241 | DRJ-57 | Drill and Complete | 5 | 1430 | 4.1042 | 0 | 0 | 2024-10-06 | 2024-10-07 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1242 | DRJ-57 | Drill and Complete | 6 | 1430 | 5.1042 | 0 | 0 | 2024-10-07 | 2024-10-08 | SURF, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1243 | DRJ-57 | Drill and Complete | 7 | 2289 | 6.1042 | 859 | 859 | 2024-10-08 | 2024-10-09 | SURF, CSGCMT | DRJ - 2024 | 859 | 1 | 0 | 2024 | 2024
1244 | DRJ-57 | Drill and Complete | 8 | 3208 | 7.1042 | 919 | 919 | 2024-10-09 | 2024-10-10 | SURF, CSGCMT | DRJ - 2024 | 919 | 1 | 0 | 2024 | 2024
1245 | DRJ-57 | Drill and Complete | 9 | 3230 | 8.1042 | 22 | 22 | 2024-10-10 | 2024-10-11 | DRLGLNR1, CSGCMT | DRJ - 2024 | 22 | 1 | 1 | 2024 | 2024
1246 | DRJ-57 | Drill and Complete | 10 | 3230 | 9.1042 | 0 | 0 | 2024-10-11 | 2024-10-12 | DRLGLNR1, CSGCMT | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1247 | DRJ-57 | Drill and Complete | 11 | 3230 | 10.1042 | 0 | 0 | 2024-10-12 | 2024-10-13 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1248 | DRJ-57 | Drill and Complete | 12 | 3230 | 11.1042 | 0 | 0 | 2024-10-13 | 2024-10-14 | DRLGLNR, TB | DRJ - 2024 | 0 | 1 | 1 | 2024 | 2024
1249 | DRJ-57 | Drill and Complete | 13 | 3370 | 12.1042 | 140 | 140 | 2024-10-14 | 2024-10-15 | DRLGLNR, TB | DRJ - 2024 | 140 | 1 | 0 | 2024 | 2024
1250 | DRJ-57 | Drill and Complete | 14 | 4060 | 13.1042 | 690 | 690 | 2024-10-15 | 2024-10-16 | DRLGLNR, TB | DRJ - 2024 | 690 | 1 | 0 | 2024 | 2024
1251 | DRJ-57 | Drill and Complete | 15 | 4815 | 14.1042 | 755 | 755 | 2024-10-16 | 2024-10-17 | DRLGLNR, TB | DRJ - 2024 | 755 | 1 | 0 | 2024 | 2024
1252 | DRJ-57 | Drill and Complete | 16 | 5289 | 15.1042 | 474 | 474 | 2024-10-17 | 2024-10-18 | DRLGLNR, TB | DRJ - 2024 | 474 | 1 | 0 | 2024 | 2024
1253 | DRJ-57 | Drill and Complete | 17 | 5372 | 16.1042 | 83 | 83 | 2024-10-18 | 2024-10-19 | DRLGLNR, TB | DRJ - 2024 | 83 | 1 | 0 | 2024 | 2024
1254 | DRJ-57 | Drill and Complete | 18 | 5810 | 17.1042 | 438 | 438 | 2024-10-19 | 2024-10-20 | DRLGLNR, TB | DRJ - 2024 | 438 | 1 | 0 | 2024 | 2024
1255 | DRJ-57 | Drill and Complete | 19 | 6000 | 18.1042 | 190 | 190 | 2024-10-20 | 2024-10-21 | PRODLNR1, CSGCMT | DRJ - 2024 | 190 | 1 | 0 | 2024 | 2024
1256 | DRJ-57 | Drill and Complete | 20 | 6000 | 18.8542 | 0 | 0 | 2024-10-21 | 2024-10-21 18:00 | PRODLNR1, CSGCMT | DRJ - 2024 | 0 | 0.75 | 0.75 | 2024 | 2024
1257 | AWI 21-8 | Drill and Complete | 1 | 372 | 0.35417 | 340 | 189 | 2025-07-08 15:30 | 2025-07-09 |  | SLK - 2025 | 372 | 0.35417 | 0 | 2025 | 2025
1258 | AWI 21-8 | Drill and Complete | 2 | 725 | 1.3542 | 378 | 353 | 2025-07-09 | 2025-07-10 |  | SLK - 2025 | 353 | 1 | 0 | 2025 | 2025
1259 | AWI 21-8 | Drill and Complete | 3 | 1096 | 2.3542 | 343 | 343 | 2025-07-10 | 2025-07-11 |  | SLK - 2025 | 371 | 1 | 0 | 2025 | 2025
1260 | AWI 21-8 | Drill and Complete | 4 | 1096 | 3.3542 | 0 | 0 | 2025-07-11 | 2025-07-12 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1261 | AWI 21-8 | Drill and Complete | 5 | 1350 | 4.3542 | 0 | 0 | 2025-07-12 | 2025-07-13 | SURF, CSGCMT | SLK - 2025 | 254 | 1 | 0 | 2025 | 2025
1262 | AWI 21-8 | Drill and Complete | 6 | 1350 | 5.3542 | 0 | 0 | 2025-07-13 | 2025-07-14 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1263 | AWI 21-8 | Drill and Complete | 7 | 1870 | 6.3542 | 565 | 570 | 2025-07-14 | 2025-07-15 | SURF, CSGCMT | SLK - 2025 | 520 | 1 | 0 | 2025 | 2025
1264 | AWI 21-8 | Drill and Complete | 8 | 2925 | 7.3542 | 1017 | 1017 | 2025-07-15 | 2025-07-16 | SURF, CSGCMT | SLK - 2025 | 1055 | 1 | 0 | 2025 | 2025
1265 | AWI 21-8 | Drill and Complete | 9 | 2925 | 8.3542 | 0 | 0 | 2025-07-16 | 2025-07-17 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1266 | AWI 21-8 | Drill and Complete | 10 | 2925 | 9.3542 | 0 | 0 | 2025-07-17 | 2025-07-18 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1267 | AWI 21-8 | Drill and Complete | 11 | 2925 | 10.3542 | 0 | 0 | 2025-07-18 | 2025-07-19 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1268 | AWI 21-8 | Drill and Complete | 12 | 2925 | 11.3542 | 0 | 0 | 2025-07-19 | 2025-07-20 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1269 | AWI 21-8 | Drill and Complete | 13 | 2925 | 12.3542 | 0 | 0 | 2025-07-20 | 2025-07-21 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1270 | AWI 21-8 | Drill and Complete | 14 | 3290 | 13.3542 | 365 | 365 | 2025-07-21 | 2025-07-22 | DRLGLNR, TB | SLK - 2025 | 365 | 1 | 0 | 2025 | 2025
1271 | AWI 21-8 | Drill and Complete | 15 | 4055 | 14.3542 | 765 | 765 | 2025-07-22 | 2025-07-23 | PRODLNR1, CSGCMT | SLK - 2025 | 765 | 1 | 0 | 2025 | 2025
1272 | AWI 21-8 | Drill and Complete | 16 | 4055 | 14.9792 | 0 | 0 | 2025-07-23 | 2025-07-23 15:00 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 0.625 | 0.625 | 2025 | 2025
1273 | AWI 21-7 | Drill and Complete | 1 | 450 | 0.60417 | 415 | 415 | 2025-07-27 09:30 | 2025-07-28 |  | SLK - 2025 | 450 | 0.60417 | 0 | 2025 | 2025
1274 | AWI 21-7 | Drill and Complete | 2 | 883 | 1.6042 | 433 | 433 | 2025-07-28 | 2025-07-29 |  | SLK - 2025 | 433 | 1 | 0 | 2025 | 2025
1275 | AWI 21-7 | Drill and Complete | 3 | 1352 | 2.6042 | 469 | 469 | 2025-07-29 | 2025-07-30 |  | SLK - 2025 | 469 | 1 | 0 | 2025 | 2025
1276 | AWI 21-7 | Drill and Complete | 4 | 1352 | 3.6042 | 0 | 0 | 2025-07-30 | 2025-07-31 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1277 | AWI 21-7 | Drill and Complete | 5 | 1352 | 4.6042 | 0 | 0 | 2025-07-31 | 2025-08-01 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1278 | AWI 21-7 | Drill and Complete | 6 | 1968 | 5.6042 | 616 | 616 | 2025-08-01 | 2025-08-02 | SURF, CSGCMT | SLK - 2025 | 616 | 1 | 0 | 2025 | 2025
1279 | AWI 21-7 | Drill and Complete | 7 | 2922.31 | 6.6042 | 954.31 | 954.31 | 2025-08-02 | 2025-08-03 | SURF, CSGCMT | SLK - 2025 | 954.31 | 1 | 0 | 2025 | 2025
1280 | AWI 21-7 | Drill and Complete | 8 | 2922.31 | 7.6042 | 0 | 0 | 2025-08-03 | 2025-08-04 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1281 | AWI 21-7 | Drill and Complete | 9 | 2922.31 | 8.6042 | 0 | 0 | 2025-08-04 | 2025-08-05 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1282 | AWI 21-7 | Drill and Complete | 10 | 2922.3 | 9.6042 | 2141.3 | 2141.3 | 2025-08-05 | 2025-08-06 | DRLGLNR1, CSGCMT | SLK - 2025 | -0.01 | 1 | 1 | 2025 | 2025
1283 | AWI 21-7 | Drill and Complete | 11 | 2922.3 | 10.6042 | 0 | 0 | 2025-08-06 | 2025-08-07 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1284 | AWI 21-7 | Drill and Complete | 12 | 3193 | 11.6042 | 271 | 271 | 2025-08-07 | 2025-08-08 | DRLGLNR, TB | SLK - 2025 | 270.7 | 1 | 0 | 2025 | 2025
1285 | AWI 21-7 | Drill and Complete | 13 | 4398 | 12.6042 | 1205 | 1205 | 2025-08-08 | 2025-08-09 | DRLGLNR, TB | SLK - 2025 | 1205 | 1 | 0 | 2025 | 2025
1286 | AWI 21-7 | Drill and Complete | 14 | 5060 | 13.6042 | 662 | 662 | 2025-08-09 | 2025-08-10 | DRLGLNR, TB | SLK - 2025 | 662 | 1 | 0 | 2025 | 2025
1287 | AWI 21-7 | Drill and Complete | 15 | 5060 | 14.6042 | 0 | 0 | 2025-08-10 | 2025-08-11 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1288 | AWI 21-7 | Drill and Complete | 16 | 5060 | 15.6042 | 0 | 0 | 2025-08-11 | 2025-08-12 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1289 | AWI 21-7 | Drill and Complete | 17 | 5060 | 16.4167 | 0 | 0 | 2025-08-12 | 2025-08-12 19:30 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 0.8125 | 0.8125 | 2025 | 2025
1290 | AWI 3-9 | Drill and Complete | 1 | 500 | 0.5625 | 270 | 270 | 2025-09-10 10:30 | 2025-09-11 | COND, DRILL | SLK - 2025 | 500 | 0.5625 | 0 | 2025 | 2025
1291 | AWI 3-9 | Drill and Complete | 2 | 1220 | 1.5625 | 720 | 720 | 2025-09-11 | 2025-09-12 | COND, DRILL | SLK - 2025 | 720 | 1 | 0 | 2025 | 2025
1292 | AWI 3-9 | Drill and Complete | 3 | 1665 | 2.5625 | 445 | 445 | 2025-09-12 | 2025-09-13 | COND, DRILL | SLK - 2025 | 445 | 1 | 0 | 2025 | 2025
1293 | AWI 3-9 | Drill and Complete | 4 | 1665 | 3.5625 | 0 | 0 | 2025-09-13 | 2025-09-14 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1294 | AWI 3-9 | Drill and Complete | 5 | 1665 | 4.5625 | 0 | 0 | 2025-09-14 | 2025-09-15 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1295 | AWI 3-9 | Drill and Complete | 6 | 1691 | 5.5625 | 26 | 26 | 2025-09-15 | 2025-09-16 | SURF, CSGCMT | SLK - 2025 | 26 | 1 | 1 | 2025 | 2025
1296 | AWI 3-9 | Drill and Complete | 7 | 2575 | 6.5625 | 884 | 884 | 2025-09-16 | 2025-09-17 | SURF, CSGCMT | SLK - 2025 | 884 | 1 | 0 | 2025 | 2025
1297 | AWI 3-9 | Drill and Complete | 8 | 3654 | 7.5625 | 1079 | 1079 | 2025-09-17 | 2025-09-18 | DRLGLNR1, DRILL | SLK - 2025 | 1079 | 1 | 0 | 2025 | 2025
1298 | AWI 3-9 | Drill and Complete | 9 | 3654 | 8.5625 | 0 | 0 | 2025-09-18 | 2025-09-19 | DRLGLNR1, DRILL | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1299 | AWI 3-9 | Drill and Complete | 10 | 3654 | 9.5625 | 0 | 0 | 2025-09-19 | 2025-09-20 | DRLGLNR1, DRILL | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1300 | AWI 3-9 | Drill and Complete | 11 | 3654 | 10.5625 | 0 | 0 | 2025-09-20 | 2025-09-21 | DRLGLNR1, DRILL | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1301 | AWI 3-9 | Drill and Complete | 12 | 3654 | 11.5625 | 0 | 0 | 2025-09-21 | 2025-09-22 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1302 | AWI 3-9 | Drill and Complete | 13 | 3654 | 12.5625 | 0 | 0 | 2025-09-22 | 2025-09-23 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1303 | AWI 3-9 | Drill and Complete | 14 | 4562 | 13.5625 | 908 | 908 | 2025-09-23 | 2025-09-24 | DRLGLNR, TB | SLK - 2025 | 908 | 1 | 0 | 2025 | 2025
1304 | AWI 3-9 | Drill and Complete | 15 | 5500 | 14.5625 | 938 | 938 | 2025-09-24 | 2025-09-25 | DRLGLNR, TB | SLK - 2025 | 938 | 1 | 0 | 2025 | 2025
1305 | AWI 3-9 | Drill and Complete | 16 | 5500 | 15.5625 | 0 | 0 | 2025-09-25 | 2025-09-26 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1306 | AWI 3-9 | Drill and Complete | 17 | 5500 | 16.5625 | 0 | 0 | 2025-09-26 | 2025-09-27 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1307 | AWI 23-1 | Drill and Complete | 1 | 512 | 0.58333 | 204 | 204 | 2025-10-18 10:00 | 2025-10-19 |  | SLK - 2025 | 512 | 0.58333 | 0 | 2025 | 2025
1308 | HMD-A01 | Drill and Complete | 1 | 356 | 0.5 | 284 | 284 | 2025-10-18 12:00 | 2025-10-19 |  | A_Others | 356 | 0.5 | 0 | 2025 | 2025
1309 | AWI 23-1 | Drill and Complete | 2 | 1370 | 1.5833 | 858 | 858 | 2025-10-19 | 2025-10-20 |  | SLK - 2025 | 1014 | 1.0833 | 0 | 2025 | 2025
1310 | HMD-A01 | Drill and Complete | 2 | 285 | 1.5 | 284 | -71 | 2025-10-19 | 2025-10-20 |  | A_Others | -1085 | -0.083333 | -0.083333 | 2025 | 2025
1311 | HMD-A01 | Drill and Complete | 3 | 427 | 2.5 | 142 | 142 | 2025-10-20 | 2025-10-21 | SURF, CSGCMT | A_Others | 142 | 1 | 0 | 2025 | 2025
1312 | AWI 23-1 | Drill and Complete | 3 | 2095 | 2.5833 | 725 | 725 | 2025-10-20 | 2025-10-21 |  | SLK - 2025 | 1668 | 0.083333 | 0 | 2025 | 2025
1313 | AWI 23-1 | Drill and Complete | 4 | 2095 | 3.5833 | 0 | 0 | 2025-10-21 | 2025-10-22 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1314 | HMD-A01 | Drill and Complete | 4 | 427 | 3.5 | 0 | 0 | 2025-10-21 | 2025-10-22 | SURF, CSGCMT | A_Others | -1668 | -0.083333 | -0.083333 | 2025 | 2025
1315 | AWI 23-1 | Drill and Complete | 5 | 2095 | 4.5833 | 0 | 0 | 2025-10-22 | 2025-10-23 | SURF, CSGCMT | SLK - 2025 | 1668 | 1.0833 | 0 | 2025 | 2025
1316 | HMD-A01 | Drill and Complete | 5 | 427 | 4.5 | 0 | 0 | 2025-10-22 | 2025-10-23 | SURF, CSGCMT | A_Others | -1668 | -0.083333 | -0.083333 | 2025 | 2025
1317 | AWI 23-1 | Drill and Complete | 6 | 2095 | 5.5833 | 0 | 0 | 2025-10-23 | 2025-10-24 | SURF, CSGCMT | SLK - 2025 | 1668 | 1.0833 | 0 | 2025 | 2025
1318 | HMD-A01 | Drill and Complete | 6 | 434 | 5.5 | 7 | 7 | 2025-10-23 | 2025-10-24 | SURF, CSGCMT | A_Others | -1661 | -0.083333 | -0.083333 | 2025 | 2025
1319 | AWI 23-1 | Drill and Complete | 7 | 3008 | 6.5833 | 913 | 913 | 2025-10-24 | 2025-10-25 | SURF, CSGCMT | SLK - 2025 | 2574 | 1.0833 | 0 | 2025 | 2025
1320 | HMD-A01 | Drill and Complete | 7 | 1155 | 6.5 | 668 | 721 | 2025-10-24 | 2025-10-25 | SURF, CSGCMT | A_Others | -1853 | -0.083333 | -0.083333 | 2025 | 2025
1321 | HMD-A01 | Drill and Complete | 8 | 1711 | 7.5 | 556 | 556 | 2025-10-25 | 2025-10-26 | SURF, CSGCMT | A_Others | 556 | 1 | 0 | 2025 | 2025
1322 | AWI 23-1 | Drill and Complete | 8 | 3870 | 7.5833 | 862 | 862 | 2025-10-25 | 2025-10-26 | SURF, CSGCMT | SLK - 2025 | 2159 | 0.083333 | 0 | 2025 | 2025
1323 | HMD-A01 | Drill and Complete | 9 | 1719 | 8.5 | 8 | 8 | 2025-10-26 | 2025-10-27 | INTCSG1, CSGCMT | A_Others | -2151 | 0.91667 | 0.91667 | 2025 | 2025
1324 | AWI 23-1 | Drill and Complete | 9 | 4724 | 8.5833 | 379 | 379 | 2025-10-26 | 2025-10-27 | SURF, CSGCMT | SLK - 2025 | 3005 | 0.083333 | 0 | 2025 | 2025
1325 | HMD-A01 | Drill and Complete | 10 | 1719 | 9.5 | 0 | 0 | 2025-10-27 | 2025-10-28 | INTCSG1, CSGCMT | A_Others | -3005 | 0.91667 | 0.91667 | 2025 | 2025
1326 | AWI 23-1 | Drill and Complete | 10 | 4782 | 9.5833 | 58 | 58 | 2025-10-27 | 2025-10-28 | DRLGLNR1, CSGCMT | SLK - 2025 | 3063 | 0.083333 | 0 | 2025 | 2025
1327 | AWI 23-1 | Drill and Complete | 11 | 4782 | 10.5833 | 0 | 0 | 2025-10-28 | 2025-10-29 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1328 | HMD-A01 | Drill and Complete | 11 | 1719 | 10.5 | 0 | 0 | 2025-10-28 | 2025-10-29 | INTCSG1, CSGCMT | A_Others | -3063 | -0.083333 | -0.083333 | 2025 | 2025
1329 | AWI 23-1 | Drill and Complete | 12 | 4782 | 11.5833 | 0 | 0 | 2025-10-29 | 2025-10-30 | DRLGLNR, TB | SLK - 2025 | 3063 | 1.0833 | 0 | 2025 | 2025
1330 | HMD-A01 | Drill and Complete | 12 | 1719 | 11.5 | 0 | 0 | 2025-10-29 | 2025-10-30 | INTCSG1, CSGCMT | A_Others | -3063 | -0.083333 | -0.083333 | 2025 | 2025
1331 | HMD-A01 | Drill and Complete | 13 | 2628 | 12.5 | 909 | 909 | 2025-10-30 | 2025-10-31 | INTCSG1, CSGCMT | A_Others | 909 | 1 | 0 | 2025 | 2025
1332 | AWI 23-1 | Drill and Complete | 13 | 4782 | 12.5833 | 0 | 0 | 2025-10-30 | 2025-10-31 | DRLGLNR, TB | SLK - 2025 | 2154 | 0.083333 | 0 | 2025 | 2025
1333 | AWI 23-1 | Drill and Complete | 14 | 4782 | 13.5833 | 0 | 0 | 2025-10-31 | 2025-11-01 | DRLGLNR, TB | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1334 | HMD-A01 | Drill and Complete | 14 | 3293 | 13.5 | 696 | 666 | 2025-10-31 | 2025-11-01 | INTCSG1, CSGCMT | A_Others | -1489 | -0.083333 | -0.083333 | 2025 | 2025
1335 | AWI 23-1 | Drill and Complete | 15 | 5920 | 14.5833 | 1138 | 1138 | 2025-11-01 | 2025-11-02 | DRLGLNR, TB | SLK - 2025 | 2627 | 1.0833 | 0 | 2025 | 2025
1336 | HMD-A01 | Drill and Complete | 15 | 3293 | 14.5 | 0 | 0 | 2025-11-01 | 2025-11-02 | PRODCSG, CSGCMT | A_Others | -2627 | -0.083333 | -0.083333 | 2025 | 2025
1337 | HMD-A01 | Drill and Complete | 16 | 3293 | 15.5 | 0 | 0 | 2025-11-02 | 2025-11-03 | PRODCSG, CSGCMT | A_Others | 0 | 1 | 1 | 2025 | 2025
1338 | AWI 23-1 | Drill and Complete | 16 | 7136 | 15.5833 | 1216 | 1216 | 2025-11-02 | 2025-11-03 | DRLGLNR, TB | SLK - 2025 | 3843 | 0.083333 | 0 | 2025 | 2025
1339 | HMD-A01 | Drill and Complete | 17 | 3946 | 16.5 | 653 | 653 | 2025-11-03 | 2025-11-04 | PRODCSG, CSGCMT | A_Others | -3190 | 0.91667 | 0.91667 | 2025 | 2025
1340 | AWI 23-1 | Drill and Complete | 17 | 8390 | 16.5833 | 1254 | 1254 | 2025-11-03 | 2025-11-04 | DRLGLNR, TB | SLK - 2025 | 4444 | 0.083333 | 0 | 2025 | 2025
1341 | HMD-A01 | Drill and Complete | 18 | 4700 | 17.5 | 754 | 754 | 2025-11-04 | 2025-11-05 | PRODCSG, CSGCMT | A_Others | -3690 | 0.91667 | 0.91667 | 2025 | 2025
1342 | AWI 23-1 | Drill and Complete | 18 | 9000 | 17.5833 | 610 | 610 | 2025-11-04 | 2025-11-05 | DRLGLNR, TB | SLK - 2025 | 4300 | 0.083333 | 0 | 2025 | 2025
1343 | HMD-A01 | Drill and Complete | 19 | 4996 | 18.5 | 296 | 296 | 2025-11-05 | 2025-11-06 | PRODLNR1, CSGCMT | A_Others | -4004 | 0.91667 | 0.91667 | 2025 | 2025
1344 | AWI 23-1 | Drill and Complete | 19 | 9000 | 18.5833 |  |  | 2025-11-05 | 2025-11-06 | DRLGLNR, TB | SLK - 2025 | 4004 | 0.083333 | 0 | 2025 | 2025
1345 | HMD-A01 | Drill and Complete | 20 | 4996 | 19.5 | 0 | 0 | 2025-11-06 | 2025-11-07 | PRODLNR1, CSGCMT | A_Others | -4004 | 0.91667 | 0.91667 | 2025 | 2025
1346 | AWI 23-1 | Drill and Complete | 20 | 9000 | 19.5833 |  |  | 2025-11-06 | 2025-11-07 | DRLGLNR, TB | SLK - 2025 | 4004 | 0.083333 | 0 | 2025 | 2025
1347 | HMD-A01 | Drill and Complete | 21 | 5597 | 20.5 | 282 | 601 | 2025-11-07 | 2025-11-08 | PRODLNR1, CSGCMT | A_Others | -3403 | 0.91667 | 0.91667 | 2025 | 2025
1348 | AWI 23-1 | Drill and Complete | 21 | 9000 | 20.4583 |  |  | 2025-11-07 | 2025-11-08 | DRLGLNR, TB | SLK - 2025 | 3403 | -0.041667 | 0 | 2025 | 2025
1349 | HMD-A01 | Drill and Complete | 22 | 5742 | 21.5 | 145 | 145 | 2025-11-08 | 2025-11-09 | PRODLNR1, CSGCMT | A_Others | -3258 | 1.0417 | 1.0417 | 2025 | 2025
1350 | HMD-A01 | Drill and Complete | 23 | 5477 | 22.5 | 0 | 0 | 2025-11-09 | 2025-11-10 | PRODLNR2, CSGCMT | A_Others | -265 | 1 | 1 | 2025 | 2025
1351 | HMD-A01 | Drill and Complete | 24 | 5477 | 22.7083 | 0 | 0 | 2025-11-10 | 2025-11-11 | PRODLNR2, CSGCMT | A_Others | 0 | 0.20833 | 0.20833 | 2025 | 2025
1352 | AWI 23-2 | Drill and Complete | 1 | 378 | 0.27083 | 85 | 85 | 2025-11-11 17:30 | 2025-11-12 | SURF, DRILL | SLK - 2025 | 378 | 0.27083 | 0 | 2025 | 2025
1353 | AWI 23-2 | Drill and Complete | 2 | 1172 | 1.2708 | 794 | 794 | 2025-11-12 | 2025-11-13 | SURF, DRILL | SLK - 2025 | 794 | 1 | 0 | 2025 | 2025
1354 | AWI 23-2 | Drill and Complete | 3 | 2054 | 2.2708 | 882 | 882 | 2025-11-13 | 2025-11-14 | SURF, DRILL | SLK - 2025 | 882 | 1 | 0 | 2025 | 2025
1355 | AWI 23-2 | Drill and Complete | 4 | 2054 | 3.2708 | 0 | 0 | 2025-11-14 | 2025-11-15 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1356 | HMD-A02 | Drill and Complete | 1 | 325 | 0.95833 | 253 | 253 | 2025-11-14 01:00 | 2025-11-15 | SURF, DRILL | A_Others | 325 | 0.95833 | 0 | 2025 | 2025
1357 | AWI 23-2 | Drill and Complete | 5 | 2054 | 4.2708 | 0 | 0 | 2025-11-15 | 2025-11-16 | SURF, CSGCMT | SLK - 2025 | 1729 | 3.3125 | 0 | 2025 | 2025
1358 | HMD-A02 | Drill and Complete | 2 | 426 | 1.9583 | 101 | 101 | 2025-11-15 | 2025-11-16 | SURF, CSGCMT | A_Others | -1628 | -2.3125 | -2.3125 | 2025 | 2025
1359 | AWI 23-2 | Drill and Complete | 6 | 2619 | 5.2708 | 567 | 565 | 2025-11-16 | 2025-11-17 | SURF, CSGCMT | SLK - 2025 | 2193 | 3.3125 | 0 | 2025 | 2025
1360 | HMD-A02 | Drill and Complete | 3 | 426 | 2.9583 | 0 | 0 | 2025-11-16 | 2025-11-17 | SURF, CSGCMT | A_Others | -2193 | -2.3125 | -2.3125 | 2025 | 2025
1361 | HMD-A02 | Drill and Complete | 4 | 476 | 3.9583 | 50 | 50 | 2025-11-17 | 2025-11-18 | SURF, CSGCMT | A_Others | 50 | 1 | 1 | 2025 | 2025
1362 | AWI 23-2 | Drill and Complete | 7 | 3983 | 6.2708 | 1364 | 1364 | 2025-11-17 | 2025-11-18 | SURF, CSGCMT | SLK - 2025 | 3507 | 2.3125 | 0 | 2025 | 2025
1363 | AWI 23-2 | Drill and Complete | 8 | 4610 | 7.2708 | 590 | 590 | 2025-11-18 | 2025-11-19 | SURF, CSGCMT | SLK - 2025 | 627 | 1 | 0 | 2025 | 2025
1364 | HMD-A02 | Drill and Complete | 5 | 776 | 4.9583 | 300 | 300 | 2025-11-18 | 2025-11-19 | SURF, CSGCMT | A_Others | -3834 | -2.3125 | -2.3125 | 2025 | 2025
1365 | AWI 23-2 | Drill and Complete | 9 | 4610 | 8.2708 | 0 | 0 | 2025-11-19 | 2025-11-20 | DRLGLNR1, CSGCMT | SLK - 2025 | 3834 | 3.3125 | 0 | 2025 | 2025
1366 | HMD-A02 | Drill and Complete | 6 | 1644 | 5.9583 | 868 | 868 | 2025-11-19 | 2025-11-20 | SURF, CSGCMT | A_Others | -2966 | -2.3125 | -2.3125 | 2025 | 2025
1367 | AWI 23-2 | Drill and Complete | 10 | 4610 | 9.2708 | 0 | 0 | 2025-11-20 | 2025-11-21 | DRLGLNR1, CSGCMT | SLK - 2025 | 2966 | 3.3125 | 0 | 2025 | 2025
1368 | HMD-A02 | Drill and Complete | 7 | 1787 | 6.9583 | 143 | 143 | 2025-11-20 | 2025-11-21 | INTCSG1, CSGCMT | A_Others | -2823 | -2.3125 | -2.3125 | 2025 | 2025
1369 | AWI 23-2 | Drill and Complete | 11 | 4610 | 10.2708 | 0 | 0 | 2025-11-21 | 2025-11-22 | DRLGLNR1, CSGCMT | SLK - 2025 | 2823 | 3.3125 | 0 | 2025 | 2025
1370 | HMD-A02 | Drill and Complete | 8 | 1787 | 7.9583 | 0 | 0 | 2025-11-21 | 2025-11-22 | INTCSG1, CSGCMT | A_Others | -2823 | -2.3125 | -2.3125 | 2025 | 2025
1371 | HMD-A02 | Drill and Complete | 9 | 1787 | 8.9583 | 0 | 0 | 2025-11-22 | 2025-11-23 | INTCSG1, CSGCMT | A_Others | 0 | 1 | 1 | 2025 | 2025
1372 | AWI 23-2 | Drill and Complete | 12 | 4610 | 11.2708 | 0 | 0 | 2025-11-22 | 2025-11-23 | DRLGLNR1, CSGCMT | SLK - 2025 | 2823 | 2.3125 | 0 | 2025 | 2025
1373 | AWI 23-2 | Drill and Complete | 13 | 5828 | 12.2708 | 1218 | 1218 | 2025-11-23 | 2025-11-24 | DRLGLNR1, CSGCMT | SLK - 2025 | 1218 | 1 | 0 | 2025 | 2025
1374 | HMD-A02 | Drill and Complete | 10 | 1792 | 9.9583 | 5 | 5 | 2025-11-23 | 2025-11-24 | INTCSG1, CSGCMT | A_Others | -4036 | -2.3125 | -2.3125 | 2025 | 2025
1375 | HMD-A02 | Drill and Complete | 11 | 2898 | 10.9583 | 1106 | 1106 | 2025-11-24 | 2025-11-25 | INTCSG1, CSGCMT | A_Others | 1106 | 1 | 0 | 2025 | 2025
1376 | AWI 23-2 | Drill and Complete | 14 | 6500 | 13.2708 | 546 | 546 | 2025-11-24 | 2025-11-25 | DRLGLNR1, CSGCMT | SLK - 2025 | 3602 | 2.3125 | 0 | 2025 | 2025
1377 | AWI 23-2 | Drill and Complete | 15 | 6500 | 14.2708 | 0 | 0 | 2025-11-25 | 2025-11-26 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1378 | HMD-A02 | Drill and Complete | 12 | 2898 | 11.9583 | 0 | 0 | 2025-11-25 | 2025-11-26 | PRODCSG, CSGCMT | A_Others | -3602 | -2.3125 | -2.3125 | 2025 | 2025
1379 | AWI 23-2 | Drill and Complete | 16 | 7107 | 15.2708 | 1210 | 605 | 2025-11-26 | 2025-11-27 | PRODLNR1, CSGCMT | SLK - 2025 | 4209 | 3.3125 | 0 | 2025 | 2025
1380 | HMD-A02 | Drill and Complete | 13 | 2898 | 12.9583 | 0 | 0 | 2025-11-26 | 2025-11-27 | PRODCSG, CSGCMT | A_Others | -4209 | -2.3125 | -2.3125 | 2025 | 2025
1381 | AWI 23-2 | Drill and Complete | 17 | 7588 | 16.2708 | 291 | 291 | 2025-11-27 | 2025-11-28 | PRODLNR1, CSGCMT | SLK - 2025 | 4690 | 3.3125 | 0 | 2025 | 2025
1382 | HMD-A02 | Drill and Complete | 14 | 2898 | 13.9583 | 0 | 0 | 2025-11-27 | 2025-11-28 | PRODCSG, CSGCMT | A_Others | -4690 | -2.3125 | -2.3125 | 2025 | 2025
1383 | AWI 23-2 | Drill and Complete | 18 | 7750 | 17.2708 | 162 | 162 | 2025-11-28 | 2025-11-29 | PRODLNR1, CSGCMT | SLK - 2025 | 4852 | 3.3125 | 0 | 2025 | 2025
1384 | HMD-A02 | Drill and Complete | 15 | 2898 | 14.9583 | 0 | 0 | 2025-11-28 | 2025-11-29 | PRODCSG, CSGCMT | A_Others | -4852 | -2.3125 | -2.3125 | 2025 | 2025
1385 | AWI 23-2 | Drill and Complete | 19 | 8050 | 18.2708 | 300 | 300 | 2025-11-29 | 2025-11-30 | PRODLNR1, CSGCMT | SLK - 2025 | 5152 | 3.3125 | 0 | 2025 | 2025
1386 | HMD-A02 | Drill and Complete | 16 | 3231 | 15.9583 | 333 | 333 | 2025-11-29 | 2025-11-30 | PRODCSG, CSGCMT | A_Others | -4819 | -2.3125 | -2.3125 | 2025 | 2025
1387 | HMD-A02 | Drill and Complete | 17 | 3962 | 16.9583 | 731 | 731 | 2025-11-30 | 2025-12-01 | PRODCSG, CSGCMT | A_Others | 731 | 1 | 0 | 2025 | 2025
1388 | AWI 23-2 | Drill and Complete | 20 | 8050 | 19.2708 | 0 | 0 | 2025-11-30 | 2025-12-01 | PRODLNR1, CSGCMT | SLK - 2025 | 4088 | 2.3125 | 0 | 2025 | 2025
1389 | HMD-A02 | Drill and Complete | 18 | 4600 | 17.9583 | 638 | 638 | 2025-12-01 | 2025-12-02 | PRODLNR1, CSGCMT | A_Others | -3450 | -1.3125 | -1.3125 | 2025 | 2025
1390 | AWI 23-2 | Drill and Complete | 21 | 8050 | 20 | 0 | 0 | 2025-12-01 | 2025-12-01 17:30 | PRODLNR2, CSGCMT | SLK - 2025 | 3450 | 2.0417 | 0 | 2025 | 2025
1391 | HMD-A02 | Drill and Complete | 19 | 4888 | 18.9583 | 576 | 288 | 2025-12-02 | 2025-12-03 | PRODLNR1, CSGCMT | A_Others | -3162 | -1.0417 | -1.0417 | 2025 | 2025
1392 | HMD-A02 | Drill and Complete | 20 | 5543 | 19.9583 | 1310 | 655 | 2025-12-03 | 2025-12-04 | PRODLNR1, CSGCMT | A_Others | 655 | 1 | 0 | 2025 | 2025
1393 | HMD-A02 | Drill and Complete | 21 | 6077 | 20.9583 | 1068 | 534 | 2025-12-04 | 2025-12-05 | PRODLNR1, CSGCMT | A_Others | 534 | 1 | 0 | 2025 | 2025
1394 | HMD-A02 | Drill and Complete | 22 | 6523 | 21.9583 | 892 | 446 | 2025-12-05 | 2025-12-06 | PRODLNR1, CSGCMT | A_Others | 446 | 1 | 0 | 2025 | 2025
1395 | HMD-A02 | Drill and Complete | 23 | 6830 | 22.9583 | 614 | 307 | 2025-12-06 | 2025-12-07 | PRODLNR1, CSGCMT | A_Others | 307 | 1 | 0 | 2025 | 2025
1396 | HMD-A02 | Drill and Complete | 24 | 6932 | 23.9583 | 102 | 102 | 2025-12-07 | 2025-12-08 | PRODLNR1, CSGCMT | A_Others | 102 | 1 | 0 | 2025 | 2025
1397 | HMD-A02 | Drill and Complete | 25 | 7429 | 24.9583 | 497 | 497 | 2025-12-08 | 2025-12-09 | PRODLNR1, CSGCMT | A_Others | 497 | 1 | 0 | 2025 | 2025
1398 | HMD-A02 | Drill and Complete | 26 | 7496 | 25.9583 | 68 | 68 | 2025-12-09 | 2025-12-10 | PRODLNR1, CSGCMT | A_Others | 67 | 1 | 0 | 2025 | 2025
1399 | HMD-A02 | Drill and Complete | 27 | 7496 | 26.9583 | 0 | 0 | 2025-12-10 | 2025-12-11 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2025 | 2025
1400 | HMD-A02 | Drill and Complete | 28 | 7496 | 27.9583 | 0 | 0 | 2025-12-11 | 2025-12-12 | PRODLNR2, CSGCMT | A_Others | 0 | 1 | 1 | 2025 | 2025
1401 | HMD-A02 | Drill and Complete | 29 | 7496 | 28.2083 | 0 | 0 | 2025-12-12 | 2025-12-12 06:00 | PRODLNR2, CSGCMT | A_Others | 0 | 0.25 | 0.25 | 2025 | 2025
1402 | AWI 2-7 ML | Drill and Complete | 1 | 237 | 0.22917 | 20 | 20 | 2025-12-23 18:30 | 2025-12-24 | SURF, DRILL | SLK - 2025 | 237 | 0.22917 | 0 | 2025 | 2025
1403 | AWI 2-7 ML | Drill and Complete | 2 | 1134 | 1.2292 | 481 | 897 | 2025-12-24 | 2025-12-25 | SURF, DRILL | SLK - 2025 | 897 | 1 | 0 | 2025 | 2025
1404 | AWI 2-7 ML | Drill and Complete | 3 | 1146 | 2.2292 | 12 | 12 | 2025-12-25 | 2025-12-26 | SURF, CSGCMT | SLK - 2025 | 12 | 1 | 1 | 2025 | 2025
1405 | AWI 2-7 ML | Drill and Complete | 4 | 1146 | 3.2292 | 0 | 0 | 2025-12-26 | 2025-12-27 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1406 | AWI 2-7 ML | Drill and Complete | 5 | 1217 | 4.2292 | 71 | 71 | 2025-12-27 | 2025-12-28 | SURF, CSGCMT | SLK - 2025 | 71 | 1 | 0 | 2025 | 2025
1407 | AWI 2-7 ML | Drill and Complete | 6 | 2382 | 5.2292 | 1129 | 1129 | 2025-12-28 | 2025-12-29 | SURF, CSGCMT | SLK - 2025 | 1165 | 1 | 0 | 2025 | 2025
1408 | AWI 2-7 ML | Drill and Complete | 7 | 2382 | 6.2292 | 0 | 0 | 2025-12-29 | 2025-12-30 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1409 | AWI 2-7 ML | Drill and Complete | 8 | 2382 | 7.2292 | 0 | 0 | 2025-12-30 | 2025-12-31 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1410 | AWI 2-7 ML | Drill and Complete | 9 | 2382 | 8.2292 | 0 | 0 | 2025-12-31 | 2026-01-01 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2025 | 2025
1411 | AWI 2-7 ML | Drill and Complete | 10 | 2616 | 9.2292 | 482 | 241 | 2026-01-01 | 2026-01-02 | DRLGLNR1, CSGCMT | SLK - 2025 | 234 | 1 | 0 | 2026 | 2026
1412 | AWI 2-7 ML | Drill and Complete | 11 | 2616 | 10.2292 | 0 | 0 | 2026-01-02 | 2026-01-03 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1413 | AWI 2-7 ML | Drill and Complete | 12 | 2898 | 11.2292 | -78 | -78 | 2026-01-03 | 2026-01-04 | DRLGLNR1, CSGCMT | SLK - 2025 | 282 | 1 | 0 | 2026 | 2026
1414 | AWI 2-7 ML | Drill and Complete | 13 | 4322 | 12.2292 | 1424 | 1424 | 2026-01-04 | 2026-01-05 | DRLGLNR1, CSGCMT | SLK - 2025 | 1424 | 1 | 0 | 2026 | 2026
1415 | AWI 2-7 ML | Drill and Complete | 14 | 5497 | 13.2292 | 1175 | 1175 | 2026-01-05 | 2026-01-06 | DRLGLNR1, CSGCMT | SLK - 2025 | 1175 | 1 | 0 | 2026 | 2026
1416 | AWI 2-7 ML | Drill and Complete | 15 | 5497 | 14.2292 | 0 | 0 | 2026-01-06 | 2026-01-07 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1417 | AWI 2-7 ML | Drill and Complete | 16 | 5497 | 15.2292 | 0 | 0 | 2026-01-07 | 2026-01-08 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1418 | AWI 2-7 ML | Drill and Complete | 17 | 5497 | 16.2292 | 0 | 0 | 2026-01-08 | 2026-01-09 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1419 | AWI 2-7 ML | Drill and Complete | 18 | 5497 | 17.2292 | 0 | 0 | 2026-01-09 | 2026-01-10 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1420 | AWI 2-7 ML | Drill and Complete | 19 | 5497 | 18.2292 | 0 | 0 | 2026-01-10 | 2026-01-11 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1421 | AWI 2-7 ML | Drill and Complete | 20 | 5497 | 19.2292 | 0 | 0 | 2026-01-11 | 2026-01-12 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1422 | AWI 2-7 ML | Drill and Complete | 21 | 3569 | 20.2292 | 1272 | 1272 | 2026-01-12 | 2026-01-13 | DRLGLNR1, CSGCMT | SLK - 2025 | -1928 | 1 | 1 | 2026 | 2026
1423 | AWI 2-7 ML | Drill and Complete | 22 | 5074 | 21.2292 | 1505 | 1505 | 2026-01-13 | 2026-01-14 | DRLGLNR1, CSGCMT | SLK - 2025 | 1505 | 1 | 0 | 2026 | 2026
1424 | AWI 2-7 ML | Drill and Complete | 23 | 5474 | 22.2292 | 400 | 400 | 2026-01-14 | 2026-01-15 | PRODLNR1, CSGCMT | SLK - 2025 | 400 | 1 | 0 | 2026 | 2026
1425 | AWI 2-7 ML | Drill and Complete | 24 | 5474 | 23.2292 | 0 | 0 | 2026-01-15 | 2026-01-16 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1426 | AWI 2-7 ML | Drill and Complete | 25 | 5474 | 24.2292 | 0 | 0 | 2026-01-16 | 2026-01-17 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1427 | AWI 2-7 ML | Drill and Complete | 26 | 5474 | 25.2292 | 0 | 0 | 2026-01-17 | 2026-01-18 | PRODLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1428 | AWI 2-7 ML | Drill and Complete | 27 | 5474 | 26 | 0 | 0 | 2026-01-18 | 2026-01-18 18:30 | PROD, CSGCLNOUT | SLK - 2025 | 0 | 0.77083 | 0.77083 | 2026 | 2026
1429 | AWI 2-6 | Drill and Complete | 1 | 771 | 0.625 | 540 | 540 | 2026-01-22 09:00 | 2026-01-23 | COND, DRILL | SLK - 2025 | 771 | 0.625 | 0 | 2026 | 2026
1430 | AWI 2-6 | Drill and Complete | 2 | 1146 | 1.625 | 375 | 375 | 2026-01-23 | 2026-01-24 | SURF, CSGCMT | SLK - 2025 | 375 | 1 | 0 | 2026 | 2026
1431 | AWI 2-6 | Drill and Complete | 3 | 1146 | 2.625 | 0 | 0 | 2026-01-24 | 2026-01-25 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1432 | AWI 2-6 | Drill and Complete | 4 | 2007 | 3.625 | 806 | 856 | 2026-01-25 | 2026-01-26 | SURF, CSGCMT | SLK - 2025 | 861 | 1 | 0 | 2026 | 2026
1433 | AWI 2-6 | Drill and Complete | 5 | 2387 | 4.625 | 380 | 380 | 2026-01-26 | 2026-01-27 | DRLGLNR1, CSGCMT | SLK - 2025 | 380 | 1 | 0 | 2026 | 2026
1434 | AWI 2-6 | Drill and Complete | 6 | 2387 | 5.625 | 0 | 0 | 2026-01-27 | 2026-01-28 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1435 | AWI 2-6 | Drill and Complete | 7 | 2429 | 6.625 | 42 | 42 | 2026-01-28 | 2026-01-29 | DRLGLNR1, CSGCMT | SLK - 2025 | 42 | 1 | 1 | 2026 | 2026
1436 | AWI 2-6 | Drill and Complete | 8 | 4448 | 7.625 | 2019 | 2019 | 2026-01-29 | 2026-01-30 | DRLGLNR1, CSGCMT | SLK - 2025 | 2019 | 1 | 0 | 2026 | 2026
1437 | AWI 2-6 | Drill and Complete | 9 | 4518 | 8.625 | 70 | 70 | 2026-01-30 | 2026-01-31 | PRODLNR1, CSGCMT | SLK - 2025 | 70 | 1 | 0 | 2026 | 2026
1438 | AWI 2-6 | Drill and Complete | 10 | 5320 | 9.625 | 802 | 802 | 2026-01-31 | 2026-02-01 | PRODLNR1, CSGCMT | SLK - 2025 | 802 | 1 | 0 | 2026 | 2026
1439 | AWI 2-6 | Drill and Complete | 11 | 5484 | 10.625 | 164 | 164 | 2026-02-01 | 2026-02-02 | PRODLNR2, CSGCMT | SLK - 2025 | 164 | 1 | 0 | 2026 | 2026
1440 | AWI 2-6 | Drill and Complete | 12 | 5484 | 11.0417 | 0 | 0 | 2026-02-02 | 2026-02-02 10:00 | PRODLNR2, CSGCMT | SLK - 2025 | 0 | 0.41667 | 0.41667 | 2026 | 2026
1441 | AWI 9-10 | Sidetrack | 1 | 0 |  |  |  | 2026-02-22 | 2026-02-23 | DRLGLNR, TB | SLK - 2021 | 0 | 0 | 0 | 2026 | 2026
1442 | AWI 9-11 | Drill and Complete | 1 | 308 | 0.33333 | 84 | 84 | 2026-03-05 16:00 | 2026-03-06 |  | SLK - 2025 | 308 | 0.33333 | 0 | 2026 | 2026
1443 | AWI 9-11 | Drill and Complete | 2 | 1351 | 1.3333 | 1043 | 1043 | 2026-03-06 | 2026-03-07 |  | SLK - 2025 | 1043 | 1 | 0 | 2026 | 2026
1444 | AWI 9-11 | Drill and Complete | 3 | 1950 | 2.3333 | 599 | 599 | 2026-03-07 | 2026-03-08 |  | SLK - 2025 | 599 | 1 | 0 | 2026 | 2026
1445 | AWI 9-11 | Drill and Complete | 4 | 1950 | 3.3333 | 0 | 0 | 2026-03-08 | 2026-03-09 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1446 | AWI 9-11 | Drill and Complete | 5 | 1950 | 4.3333 | 0 | 0 | 2026-03-09 | 2026-03-10 | SURF, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1447 | AWI 9-11 | Drill and Complete | 6 | 2818 | 5.3333 | 868 | 868 | 2026-03-10 | 2026-03-11 | SURF, CSGCMT | SLK - 2025 | 868 | 1 | 0 | 2026 | 2026
1448 | AWI 9-11 | Drill and Complete | 7 | 4351 | 6.3333 | 1441 | 1441 | 2026-03-11 | 2026-03-12 | SURF, CSGCMT | SLK - 2025 | 1533 | 1 | 0 | 2026 | 2026
1449 | AWI 9-11 | Drill and Complete | 8 | 4495 | 7.3333 | 144 | 144 | 2026-03-12 | 2026-03-13 | DRLGLNR1, CSGCMT | SLK - 2025 | 144 | 1 | 0 | 2026 | 2026
1450 | AWI 9-11 | Drill and Complete | 9 | 4495 | 8.3333 | 0 | 0 | 2026-03-13 | 2026-03-14 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1451 | AWI 9-11 | Drill and Complete | 10 | 4495 | 9.3333 | 0 | 0 | 2026-03-14 | 2026-03-15 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1452 | AWI 9-11 | Drill and Complete | 11 | 4495 | 10.3333 | 0 | 0 | 2026-03-15 | 2026-03-16 | DRLGLNR1, CSGCMT | SLK - 2025 | 0 | 1 | 1 | 2026 | 2026
1453 | AWI 9-11 | Drill and Complete | 12 | 4500 | 11.3333 | 5 | 5 | 2026-03-16 | 2026-03-17 | DRLGLNR1, CSGCMT | SLK - 2025 | 5 | 1 | 1 | 2026 | 2026

## Phase.Summary
Phase Summary 2018-2026
# | Well Name | Job Cat | Phase 1 | Phase 2 | Hole/Casing Size | Actual Start Depth (ftKB) | Actual End Depth (ftKB) | Actual Dur (days) | Act Cum Dur (days) | Campaign
1 | AWI 10-4 | Drill and Complete | MOB | RU | 30 |  |  | 26.0208 | 26.0208 | A_Others
2 | AWI 10-4 | Drill and Complete | COND | DRILL | 30 |  |  | 0.083333 | 26.1042 | A_Others
3 | AWI 10-4 | Drill and Complete | INTCSG1 | DRILL | 26 | 182 | 1807 | 7.9792 | 34.0833 | A_Others
4 | AWI 10-4 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1391 | 1807 | 1.7708 | 35.8542 | A_Others
5 | AWI 10-4 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1807 | 3724 | 3.3333 | 39.1875 | A_Others
6 | AWI 10-4 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3724 | 4200 | 2.1458 | 41.3333 | A_Others
7 | AWI 10-4 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 4200 | 4200 | 1 | 42.3333 | A_Others
8 | AWI 10-4 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4200 | 6623 | 3.5938 | 45.9271 | A_Others
9 | AWI 10-4 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 6623 | 6900 | 1.5833 | 47.5104 | A_Others
10 | AWI 10-4 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 6900 | 8343 | 1.8438 | 49.3542 | A_Others
11 | AWI 10-4 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 8343 | 8343 | 0.83333 | 50.1875 | A_Others
12 | AWI 10-4 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 | 8343 | 8862 | 1.0417 | 51.2292 | A_Others
13 | AWI 10-4 | Drill and Complete | PRODLNR3 | CSGCMT | 7 | 8432 | 8862 | 1.0208 | 52.25 | A_Others
14 | AWI 10-4 | Drill and Complete | PROD | DISPL |  | 8862 | 8862 | 0.67708 | 52.9271 | A_Others
15 | AWI 10-4 | Drill and Complete | DEMOB | RD |  | 8862 | 8862 | 0.13542 | 53.0625 | A_Others
16 | AWI 16-8 | Drill and Complete | SURF | DRILL | 26 | 0 | 543 | 2 | 2 | SLK - 2021
17 | AWI 16-8 | Sidetrack | PROD | CSGCLNOUT |  |  |  | 0.29167 | 0.29167 | SLK - 2021
18 | AWI 16-8 | Drill and Complete | SURF | CSGCMT | 20 | 543 | 1140 | 1.8854 | 3.8854 | SLK - 2021
19 | AWI 16-8 | Sidetrack | ABAN | CMTPLUG |  | 0 | 0 | 1.0417 | 1.3333 | SLK - 2021
20 | AWI 16-8 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1140 | 3211 | 9.3646 | 13.25 | SLK - 2021
21 | AWI 16-8 | Sidetrack | PRODLNR | SQUEEZE |  | 0 | 0 | 2.6458 | 3.9792 | SLK - 2021
22 | AWI 16-8 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3211 | 3211 | 4 | 17.25 | SLK - 2021
23 | AWI 16-8 | Sidetrack | PRODOH | DRILL |  | 0 | 4341 | 4.4479 | 8.4271 | SLK - 2021
24 | AWI 16-8 | Drill and Complete | DRLGLNR | TB | 13 3/8 |  |  |  |  | SLK - 2021
25 | AWI 16-8 | Sidetrack | PRODLNR1 | CSGCMT |  | 4341 | 4341 | 0.44792 | 8.875 | SLK - 2021
26 | AWI 16-8 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3211 | 3625 | 3.8646 | 21.1146 | SLK - 2021
27 | AWI 16-8 | Sidetrack | DRLGLNR2 | DRILL |  | 4341 | 5000 | 1.7708 | 10.6458 | SLK - 2021
28 | AWI 16-8 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 3625 | 3625 | 2.5312 | 23.6458 | SLK - 2021
29 | AWI 16-8 | Sidetrack | DRLGLNR2 | CSGCMT |  | 5000 | 5000 | 1.9167 | 12.5625 | SLK - 2021
30 | AWI 16-8 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 3625 | 4114 | 15.3958 | 39.0417 | SLK - 2021
31 | AWI 16-8 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2021
32 | AWI 16-9 | Drill and Complete | SURF | DRILL | 26 | 0 | 1470 | 3.4583 | 3.4583 | SLK - 2021
33 | AWI 16-9 | Drill and Complete | SURF | CSGCMT | 20 | 1470 | 1470 | 1.1667 | 4.625 | SLK - 2021
34 | AWI 16-9 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1470 | 3092 | 3.2917 | 7.9167 | SLK - 2021
35 | AWI 16-9 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3092 | 3344 | 1.1042 | 9.0208 | SLK - 2021
36 | AWI 16-9 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3344 | 3344 | 3.1042 | 12.125 | SLK - 2021
37 | AWI 16-9 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3344 | 5025 | 3.0833 | 15.2083 | SLK - 2021
38 | AWI 16-9 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5025 | 5379 | 1.7812 | 16.9896 | SLK - 2021
39 | AWI 16-9 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5025 | 5379 | 0.63542 | 17.625 | SLK - 2021
40 | AWI 16-9 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 5379 | 5379 | 1.6458 | 19.2708 | SLK - 2021
41 | AWI 2-6 | Drill and Complete | COND | DRILL | 26 | 231 | 1146 | 0.9375 | 0.9375 | SLK - 2025
42 | AWI 2-6 | Drill and Complete | SURF | CSGCMT | 20 | 1146 | 1146 | 2.125 | 3.0625 | SLK - 2025
43 | AWI 2-6 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1151 | 2387 | 0.83333 | 3.8958 | SLK - 2025
44 | AWI 2-6 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2387 | 2387 | 2.7083 | 6.6042 | SLK - 2025
45 | AWI 2-6 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2387 | 4518 | 1.0417 | 7.6458 | SLK - 2025
46 | AWI 2-6 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4518 | 4518 | 1.5833 | 9.2292 | SLK - 2025
47 | AWI 2-6 | Drill and Complete | PRODLNR2 | DRILL | 9-7/8 | 4518 | 5484 | 0.45833 | 9.6875 | SLK - 2025
48 | AWI 2-6 | Drill and Complete | PRODLNR2 | CSGCMT | 7 | 5484 | 5484 | 1.3542 | 11.0417 | SLK - 2025
49 | AWI 2-6 | Drill and Complete | [7 empty] | SLK - 2025
50 | AWI 2-7 ML | Drill and Complete | COND | DRILL | 30 |  |  |  |  | SLK - 2025
51 | AWI 2-7 ML | Drill and Complete | SURF | DRILL | 26 | 0 | 1146 | 1.3542 | 1.3542 | SLK - 2025
52 | AWI 2-7 ML | Drill and Complete | SURF | CSGCMT | 20 | 1146 | 1146 | 2.7917 | 4.1458 | SLK - 2025
53 | AWI 2-7 ML | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1146 | 2382 | 1.0625 | 5.2083 | SLK - 2025
54 | AWI 2-7 ML | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2382 | 2382 | 2.6667 | 7.875 | SLK - 2025
55 | AWI 2-7 ML | Drill and Complete | DRLGLNR | TB | 13 3/8 |  |  |  |  | SLK - 2025
56 | AWI 2-7 ML | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2375 | 5497 | 4.5208 | 12.3958 | SLK - 2025
57 | AWI 2-7 ML | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5497 | 5497 | 2.125 | 14.5208 | SLK - 2025
58 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2025
59 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2025
60 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | EVAL | 8 5/8 | 5497 | 5497 | 0.5625 | 15.0833 | SLK - 2025
61 | AWI 2-7 ML | Drill and Complete | DRLGLNR1 | CSGMILL | 13 3/8 | 5497 | 5497 | 3.6875 | 18.7708 | SLK - 2025
62 | AWI 2-7 ML | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2297 | 5474 | 2.0417 | 20.8125 | SLK - 2025
63 | AWI 2-7 ML | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5474 | 5474 | 1.0417 | 21.8542 | SLK - 2025
64 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2025
65 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2025
66 | AWI 2-7 ML | Drill and Complete | PRODLNR2 | EVAL | 8 5/8 | 5474 | 5474 | 0.5625 | 22.4167 | SLK - 2025
67 | AWI 2-7 ML | Drill and Complete | PROD | CSGCLNOUT | 10 3/4 | 5474 | 5474 | 2.8958 | 25.3125 | SLK - 2025
68 | AWI 21-5 | Drill and Complete | SURF | DRILL | 26 | 0 | 1250 | 2.375 | 2.375 | SLK - 2021
69 | AWI 21-5 | Drill and Complete | SURF | CSGCMT | 20 | 1250 | 1250 | 1.1875 | 3.5625 | SLK - 2021
70 | AWI 21-5 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1250 | 2937 | 2.9792 | 6.5417 | SLK - 2021
71 | AWI 21-5 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2937 | 2937 | 7.4792 | 14.0208 | SLK - 2021
72 | AWI 21-5 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2937 | 2937 | 3.6667 | 17.6875 | SLK - 2021
73 | AWI 21-5 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2937 | 4243 | 2.3542 | 20.0417 | SLK - 2021
74 | AWI 21-5 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4243 | 4685 | 2.0208 | 22.0625 | SLK - 2021
75 | AWI 21-5 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2021
76 | AWI 21-5 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2021
77 | AWI 21-6 | Drill and Complete | SURF | DRILL | 26 | 191 | 1365 | 2.3333 | 2.3333 | SLK - 2021
78 | AWI 21-6 | Drill and Complete | SURF | CSGCMT | 20 | 1365 | 1365 | 1.5 | 3.8333 | SLK - 2021
79 | AWI 21-6 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1365 | 2936 | 2.4375 | 6.2708 | SLK - 2021
80 | AWI 21-6 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2936 | 2936 | 1.7917 | 8.0625 | SLK - 2021
81 | AWI 21-6 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 0 | 2936 | 0.85417 | 8.9167 | SLK - 2021
82 | AWI 21-6 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 0 | 4918 | 2.4375 | 11.3542 | SLK - 2021
83 | AWI 21-6 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4918 | 4918 | 1.1451 | 12.4993 | SLK - 2021
84 | AWI 21-6 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2021
85 | AWI 21-6 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2021
86 | AWI 21-7 | Drill and Complete | COND | DRILL | 26 | 0 | 1352 | 2.2083 | 2.2083 | SLK - 2025
87 | AWI 21-7 | Drill and Complete | SURF | CSGCMT | 20 | 1352 | 1352 | 2.8333 | 5.0417 | SLK - 2025
88 | AWI 21-7 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1352 | 2857 | 1.4167 | 6.4583 | SLK - 2025
89 | AWI 21-7 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2857 | 2922.3 | 3.3542 | 9.8125 | SLK - 2025
90 | AWI 21-7 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2922.3 | 2922.3 | 1.4792 | 11.2917 | SLK - 2025
91 | AWI 21-7 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2922 | 5060 | 1.8333 | 13.125 | SLK - 2025
92 | AWI 21-7 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5060 | 5060 | 3.2917 | 16.4167 | SLK - 2025
93 | AWI 21-8 | Drill and Complete | COND | DRILL | 26 | 0 | 1096 | 2.375 | 2.375 | SLK - 2025
94 | AWI 21-8 | Drill and Complete | SURF | CSGCMT | 20 | 1096 | 1355 | 3.4375 | 5.8125 | SLK - 2025
95 | AWI 21-8 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1355 | 2478 | 1.4167 | 7.2292 | SLK - 2025
96 | AWI 21-8 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2478 | 2925 | 3.5833 | 10.8125 | SLK - 2025
97 | AWI 21-8 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2925 | 2925 | 2.1042 | 12.9167 | SLK - 2025
98 | AWI 21-8 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2925 | 4055 | 1 | 13.9167 | SLK - 2025
99 | AWI 21-8 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4055 | 4055 | 1.0625 | 14.9792 | SLK - 2025
100 | AWI 23-1 | Drill and Complete | COND | DRILL | 30 |  |  |  |  | SLK - 2025
101 | AWI 23-1 | Drill and Complete | SURF | DRILL | 26 | 0 | 2095 | 2.4583 | 2.4583 | SLK - 2025
102 | AWI 23-1 | Drill and Complete | SURF | CSGCMT | 20 | 2095 | 2095 | 1.9792 | 4.4375 | SLK - 2025
103 | AWI 23-1 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 2095 | 4782 | 4.2083 | 8.6458 | SLK - 2025
104 | AWI 23-1 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4782 | 4782 | 2.8125 | 11.4583 | SLK - 2025
105 | AWI 23-1 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 4782 | 4782 | 2.2396 | 13.6979 | SLK - 2025
106 | AWI 23-1 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4782 | 9000 | 3.375 | 17.0729 | SLK - 2025
107 | AWI 23-1 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 |  |  |  |  | SLK - 2025
108 | AWI 23-1 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2025
109 | AWI 23-1 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2025
110 | AWI 23-1 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 |  |  |  |  | SLK - 2025
111 | AWI 23-1 | Drill and Complete | PRODLNR3 | CSGCMT | 7 |  |  |  |  | SLK - 2025
112 | AWI 23-1 | Drill and Complete | PRODLNR1 | EVAL | 12 1/4 | 9000 | 9000 | 2.1979 | 19.2708 | SLK - 2025
113 | AWI 23-1 | Drill and Complete | PRODLNR1 | CSGCMT | 12 1/4 | 0 | 9000 | 1.1875 | 20.4583 | SLK - 2025
114 | AWI 23-1 | Drill and Complete | PRODLNR1 | CSGMILL | 12 1/4 |  |  |  |  | SLK - 2025
115 | AWI 23-1 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 |  |  |  |  | SLK - 2025
116 | AWI 23-1 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 |  |  |  |  | SLK - 2025
117 | AWI 23-1 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2025
118 | AWI 23-1 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2025
119 | AWI 23-2 | Drill and Complete | COND | DRILL | 30 |  |  |  |  | SLK - 2025
120 | AWI 23-2 | Drill and Complete | SURF | DRILL | 26 | 0 | 2054 | 2.4583 | 2.4583 | SLK - 2025
121 | AWI 23-2 | Drill and Complete | SURF | CSGCMT | 20 | 2054 | 2054 | 1.5 | 3.9583 | SLK - 2025
122 | AWI 23-2 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 2054 | 4610 | 3.3125 | 7.2708 | SLK - 2025
123 | AWI 23-2 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4610 | 4610 | 3.4167 | 10.6875 | SLK - 2025
124 | AWI 23-2 | Drill and Complete | DRLGLNR | TB | 13 3/8 |  |  |  |  | SLK - 2025
125 | AWI 23-2 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4610 | 6500 | 2.625 | 13.3125 | SLK - 2025
126 | AWI 23-2 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 6500 | 6500 | 0.625 | 13.9375 | SLK - 2025
127 | AWI 23-2 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 6500 | 8050 | 4.4167 | 18.3542 | SLK - 2025
128 | AWI 23-2 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 8050 | 8050 | 1.6458 | 20 | SLK - 2025
129 | AWI 23-2 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 |  |  |  |  | SLK - 2025
130 | AWI 23-2 | Drill and Complete | PRODLNR3 | CSGCMT | 7 |  |  |  |  | SLK - 2025
131 | AWI 3-9 | Drill and Complete | COND | DRILL | 26 | 0 | 1665 | 2.6667 | 2.6667 | SLK - 2025
132 | AWI 3-9 | Drill and Complete | SURF | CSGCMT | 20 | 1665 | 1665 | 2.8333 | 5.5 | SLK - 2025
133 | AWI 3-9 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1665 | 3654 | 1.9375 | 7.4375 | SLK - 2025
134 | AWI 3-9 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3654 | 3654 | 3.125 | 10.5625 | SLK - 2025
135 | AWI 3-9 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3654 | 3654 | 2.0208 | 12.5833 | SLK - 2025
136 | AWI 3-9 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3654 | 5500 | 1.75 | 14.3333 | SLK - 2025
137 | AWI 3-9 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5500 | 5500 | 2.2292 | 16.5625 | SLK - 2025
138 | AWI 8-3 | Drill and Complete | MOB | RU |  |  |  | 6.2083 | 6.2083 | A_Others
139 | AWI 8-3 | Well Services | MOB | RU | [5 empty] | A_Others
140 | AWI 8-3 | Drill and Complete | COND | DRILL | 36 | 45 | 403 | 6.9583 | 13.1667 | A_Others
141 | AWI 8-3 | Well Services | INTER | INTER | [5 empty] | A_Others
142 | AWI 8-3 | Drill and Complete | COND | CSGCMT | 30 | 403 | 481 | 1.4375 | 14.6042 | A_Others
143 | AWI 8-3 | Drill and Complete | INTCSG1 | DRILL | 26 | 481 | 1530 | 14.1042 | 28.7083 | A_Others
144 | AWI 8-3 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1530 | 1530 | 3.875 | 32.5833 | A_Others
145 | AWI 8-3 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1530 | 4505 | 8.3333 | 40.9167 | A_Others
146 | AWI 8-3 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4505 | 4505 | 4.8333 | 45.75 | A_Others
147 | AWI 8-3 | Drill and Complete | PRODCSG | DRILL | 12 1/4 | 4505 | 7383 | 13.7708 | 59.5208 | A_Others
148 | AWI 8-3 | Drill and Complete | PRODLNR1 | CSGCMT | 9 5/8 | 7383 | 7383 | 0.95833 | 60.4792 | A_Others
149 | AWI 8-3 | Drill and Complete | PRODLNR2 | DRILL | 8 1/2 | 7383 | 7950 | 3.0208 | 63.5 | A_Others
150 | AWI 8-3 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 7950 | 7950 | 3.75 | 67.25 | A_Others
151 | AWI 8-3 | Drill and Complete | PRODLNR2 | CSGCMT | 7 | 7950 | 7950 | 1.2083 | 68.4583 | A_Others
152 | AWI 8-3 | Drill and Complete | DEMOB | RD | 7 | 7950 | 7950 | 0.54167 | 69 | A_Others
153 | AWI 9-10 | Drill and Complete | SURF | DRILL | 26 | 0 | 1750 | 2.4792 | 2.4792 | SLK - 2021
154 | AWI 9-10 | Sidetrack | DRLGLNR1 | CSGMILL | 13 3/8 |  |  | 13.2708 | 13.2708 | SLK - 2021
155 | AWI 9-10 | Drill and Complete | SURF | CSGCMT | 20 | 1750 | 1750 | 2.1354 | 4.6146 | SLK - 2021
156 | AWI 9-10 | Sidetrack | PRODLNR1 | DRILL | 12 1/4 |  |  |  |  | SLK - 2021
157 | AWI 9-10 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1750 | 4554 | 3.6562 | 8.2708 | SLK - 2021
158 | AWI 9-10 | Sidetrack | PRODLNR1 | CSGCMT | 10 3/4 |  |  |  |  | SLK - 2021
159 | AWI 9-10 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4554 | 4554 | 2.8958 | 11.1667 | SLK - 2021
160 | AWI 9-10 | Sidetrack | PRODLNR2 | DRILL | 9 7/8 |  |  |  |  | SLK - 2021
161 | AWI 9-10 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 4554 | 4554 | 1.7083 | 12.875 | SLK - 2021
162 | AWI 9-10 | Sidetrack | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | SLK - 2021
163 | AWI 9-10 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4554 | 7532 | 3.3958 | 16.2708 | SLK - 2021
164 | AWI 9-10 | Sidetrack | PRODLNR2 | DRILL | 7 7/8 |  |  |  |  | SLK - 2021
165 | AWI 9-10 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 7532 | 7532 | 0.72917 | 17 | SLK - 2021
166 | AWI 9-10 | Sidetrack | PRODLNR3 | CSGCMT | 7 |  |  |  |  | SLK - 2021
167 | AWI 9-10 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 7532 | 8919 | 2.8438 | 19.8438 | SLK - 2021
168 | AWI 9-10 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 8919 | 8919 | 2.1979 | 22.0417 | SLK - 2021
169 | AWI 9-11 | Drill and Complete | COND | DRILL | 26 | 0 | 1950 | 2.1042 | 2.1042 | SLK - 2025
170 | AWI 9-11 | Drill and Complete | SURF | CSGCMT | 20 | 1950 | 1955 | 2.625 | 4.7292 | SLK - 2025
171 | AWI 9-11 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1955 | 4495 | 1.7708 | 6.5 | SLK - 2025
172 | AWI 9-11 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4495 | 4495 | 4.8125 | 11.3125 | SLK - 2025
173 | AWI 9-11 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4495 | 7343 | 5.5417 | 16.8542 | SLK - 2025
174 | AWI 9-11 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 7343 | 7343 | 1.7708 | 18.625 | SLK - 2025
175 | AWI 9-11 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 7343 | 9000 | 1.6667 | 20.2917 | SLK - 2025
176 | AWI 9-11 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 9000 | 9000 | 2.0417 | 22.3333 | SLK - 2025
177 | AWI 9-11 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 |  |  |  |  | SLK - 2025
178 | AWI 9-11 | Drill and Complete | PRODLNR3 | CSGCMT | 7 |  |  |  |  | SLK - 2025
179 | DRJ-16 | Drill and Complete | MOB | RU |  |  |  | 9.3125 | 9.3125 | A_Others
180 | DRJ-16 | Well Services | MOB | RU | [5 empty] | A_Others
181 | DRJ-16 | Drill and Complete | COND | CSGCMT | 30 |  |  | 0.125 | 9.4375 | A_Others
182 | DRJ-16 | Well Services | INTER | INTER | [5 empty] | A_Others
183 | DRJ-16 | Drill and Complete | INTCSG1 | DRILL | 26 | 32 | 1456 | 4.2917 | 13.7292 | A_Others
184 | DRJ-16 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1456 | 1456 | 3.8125 | 17.5417 | A_Others
185 | DRJ-16 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1427 | 3940 | 9.8333 | 27.375 | A_Others
186 | DRJ-16 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3940 | 3940 | 4.2292 | 31.6042 | A_Others
187 | DRJ-16 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3934 | 4704 | 3.0625 | 34.6667 | A_Others
188 | DRJ-16 | Drill and Complete | PRODLNR1 | EVAL | 12 1/4 | 4704 | 4704 | 1.1667 | 35.8333 | A_Others
189 | DRJ-16 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4650 | 6367 | 7.375 | 43.2083 | A_Others
190 | DRJ-16 | Drill and Complete | PRODLNR1 | CSGCMT | 9 5/8 | 6367 | 6367 | 1.7917 | 45 | A_Others
191 | DRJ-37 | Drill and Complete | MOB | MOVEON | 30 |  |  | 11 | 11 | A_Others
192 | DRJ-37 | Well Services | MOB | MOVEON | [5 empty] | A_Others
193 | DRJ-37 | Well Services | MOB | RU |  |  |  | 3.9583 | 3.9583 | A_Others
194 | DRJ-37 | Well Services | MOB | RU |  |  |  | 4.6667 | 4.6667 | A_Others
195 | DRJ-37 | Drill and Complete | MOB | RU | 30 |  |  | 10.2917 | 21.2917 | A_Others
196 | DRJ-37 | Well Services | PROD | CSGCLNOUT | [5 empty] | A_Others
197 | DRJ-37 | Well Services | PROD | CSGCLNOUT |  |  |  | 1.2083 | 5.1667 | A_Others
198 | DRJ-37 | Well Services | PROD | CSGCLNOUT |  |  |  | 3.75 | 8.4167 | A_Others
199 | DRJ-37 | Drill and Complete | COND | CSGCMT | 30 |  |  | 0.625 | 21.9167 | A_Others
200 | DRJ-37 | Well Services | DEMOB | RD |  |  |  | 1.7917 | 10.2083 | A_Others
201 | DRJ-37 | Drill and Complete | INTCSG1 | DRILL | 26 | 182 | 1516 | 1.2708 | 23.1875 | A_Others
202 | DRJ-37 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1516 | 1516 | 1.375 | 24.5625 | A_Others
203 | DRJ-37 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1516 | 3696.9999 | 3.625 | 28.1875 | A_Others
204 | DRJ-37 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3696.9999 | 3696.9999 | 1.7083 | 29.8958 | A_Others
205 | DRJ-37 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3696.9999 | 3696.9999 | 1.0208 | 30.9167 | A_Others
206 | DRJ-37 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3696.9999 | 6989 | 8.1875 | 39.1042 | A_Others
207 | DRJ-37 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 6989 | 6989 | 1.1875 | 40.2917 | A_Others
208 | DRJ-37 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 6989 | 7898.0005 | 4.0833 | 44.375 | A_Others
209 | DRJ-37 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 7898.0005 | 7898.0005 | 0.875 | 45.25 | A_Others
210 | DRJ-38RD | Drill and Complete | MOB | RU | 30 |  |  | 4.8125 | 4.8125 | DRJ - 2022
211 | DRJ-38RD | Well Services | MOB | RU |  |  |  | 8.4167 | 8.4167 | DRJ - 2022
212 | DRJ-38RD | Sidetrack | ABAN | CSGMILL | 13 3/8 | 0 | 1986 | 12.1354 | 12.1354 | DRJ - 2022
213 | DRJ-38RD | Drill and Complete | COND | CSGCMT | 30 |  |  | 0.1875 | 5 | DRJ - 2022
214 | DRJ-38RD | Well Services | PROD | CSGCLNOUT |  |  |  | 0.58333 | 9 | DRJ - 2022
215 | DRJ-38RD | Sidetrack | DRLGLNR1 | DRILL | 12 1/4 | 1986 | 4525 | 4.7812 | 16.9167 | DRJ - 2022
216 | DRJ-38RD | Drill and Complete | INTCSG1 | DRILL | 26 | 174 | 1890.0001 | 3.5417 | 8.5417 | DRJ - 2022
217 | DRJ-38RD | Sidetrack | DRLGLNR1 | CSGCMT | 10 3/4 | 4525 | 4525 | 3.1979 | 20.1146 | DRJ - 2022
218 | DRJ-38RD | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1890.0001 | 2000.0001 | 3.0625 | 11.6042 | DRJ - 2022
219 | DRJ-38RD | Sidetrack | PRODLNR1 | DRILL | 9 7/8 | 4525 | 6748 | 9 | 29.1146 | DRJ - 2022
220 | DRJ-38RD | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 2000.0001 | 4611.0002 | 5.5417 | 17.1458 | DRJ - 2022
221 | DRJ-38RD | Sidetrack | PRODLNR1 | CSGMILL | 8 5/8 | 6748 | 6748 | 0.89583 | 30.0104 | DRJ - 2022
222 | DRJ-38RD | Drill and Complete | DRLGLNR1 | EVAL | 17 1/2 | 4611.0002 | 4611.0002 | 0.041667 | 17.1875 | DRJ - 2022
223 | DRJ-38RD | Sidetrack | PRODLNR2 | DRILL | 7 7/8 |  |  |  |  | DRJ - 2022
224 | DRJ-38RD | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 4611.0002 | 4611.0002 | 0.14583 | 17.3333 | DRJ - 2022
225 | DRJ-38RD | Sidetrack | PRODLNR2 | CSGCMT | 7 |  |  |  |  | DRJ - 2022
226 | DRJ-38RD | Drill and Complete | DRLGLNR1 | EVAL | 17 1/2 | 4611.0002 | 4611.0002 | 0.41667 | 17.75 | DRJ - 2022
227 | DRJ-38RD | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4611.0002 | 4650.0002 | 2.7292 | 20.4792 | DRJ - 2022
228 | DRJ-38RD | Drill and Complete | DRLGLNR | TB | 13 3/8 | 4650.0002 | 4650.0002 | 1.0625 | 21.5417 | DRJ - 2022
229 | DRJ-38RD | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4650.0002 | 5701 | 6.2708 | 27.8125 | DRJ - 2022
230 | DRJ-38RD | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5701 | 5774.9999 | 0.6875 | 28.5 | DRJ - 2022
231 | DRJ-38RD | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5774.9999 | 7673.9999 | 5.5417 | 34.0417 | DRJ - 2022
232 | DRJ-38RD | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 7673.9999 | 7898.0005 | 0.70833 | 34.75 | DRJ - 2022
233 | DRJ-38RD | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 | 7898.0005 | 8224.0003 | 0.97917 | 35.7292 | DRJ - 2022
234 | DRJ-38RD | Drill and Complete | PRODLNR3 | CSGCMT | 7 | 8224.0003 | 8250.0003 | 0.6875 | 36.4167 | DRJ - 2022
235 | DRJ-44 | Drill and Complete | SURF | DRILL | 26 | 180 | 1398 | 4.6667 | 4.6667 | DRJ - 2019
236 | DRJ-44 | Drill and Complete | SURF | CSGCMT | 20 | 1398 | 1398 | 2.5625 | 7.2292 | DRJ - 2019
237 | DRJ-44 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1408 | 3187 | 9.7917 | 17.0208 | DRJ - 2019
238 | DRJ-44 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3187 | 3230 | 5.3125 | 22.3333 | DRJ - 2019
239 | DRJ-44 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3230 | 3230 | 2.6042 | 24.9375 | DRJ - 2019
240 | DRJ-44 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3230 | 5703 | 9.1875 | 34.125 | DRJ - 2019
241 | DRJ-44 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5703 | 5860 | 1.9167 | 36.0417 | DRJ - 2019
242 | DRJ-45 | Drill and Complete | SURF | DRILL | 26 | 200 | 1378 | 7.0625 | 7.0625 | DRJ - 2019
243 | DRJ-45 | Drill and Complete | SURF | CSGCMT | 20 | 1378 | 1500 | 11.7604 | 18.8229 | DRJ - 2019
244 | DRJ-45 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1500 | 2514 | 20.1562 | 38.9792 | DRJ - 2019
245 | DRJ-45 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2514 | 2514 | 6.3333 | 45.3125 | DRJ - 2019
246 | DRJ-45 | Drill and Complete | DRLGLNR | TB | 10 3/4 | 1959 | 3446 | 11.2917 | 56.6042 | DRJ - 2019
247 | DRJ-45 | Drill and Complete | PRODLNR1 | DRILL | 9 7/8 | 3446 | 5977 | 8.9583 | 65.5625 | DRJ - 2019
248 | DRJ-45 | Drill and Complete | PRODLNR1 | CSGCMT | 9 7/8 | 5977 | 5977 | 14.9167 | 80.4792 | DRJ - 2019
249 | DRJ-46 | Drill and Complete | SURF | DRILL | 26 | 215 | 1620 | 13.9792 | 13.9792 | DRJ - 2019
250 | DRJ-46 | Drill and Complete | SURF | CSGCMT | 20 | 1620 | 1620 | 5.6042 | 19.5833 | DRJ - 2019
251 | DRJ-46 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1620 | 3550 | 10.8958 | 30.4792 | DRJ - 2019
252 | DRJ-46 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3550 | 3550 | 7.2292 | 37.7083 | DRJ - 2019
253 | DRJ-46 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3550 | 3550 | 2.9896 | 40.6979 | DRJ - 2019
254 | DRJ-46 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3550 | 5836 | 5.3646 | 46.0625 | DRJ - 2019
255 | DRJ-46 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5836 | 5836 | 1.0208 | 47.0833 | DRJ - 2019
256 | DRJ-47 | Drill and Complete | SURF | DRILL | 26 | 213 | 1620 | 12.25 | 12.25 | DRJ - 2019
257 | DRJ-47 | Drill and Complete | SURF | CSGCMT | 20 | 1620 | 1620 | 6.5417 | 18.7917 | DRJ - 2019
258 | DRJ-47 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1620 | 3200 | 3.4583 | 22.25 | DRJ - 2019
259 | DRJ-47 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3200 | 3200 | 1.6667 | 23.9167 | DRJ - 2019
260 | DRJ-47 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3200 | 3200 | 1.0417 | 24.9583 | DRJ - 2019
261 | DRJ-47 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3200 | 5902 | 6.3125 | 31.2708 | DRJ - 2019
262 | DRJ-47 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5902 | 5902 | 4.5625 | 35.8333 | DRJ - 2019
263 | DRJ-48 | Drill and Complete | SURF | DRILL | 26 | 174 | 1422 | 4.0625 | 4.0625 | DRJ - 2019
264 | DRJ-48 | Drill and Complete | SURF | CSGCMT | 20 | 1422 | 1422 | 3.0417 | 7.1042 | DRJ - 2019
265 | DRJ-48 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1422 | 3350 | 4.4792 | 11.5833 | DRJ - 2019
266 | DRJ-48 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3350 | 3350 | 2.1458 | 13.7292 | DRJ - 2019
267 | DRJ-48 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3350 | 1121 | 2.1875 | 15.9167 | DRJ - 2019
268 | DRJ-48 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 1121 | 4949 | 4.6042 | 20.5208 | DRJ - 2019
269 | DRJ-48 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4949 | 4949 | 0.91667 | 21.4375 | DRJ - 2019
270 | DRJ-48 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 4949 | 4949 | 4.0625 | 25.5 | DRJ - 2019
271 | DRJ-48 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 | 4949 | 5399.5 | 3.375 | 28.875 | DRJ - 2019
272 | DRJ-49 | Drill and Complete | SURF | DRILL | 26 | 232 | 1952 | 13.2083 | 13.2083 | DRJ - 2022
273 | DRJ-49 | Drill and Complete | SURF | CSGCMT | 20 | 1952 | 1952 | 2.9688 | 16.1771 | DRJ - 2022
274 | DRJ-49 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1952 | 4433 | 6.5104 | 22.6875 | DRJ - 2022
275 | DRJ-49 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 4433 | 4433 | 2.0938 | 24.7812 | DRJ - 2022
276 | DRJ-49 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 4433 | 4433 | 2.8646 | 27.6458 | DRJ - 2022
277 | DRJ-49 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 4433 | 5935 | 4.5312 | 32.1771 | DRJ - 2022
278 | DRJ-49 | Drill and Complete | PRODLNR1 | CSGCMT | 12 1/4 | 5935 | 5935 | 1.1667 | 33.3437 | DRJ - 2022
279 | DRJ-49 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5935 | 6310 | 1.6667 | 35.0104 | DRJ - 2022
280 | DRJ-49 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | DRJ - 2022
281 | DRJ-50 | Drill and Complete | SURF | DRILL | 26 | 0 | 1384 | 2.6771 | 2.6771 | DRJ - 2022
282 | DRJ-50 | Drill and Complete | SURF | CSGCMT | 20 | 1384 | 1384 | 1.5521 | 4.2292 | DRJ - 2022
283 | DRJ-50 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1384 | 3151 | 4.7292 | 8.9583 | DRJ - 2022
284 | DRJ-50 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3151 | 3151 | 1.7292 | 10.6875 | DRJ - 2022
285 | DRJ-50 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3151 | 3151 | 1.9167 | 12.6042 | DRJ - 2022
286 | DRJ-50 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3151 | 5488 | 11.7708 | 24.375 | DRJ - 2022
287 | DRJ-50 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5488 | 5488 | 0.72917 | 25.1042 | DRJ - 2022
288 | DRJ-50 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5488 | 5749 | 4.125 | 29.2292 | DRJ - 2022
289 | DRJ-50 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | DRJ - 2022
290 | DRJ-51 | Drill and Complete | SURF | DRILL | 26 | 232 | 1405 | 3.2292 | 3.2292 | DRJ - 2022
291 | DRJ-51 | Drill and Complete | SURF | CSGCMT | 20 | 1405 | 1405 | 3.9583 | 7.1875 | DRJ - 2022
292 | DRJ-51 | Drill and Complete | PRODCSG | DRILL | 17 1/2 | 1405 | 3212 | 5.5521 | 12.7396 | DRJ - 2022
293 | DRJ-51 | Drill and Complete | PRODCSG | CSGCMT | 13 3/8 | 3212 | 3212 | 1.6146 | 14.3542 | DRJ - 2022
294 | DRJ-51 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3212 | 3212 | 0.875 | 15.2292 | DRJ - 2022
295 | DRJ-51 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3212 | 4993 | 12.2917 | 27.5208 | DRJ - 2022
296 | DRJ-51 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4993 | 4993 | 1.9167 | 29.4375 | DRJ - 2022
297 | DRJ-52 | Drill and Complete | SURF | DRILL | 26 | 0 | 1423 | 2.1667 | 2.1667 | DRJ - 2022
298 | DRJ-52 | Drill and Complete | SURF | CSGCMT | 20 | 1423 | 1423 | 1.25 | 3.4167 | DRJ - 2022
299 | DRJ-52 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1423 | 3200 | 4.0625 | 7.4792 | DRJ - 2022
300 | DRJ-52 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3200 | 3200 | 1.75 | 9.2292 | DRJ - 2022
301 | DRJ-52 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3200 | 3200 | 0.71875 | 9.9479 | DRJ - 2022
302 | DRJ-52 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3200 | 5000 | 4.75 | 14.6979 | DRJ - 2022
303 | DRJ-52 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5000 | 5000 | 0.59375 | 15.2917 | DRJ - 2022
304 | DRJ-52 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5000 | 5765 | 3.8021 | 19.0938 | DRJ - 2022
305 | DRJ-52 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 5765 | 5765 | 1.2812 | 20.375 | DRJ - 2022
306 | DRJ-53 | Drill and Complete | SURF | DRILL | 26 | 0 | 1463 | 2.125 | 2.125 | DRJ - 2024
307 | DRJ-53 | Drill and Complete | SURF | CSGCMT | 20 | 1463 | 1463 | 3.625 | 5.75 | DRJ - 2024
308 | DRJ-53 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1473 | 3590 | 3.2292 | 8.9792 | DRJ - 2024
309 | DRJ-53 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3590 | 3900 | 2.375 | 11.3542 | DRJ - 2024
310 | DRJ-53 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3900 | 3900 | 2.0625 | 13.4167 | DRJ - 2024
311 | DRJ-53 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3900 | 6500 | 7.8958 | 21.3125 | DRJ - 2024
312 | DRJ-53 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 6500 | 6500 | 1.4583 | 22.7708 | DRJ - 2024
313 | DRJ-54 | Drill and Complete | SURF | DRILL | 26 | 0 | 882 | 1.875 | 1.875 | DRJ - 2024
314 | DRJ-54 | Drill and Complete | SURF | CSGCMT | 20 | 882 | 1381 | 1.9896 | 3.8646 | DRJ - 2024
315 | DRJ-54 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1381 | 2900 | 1.7812 | 5.6458 | DRJ - 2024
316 | DRJ-54 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2900 | 2900 | 2.375 | 8.0208 | DRJ - 2024
317 | DRJ-54 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2900 | 2900 | 1.5 | 9.5208 | DRJ - 2024
318 | DRJ-54 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 |  |  |  |  | DRJ - 2024
319 | DRJ-54 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 |  |  |  |  | DRJ - 2024
320 | DRJ-54 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2900 | 5026 | 16.8333 | 26.3542 | DRJ - 2024
321 | DRJ-54 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5026 | 5026 | 0.875 | 27.2292 | DRJ - 2024
322 | DRJ-54 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5026 | 5638 | 1.7188 | 28.9479 | DRJ - 2024
323 | DRJ-54 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 5638 | 6014 | 0.73958 | 29.6875 | DRJ - 2024
324 | DRJ-55 | Drill and Complete | SURF | DRILL | 26 | 232 | 1360 | 1.8125 | 1.8125 | DRJ - 2024
325 | DRJ-55 | Drill and Complete | SURF | CSGCMT | 20 | 1360 | 1360 | 1.9375 | 3.75 | DRJ - 2024
326 | DRJ-55 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1360 | 2755 | 1.8333 | 5.5833 | DRJ - 2024
327 | DRJ-55 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2755 | 2755 | 3.5417 | 9.125 | DRJ - 2024
328 | DRJ-55 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2755 | 2755 | 1.75 | 10.875 | DRJ - 2024
329 | DRJ-55 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2755 | 5492 | 3.1458 | 14.0208 | DRJ - 2024
330 | DRJ-55 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5058 | 5492 | 1.7083 | 15.7292 | DRJ - 2024
331 | DRJ-55 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5492 | 6000 | 1.125 | 16.8542 | DRJ - 2024
332 | DRJ-55 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 6000 | 6000 | 1.375 | 18.2292 | DRJ - 2024
333 | DRJ-56 | Drill and Complete | SURF | DRILL | 26 | 61 | 1300 | 1.6458 | 1.6458 | DRJ - 2024
334 | DRJ-56 | Drill and Complete | SURF | CSGCMT | 20 | 1300 | 1300 | 2.25 | 3.8958 | DRJ - 2024
335 | DRJ-56 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1300 | 3320 | 2.5625 | 6.4583 | DRJ - 2024
336 | DRJ-56 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3320 | 3320 | 1.7292 | 8.1875 | DRJ - 2024
337 | DRJ-56 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3320 | 3320 | 2.3125 | 10.5 | DRJ - 2024
338 | DRJ-56 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3320 | 4816 | 16.3542 | 26.8542 | DRJ - 2024
339 | DRJ-56 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4816 | 4816 | 4.3542 | 31.2083 | DRJ - 2024
340 | DRJ-56 | Drill and Complete | DRLGLNR1 | CSGMILL | 13 3/8 | 4816 | 3079 | 6.6458 | 37.8542 | DRJ - 2024
341 | DRJ-56 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3079 | 3530 | 1.9583 | 39.8125 | DRJ - 2024
342 | DRJ-56 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 3530 | 3796 | 1.1667 | 40.9792 | DRJ - 2024
343 | DRJ-56 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 3796 | 6500 | 5.9583 | 46.9375 | DRJ - 2024
344 | DRJ-56 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 6500 | 6500 | 1.4167 | 48.3542 | DRJ - 2024
345 | DRJ-56 | Drill and Complete | PRODLNR3 | DRILL | 7 7/8 | 167 | 5464 | 0.77083 | 49.125 | DRJ - 2024
346 | DRJ-56 | Drill and Complete | PRODLNR3 | CSGCMT | 7 | 5464 | 5464 | 1.1875 | 50.3125 | DRJ - 2024
347 | DRJ-57 | Drill and Complete | COND | DRILL | 26 | 0 | 1430 | 2.6042 | 2.6042 | DRJ - 2024
348 | DRJ-57 | Drill and Complete | SURF | CSGCMT | 20 | 1430 | 1435 | 2.8125 | 5.4167 | DRJ - 2024
349 | DRJ-57 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1435 | 3230 | 1.7708 | 7.1875 | DRJ - 2024
350 | DRJ-57 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3230 | 3230 | 2.1458 | 9.3333 | DRJ - 2024
351 | DRJ-57 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3230 | 3230 | 2.5625 | 11.8958 | DRJ - 2024
352 | DRJ-57 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3230 | 5810 | 5.4792 | 17.375 | DRJ - 2024
353 | DRJ-57 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5810 | 6000 | 1.4792 | 18.8542 | DRJ - 2024
354 | HMD-A01 | Drill and Complete | PILOTOH | DRILL | 8 1/2 | 72 | 427 | 0.60417 | 0.60417 | A_Others
355 | HMD-A01 | Drill and Complete | PILOTOH | CMTPLUG | 8 1/2 | 427 | 427 | 0.33333 | 0.9375 | A_Others
356 | HMD-A01 | Drill and Complete | SURF | DRILL | 26 | 72 | 427 | 0.97917 | 1.9167 | A_Others
357 | HMD-A01 | Drill and Complete | SURF | CSGCMT | 20 | 427 | 427 | 3.5417 | 5.4583 | A_Others
358 | HMD-A01 | Drill and Complete | INTCSG1 | DRILL | 17 1/2 | 427 | 1719 | 2.0625 | 7.5208 | A_Others
359 | HMD-A01 | Drill and Complete | INTCSG1 | CSGCMT | 13 3/8 | 1719 | 1724 | 4.3125 | 11.8333 | A_Others
360 | HMD-A01 | Drill and Complete | PRODCSG | DRILL | 12 1/4 | 1724 | 3293 | 1.2708 | 13.1042 | A_Others
361 | HMD-A01 | Drill and Complete | PRODCSG | CSGCMT | 10 3/4 | 3293 | 3293 | 2.5417 | 15.6458 | A_Others
362 | HMD-A01 | Drill and Complete | PRODLNR1 | DRILL | 9 7/8 | 3293 | 4996 | 2.3542 | 18 | A_Others
363 | HMD-A01 | Drill and Complete | PRODLNR1 | CSGCMT | 8 5/8 | 4996 | 4996 | 1.5625 | 19.5625 | A_Others
364 | HMD-A01 | Drill and Complete | PRODLNR2 | DRILL | 7 7/8 | 4996 | 5477 | 1.75 | 21.3125 | A_Others
365 | HMD-A01 | Drill and Complete | PRODLNR2 | CSGCMT | 7 | 5477 | 5477 | 1.4167 | 22.7292 | A_Others
366 | HMD-A01 | Drill and Complete | PRODLNR3 | DRILL | 6 7/8 |  |  |  |  | A_Others
367 | HMD-A01 | Drill and Complete | PRODLNR3 | CSGCMT | 4 1/2 |  |  |  |  | A_Others
368 | HMD-A02 | Drill and Complete | SURF | DRILL | 26 | 72 | 426 | 1.3542 | 1.3542 | A_Others
369 | HMD-A02 | Drill and Complete | SURF | CSGCMT | 20 | 426 | 431 | 2.5208 | 3.875 | A_Others
370 | HMD-A02 | Drill and Complete | INTCSG1 | DRILL | 17 1/2 | 431 | 1787 | 2.2292 | 6.1042 | A_Others
371 | HMD-A02 | Drill and Complete | INTCSG1 | CSGCMT | 13 3/8 | 1787 | 1792 | 3.8542 | 9.9583 | A_Others
372 | HMD-A02 | Drill and Complete | PRODCSG | DRILL | 12 1/4 | 1792 | 2898 | 1 | 10.9583 | A_Others
373 | HMD-A02 | Drill and Complete | PRODCSG | CSGCMT | 10 3/4 | 2898 | 2898 | 4.7708 | 15.7292 | A_Others
374 | HMD-A02 | Drill and Complete | PRODLNR1 | DRILL | 9 7/8 | 2898 | 4600 | 2.0208 | 17.75 | A_Others
375 | HMD-A02 | Drill and Complete | PRODLNR1 | CSGCMT | 8 5/8 | 4600 | 4600 | 0.91667 | 18.6667 | A_Others
376 | HMD-A02 | Drill and Complete | PRODLNR2 | DRILL | 7 7/8 | 4600 | 7496 | 6.5833 | 25.25 | A_Others
377 | HMD-A02 | Drill and Complete | PRODLNR2 | CSGCMT | 7 | 7496 | 7496 | 3.0417 | 28.2917 | A_Others
378 | HMD-A02 | Drill and Complete | PRODLNR3 | DRILL | 6 7/8 |  |  |  |  | A_Others
379 | HMD-A02 | Drill and Complete | PRODLNR3 | CSGCMT | 4 1/2 |  |  |  |  | A_Others
380 | MBA-6 | Drill and Complete | COND | DRILL | 36 | 187 | 0 |  | 0 | WW - 2018
381 | MBA-6 | Drill and Complete | INTCSG1 | DRILL | 26 | 187 | 1070 | 3.8333 | 3.8333 | WW - 2018
382 | MBA-6 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1070 | 1070 | 2.5 | 6.3333 | WW - 2018
383 | MBA-6 | Drill and Complete | DRLGLNR1 | DRILL | 17.5 | 1070 | 2581 | 5.3958 | 11.7292 | WW - 2018
384 | MBA-6 | Drill and Complete | DRLGLNR1 | CSGCMT | 13.375 | 2581 | 2581 | 5.2292 | 16.9583 | WW - 2018
385 | MBA-6 | Drill and Complete | DRLGLNR | TB | 13.375 | 2581 | 2581 | 2.2292 | 19.1875 | WW - 2018
386 | MBA-6 | Drill and Complete | PRODLNR1 | DRILL | 12.25 | 2581 | 4716 | 4.75 | 23.9375 | WW - 2018
387 | MBA-6 | Drill and Complete | PRODLNR1 | CSGCMT | 10.75 | 4716 | 4716 | 1.4167 | 25.3542 | WW - 2018
388 | MBA-6 | Drill and Complete | PRODLNR2 | DRILL | 9.875 | 4716 | 5732 | 2.2917 | 27.6458 | WW - 2018
389 | MBA-6 | Drill and Complete | PRODLNR2 | CSGCMT | 8.625 | 5732 | 5732 | 1.25 | 28.8958 | WW - 2018
390 | MBA-7 | Drill and Complete | COND | DRILL | 36 |  |  |  |  | WW - 2018
391 | MBA-7 | Drill and Complete | INTCSG1 | DRILL | 26 | 187 | 1115 | 5.0833 | 5.0833 | WW - 2018
392 | MBA-7 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1115 | 1115 | 2.4688 | 7.5521 | WW - 2018
393 | MBA-7 | Drill and Complete | DRLGLNR1 | DRILL | 17.5 | 1115 | 2540 | 4.0938 | 11.6458 | WW - 2018
394 | MBA-7 | Drill and Complete | DRLGLNR1 | CSGCMT | 13.375 | 2540 | 2540 | 2.1875 | 13.8333 | WW - 2018
395 | MBA-7 | Drill and Complete | DRLGLNR | TB | 13.375 | 2540 | 2540 | 2.1458 | 15.9792 | WW - 2018
396 | MBA-7 | Drill and Complete | PRODLNR1 | DRILL | 12.25 | 2540 | 3629 | 2.3958 | 18.375 | WW - 2018
397 | MBA-7 | Drill and Complete | PRODLNR1 | CSGCMT | 10.75 | 3629 | 3629 | 1.625 | 20 | WW - 2018
398 | MBA-7 | Drill and Complete | PRODLNR2 | DRILL | 9.875 | 3629 | 4938 | 4.8958 | 24.8958 | WW - 2018
399 | MBA-7 | Drill and Complete | PRODLNR2 | CSGCMT | 8.625 | 4938 | 4965 | 2.6875 | 27.5833 | WW - 2018
400 | MBD-7 | Drill and Complete | COND | DRILL | 36 |  |  |  |  | WW - 2018
401 | MBD-7 | Drill and Complete | INTCSG1 | DRILL | 26 | 186 | 1032 | 3.3542 | 3.3542 | WW - 2018
402 | MBD-7 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1032 | 1032 | 2.2188 | 5.5729 | WW - 2018
403 | MBD-7 | Drill and Complete | DRLGLNR1 | DRILL | 17.5 | 1032 | 2310 | 3.6979 | 9.2708 | WW - 2018
404 | MBD-7 | Drill and Complete | DRLGLNR1 | CSGCMT | 13.375 | 2310 | 2310 | 1.6458 | 10.9167 | WW - 2018
405 | MBD-7 | Drill and Complete | DRLGLNR | TB | 13.375 | 2310 | 2310 | 2.875 | 13.7917 | WW - 2018
406 | MBD-7 | Drill and Complete | PRODLNR1 | DRILL | 12.25 | 2310 | 4997 | 16.3021 | 30.0938 | WW - 2018
407 | MBD-7 | Drill and Complete | PRODLNR1 | CSGCMT | 10.75 | 4997 | 4997 | 9.6771 | 39.7708 | WW - 2018
408 | MBD-8 | Drill and Complete | COND | DRILL | 36 | 187 | 0 | 0.14583 | 0.14583 | WW - 2018
409 | MBD-8 | Sidetrack | ABAN | CSGCLNOUT | 10.75 |  |  | 0.75 | 0.75 | WW - 2018
410 | MBD-8 | Drill and Complete | INTCSG1 | DRILL | 26 | 187 | 1032 | 2.7083 | 2.8542 | WW - 2018
411 | MBD-8 | Sidetrack | ABAN | CMTPLUG | 10.75 |  |  |  |  | WW - 2018
412 | MBD-8 | Drill and Complete | INTCSG1 | CSGCMT | 20 | 1032 | 1032 | 3.375 | 6.2292 | WW - 2018
413 | MBD-8 | Sidetrack | ABAN | CSGPULL | 10.75 |  |  | 0.9375 | 1.6875 | WW - 2018
414 | MBD-8 | Drill and Complete | DRLGLNR1 | DRILL | 17.5 | 1032 | 2222 | 3.0625 | 9.2917 | WW - 2018
415 | MBD-8 | Sidetrack | ABAN | MECHPLUG | 10.75 | 0 | 2010 | 5.9375 | 7.625 | WW - 2018
416 | MBD-8 | Drill and Complete | DRLGLNR1 | CSGCMT | 13.375 | 2222 | 2222 | 1.8125 | 11.1042 | WW - 2018
417 | MBD-8 | Sidetrack | PRODLNR1 | DRILL | 12.25 | 2010 | 3100 | 2.4792 | 10.1042 | WW - 2018
418 | MBD-8 | Drill and Complete | DRLGLNR | TB | 13.375 | 2222 | 2222 | 2.75 | 13.8542 | WW - 2018
419 | MBD-8 | Sidetrack | PRODLNR1 | CSGCMT | 10.75 | 3100 | 2927 | 2.6667 | 12.7708 | WW - 2018
420 | MBD-8 | Drill and Complete | PRODLNR1 | DRILL | 10.75 | 2222 | 4083 | 31.4792 | 45.3333 | WW - 2018
421 | MBD-8 | Sidetrack | PRODLNR2 | DRILL | 9.875 | 3100 | 4140 | 15.4583 | 28.2292 | WW - 2018
422 | MBD-8 | Drill and Complete | PRODLNR1 | CSGCMT | 10.75 | 4083 | 4083 | 5.4167 | 50.75 | WW - 2018
423 | MBD-8 | Sidetrack | PRODLNR2 | CSGCMT | 8.625 |  |  |  |  | WW - 2018
424 | MBD-8 | Drill and Complete | PRODLNR2 | DRILL | 8.625 |  |  |  |  | WW - 2018
425 | MBD-8 | Drill and Complete | PRODLNR2 | CSGCMT | 8.625 |  |  |  |  | WW - 2018
426 | MBD-8 | Drill and Complete | PRODLNR3 | DRILL | 7 |  |  |  |  | WW - 2018
427 | MBD-8 | Drill and Complete | PRODLNR3 | CSGCMT | 7 |  |  |  |  | WW - 2018
428 | MBE-6 | Drill and Complete | SURF | DRILL | 26 | 190 | 1246 | 2.4375 | 2.4375 | WW - 2021
429 | MBE-6 | Drill and Complete | SURF | CSGCMT | 20 | 1246 | 1246 | 2.6875 | 5.125 | WW - 2021
430 | MBE-6 | Drill and Complete | INTCSG1 | DRILL | 17 1/2 | 1246 | 2860 | 3.8333 | 8.9583 | WW - 2021
431 | MBE-6 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2860 | 2860 | 2.0625 | 11.0208 | WW - 2021
432 | MBE-6 | Drill and Complete | PROD | TB | 13 3/8 | 2860 | 2860 | 1.5833 | 12.6042 | WW - 2021
433 | MBE-6 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2860 | 4500 | 1.7917 | 14.3958 | WW - 2021
434 | MBE-6 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4500 | 4500 | 0.83333 | 15.2292 | WW - 2021
435 | MBE-7 | Drill and Complete | SURF | DRILL | 26 | 228 | 1265 | 2.2812 | 2.2812 | WW - 2021
436 | MBE-7 | Drill and Complete | SURF | CSGCMT | 20 | 1265 | 1265 | 2.125 | 4.4062 | WW - 2021
437 | MBE-7 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1265 | 2746 | 1.8438 | 6.25 | WW - 2021
438 | MBE-7 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2746 | 2746 | 3.3958 | 9.6458 | WW - 2021
439 | MBE-7 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2746 | 2746 | 2.8333 | 12.4792 | WW - 2021
440 | MBE-7 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2746 | 5128 | 2.2917 | 14.7708 | WW - 2021
441 | MBE-7 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 5128 | 5128 | 3.3229 | 18.0937 | WW - 2021
442 | MBE-7 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 5128 | 7065 | 3.1042 | 21.1979 | WW - 2021
443 | MBE-7 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 | 7065 | 7065 | 1.6562 | 22.8542 | WW - 2021
444 | MBE-7 | Drill and Complete | PRODLNR3 | CSGCMT | 7 | 7065 | 7065 | 1.25 | 24.1042 | WW - 2021
445 | MBI-1 | Drill and Complete | SURF | DRILL | 26 | 227 | 449 | 1.3958 | 1.3958 | WW - 2021
446 | MBI-1 | Drill and Complete | SURF | CSGCMT | 20 | 449 | 1030 | 1.8542 | 3.25 | WW - 2021
447 | MBI-1 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1030 | 2260 | 1.7604 | 5.0104 | WW - 2021
448 | MBI-1 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 2260 | 2260 | 1.5521 | 6.5625 | WW - 2021
449 | MBI-1 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 2260 | 2260 | 1.3958 | 7.9583 | WW - 2021
450 | MBI-1 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 2260 | 4325 | 1.8438 | 9.8021 | WW - 2021
451 | MBI-1 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4325 | 4325 | 1.1146 | 10.9167 | WW - 2021
452 | WWA-8 | Drill and Complete | SURF | DRILL | 26 | 0 | 1274 | 3.4167 | 3.4167 | WW - 2021
453 | WWA-8 | Drill and Complete | SURF | CSGCMT | 20 | 1274 | 1274 | 2.4375 | 5.8542 | WW - 2021
454 | WWA-8 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1274 | 3087 | 2.2188 | 8.0729 | WW - 2021
455 | WWA-8 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3087 | 3087 | 2.9271 | 11 | WW - 2021
456 | WWA-8 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3087 | 3087 | 3.3125 | 14.3125 | WW - 2021
457 | WWA-8 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3087 | 2924 | 23.6458 | 37.9583 | WW - 2021
458 | WWA-8 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 2924 | 3700 | 0.875 | 38.8333 | WW - 2021
459 | WWA-8 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 3700 | 4287 | 7.3958 | 46.2292 | WW - 2021
460 | WWA-8 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | WW - 2021
461 | WWA-9 | Drill and Complete | SURF | DRILL | 26 | 182 | 1434 | 2.2083 | 2.2083 | WW - 2021
462 | WWA-9 | Drill and Complete | SURF | CSGCMT | 20 | 1434 | 1434 | 2.4792 | 4.6875 | WW - 2021
463 | WWA-9 | Drill and Complete | DRLGLNR1 | DRILL | 17 1/2 | 1434 | 3200 | 3.4167 | 8.1042 | WW - 2021
464 | WWA-9 | Drill and Complete | DRLGLNR1 | CSGCMT | 13 3/8 | 3200 | 3200 | 2.0833 | 10.1875 | WW - 2021
465 | WWA-9 | Drill and Complete | DRLGLNR | TB | 13 3/8 | 3200 | 3200 | 1.6042 | 11.7917 | WW - 2021
466 | WWA-9 | Drill and Complete | PRODLNR1 | DRILL | 12 1/4 | 3200 | 4805 | 2.1667 | 13.9583 | WW - 2021
467 | WWA-9 | Drill and Complete | PRODLNR1 | CSGCMT | 10 3/4 | 4805 | 5246 | 0.89583 | 14.8542 | WW - 2021
468 | WWA-9 | Drill and Complete | PRODLNR2 | DRILL | 9 7/8 | 0 | 7158 | 4.2292 | 19.0833 | WW - 2021
469 | WWA-9 | Drill and Complete | PRODLNR2 | CSGCMT | 8 5/8 |  |  |  |  | WW - 2021

## Compared
SOURCE: PHASE SUMMARY |  |  |  | SOURCE: DEPTH VS DAYS (WELLVIEW RAW) | [5 empty] | PH SUM - DEPTH vs DAYS
Campaign | Well Name | Max of Actual End Depth (ftKB) | Max of Act Cum Dur (days) | Campaign | Well Name (WellView Version) | Max of Depth End (MD) | Max of Cum Time Log Days_WV | Well OK? | Well | dZ, ft | dDays, days | Gen.Camp ft, MD | Diff | TVD Chart |  | Depth, ft MD
DRJ - 2019 | DRJ-44 | 5860 | 36.0417 | DRJ - 2019 | DRJ-44 | 5860 | 36.0417 | TRUE | DRJ-44 | 0 | 0 | 5860 | 0 |  | MBA-6 | 5732
DRJ - 2019 | DRJ-45 | 5977 | 80.4792 | DRJ - 2019 | DRJ-45 | 5977 | 80.4792 | TRUE | DRJ-45 | 0 | 0 | 5977 | 0 |  | MBA-7 | 4965
DRJ - 2019 | DRJ-46 | 5836 | 47.0833 | DRJ - 2019 | DRJ-46 | 5836 | 47.4792 | TRUE | DRJ-46 | 0 | -0.39583 | 5836 | 0 |  | MBD-7 | 4997
DRJ - 2019 | DRJ-47 | 5902 | 35.8333 | DRJ - 2019 | DRJ-47 | 5902 | 35.8333 | TRUE | DRJ-47 | 0 | 0 | 5902 | 0 |  | MBD-8 | 4140
DRJ - 2019 | DRJ-48 | 5399.5 | 28.875 | DRJ - 2019 | DRJ-48 | 5399.5 | 28.9375 | TRUE | DRJ-48 | 0 | -0.0625 | 5399.5 | 0 |  | DRJ-48 | 5399.5
DRJ - 2022 | DRJ-38RD | 8250.0003 | 36.4167 | DRJ - 2022 | DRJ-38RD | 6748 | 30 | TRUE | DRJ-38RD | 1502.0003 | 6.4167 | 6748 | 1502.0003 | 6748 | DRJ-47 | 5902
DRJ - 2022 | DRJ-49 | 6310 | 35.0104 | DRJ - 2022 | DRJ-49 | 6310 | 35.0208 | TRUE | DRJ-49 | 0 | -0.010417 | 6310 | 0 |  | DRJ-44 | 5860
DRJ - 2022 | DRJ-50 | 5749 | 29.2292 | DRJ - 2022 | DRJ-50 | 5749 | 29.2292 | TRUE | DRJ-50 | 0 | 0 | 5749 | 0 |  | DRJ-45 | 5977
DRJ - 2022 | DRJ-51 | 4993 | 29.4375 | DRJ - 2022 | DRJ-51 | 4993 | 29.4375 | TRUE | DRJ-51 | 0 | 0 | 4993 | 0 |  | DRJ-46 | 5836
DRJ - 2022 | DRJ-52 | 5765 | 20.375 | DRJ - 2022 | DRJ-52 | 5765 | 20.375 | TRUE | DRJ-52 | 0 | 0 | 5765 | 0 |  | MBI-1 | 4325
DRJ - 2024 | DRJ-53 | 6500 | 22.7708 | DRJ - 2024 | DRJ-53 | 6500 | 22.7708 | TRUE | DRJ-53 | 0 | 0 | 6500 | 0 |  | WWA-9 | 7158
DRJ - 2024 | DRJ-54 | 6014 | 29.6875 | DRJ - 2024 | DRJ-54 | 6014 | 29.6875 | TRUE | DRJ-54 | 0 | 0 | 6014 | 0 |  | WWA-8 | 5263
DRJ - 2024 | DRJ-55 | 6000 | 18.2292 | DRJ - 2024 | DRJ-55 | 6000 | 18.2292 | TRUE | DRJ-55 | 0 | 0 | 6000 | 0 |  | MBE-7 | 7065
DRJ - 2024 | DRJ-56 | 6500 | 50.3125 | DRJ - 2024 | DRJ-56 | 6500 | 50.3125 | TRUE | DRJ-56 | 0 | 0 | 6500 | 0 |  | MBE-6 | 4500
DRJ - 2024 | DRJ-57 | 6000 | 18.8542 | DRJ - 2024 | DRJ-57 | 6000 | 18.8542 | TRUE | DRJ-57 | 0 | 0 | 6000 | 0 |  | MBD-8WO
SLK - 2021 | AWI 16-8 | 5000 | 39.0417 | SLK - 2021 | AWI 16-8 | 5000 | 38.5417 | TRUE | AWI 16-8 | 0 | 0.5 | 5000 | 0 |  | AWI 21-6 | 4918
SLK - 2021 | AWI 16-9 | 5379 | 19.2708 | SLK - 2021 | AWI 16-9 | 5379 | 18.2708 | TRUE | AWI 16-9 | 0 | 1 | 5379 | 0 |  | AWI 21-5 | 4685
SLK - 2021 | AWI 21-5 | 4685 | 22.0625 | SLK - 2021 | AWI 21-5 | 4685 | 22.0625 | TRUE | AWI 21-5 | 0 | 0 | 4685 | 0 |  | AWI 16-9 | 5379
SLK - 2021 | AWI 21-6 | 4918 | 12.4993 | SLK - 2021 | AWI 21-6 | 4918 | 12.5 | TRUE | AWI 21-6 | 0 | -0.00069444 | 4918 | 0 |  | AWI 16-8 | 5000
SLK - 2021 | AWI 9-10 | 8919 | 22.0417 | SLK - 2021 | AWI 9-10 | 8919 | 22 | TRUE | AWI 9-10 | 0 | 0.041667 | 8919 | 0 |  | AWI 9-10 | 8919
SLK - 2025 | AWI 21-7 | 5060 | 16.4167 | SLK - 2025 | AWI 21-7 | 5060 | 16.4167 | TRUE | AWI 21-7 | 0 | 0 | 5060 | 0 |  | DRJ-51 | 4993
SLK - 2025 | AWI 21-8 | 4055 | 14.9792 | SLK - 2025 | AWI 21-8 | 4055 | 14.9792 | TRUE | AWI 21-8 | 0 | 0 | 4055 | 0 |  | DRJ-52 | 5765
SLK - 2025 | AWI 23-1 | 9000 | 20.4583 | SLK - 2025 | AWI 23-1 | 9000 | 20.4583 | TRUE | AWI 23-1 | 0 | 0 | 9000 | 0 |  | DRJ-50 | 5749
SLK - 2025 | AWI 23-2 | 8050 | 20 | SLK - 2025 | AWI 23-2 | 8050 | 20 | TRUE | AWI 23-2 | 0 | 0 | 8050 | 0 |  | DRJ-49 | 6310
SLK - 2025 | AWI 2-6 | 5484 | 11.0417 | SLK - 2025 | AWI 2-6 | 5484 | 11.0417 | TRUE | AWI 2-6 | 0 | 0 | 5484 | 0 |  | DRJ-38RD | 6748
SLK - 2025 | AWI 2-7 ML | 5497 | 25.3125 | SLK - 2025 | AWI 2-7 ML | 5497 | 26 | TRUE | AWI 2-7 ML | 0 | -0.6875 | 5497 | 0 |  | DRJ-53 | 6500
SLK - 2025 | AWI 3-9 | 5500 | 16.5625 | SLK - 2025 | AWI 3-9 | 5500 | 16.5625 | TRUE | AWI 3-9 | 0 | 0 | 5500 | 0 |  | DRJ-54 | 6014
SLK - 2025 | AWI 9-11 | 9000 | 22.3333 | SLK - 2025 | AWI 9-11 | 4500 | 11.3333 | TRUE | AWI 9-11 | 4500 | 11 | 9000 | 0 | 9000 | DRJ-55 | 6000
WW - 2018 | MBA-6 | 5732 | 28.8958 | WW - 2018 | MBA-6 | 5732 | 28.8958 | TRUE | MBA-6 | 0 | 0 | 5732 | 0 |  | DRJ-56 | 6500
WW - 2018 | MBA-7 | 4965 | 27.5833 | WW - 2018 | MBA-7 | 4965 | 27.5833 | TRUE | MBA-7 | 0 | 0 | 4965 | 0 |  | DRJ-57 | 6000
WW - 2018 | MBD-7 | 4997 | 39.7708 | WW - 2018 | MBD-7 | 4997 | 38.7708 | TRUE | MBD-7 | 0 | 1 | 4997 | 0 |  | AWI 21-8 | 4055
WW - 2018 | MBD-8 | 4140 | 50.75 | WW - 2018 | MBD-8 | 4140 | 50.6042 | TRUE | MBD-8 | 0 | 0.14583 | 4140 | 0 |  | AWI 21-7 | 5060
WW - 2021 | MBE-6 | 4500 | 15.2292 | WW - 2021 | MBE-6 | 4500 | 15.2292 | TRUE | MBE-6 | 0 | 0 | 4500 | 0 |  | AWI 3-9 | 5500
WW - 2021 | MBE-7 | 7065 | 24.1042 | WW - 2021 | MBE-7 | 7065 | 24.1042 | TRUE | MBE-7 | 0 | 0 | 7065 | 0 |  | AWI 23-1 | 9000
WW - 2021 | MBI-1 | 4325 | 10.9167 | WW - 2021 | MBI-1 | 4325 | 10.9167 | TRUE | MBI-1 | 0 | 0 | 4325 | 0 |  | AWI 23-2 | 8050
WW - 2021 | WWA-8 | 4287 | 46.2292 | WW - 2021 | WWA-8 | 5263 | 45.2292 | TRUE | WWA-8 | -976 | 1 | 5263 | -976 | 4287 | AWI 2-7 ML | 5497
WW - 2021 | WWA-9 | 7158 | 19.0833 | WW - 2021 | WWA-9 | 7158 | 18.4583 | TRUE | WWA-9 | 0 | 0.625 | 7158 | 0 |  | AWI 2-6 | 5484
[15 empty] | AWI 9-11 | 9000
[15 empty] | AWI 9-10 RD | #N/A

## Drill.Campaign.Ref.Tidy
WBS Reference for Drilling Campaign (Drilling Cost)
WBS Level | WBS Drilling Campaign | Campaign | Well Name
2 | E500-2-0-8501-185003 | Wayang Windu Campaign 2018/2019 | MBA-6 MBA-7 MBD-7 MBD-8
2 | E530-30101-D19001 | Darajat Campaign 2019 | DRJ S4 SW DRJ 20 WNW DRJ S4SSE DRJ S4S
2 | E500-30101-D205011 | Wayang Windu Campaign 2020/2021 | MBI 1 WWA 9 WWA 8 MBE 07 MBE 06 MBD 8 WO
2 | E540-30101-D20001 | Salak Campaign 2021 | AWI 21-06 AWI 21-05 AWI 16-09 AWI 16-08 AWI 9-10
2 | E530-30101-D225301 | Darajat Campaign 2022 | DRJ 14-1 DRJ 14-2 DRJ 20-1 DRJ SF-1 DRJ SF-ML
2 | E530-30101-D235301 | Darajat Campaign 2023/2024 | DRJ Steam 6 : DRJ 53 DRJ Steam 2 : DRJ 54 DRJ Steam 3 : DRJ 55 DRJ Steam 4 : DRJ 56 DRJ Steam 5 : DRJ 57
2 | E540-30101-D245401 | Salak Campaign 2025/2026 | AWI 21-8 AWI 21-7 AWI 3-9 AWI 23-1 AWI 23-2 AWI 2-7 ML AWI 2-6 AWI 9-11 AWI 2-10RD

## Sheet9
ft/day
Asset_Label | Campaign | Darajat | Salak | Wayang Windu
Darajat | DRJ - 2019 | 241.3036
Darajat | DRJ - 2022 | 224.9333
Darajat | DRJ - 2024 | 221.7596
Salak | SLK - 2021 |  | 405.4091
Salak | SLK - 2025 |  | 377.1994
Wayang Windu | WW - 2018 |  |  | 121.1624
Wayang Windu | WW - 2021 |  |  | 239.2659
Ft | 600 | ft |  | z x v
Ideal time | 20 | days
Actual time | 30 | days |  | z x v2
Delta days | -10 | days |  | z x (v - dv)
|  |  |  | z | 600 | ft
ROP & Penetration |  |  |  | V1 | 30 | ft/d
ROP ideal | 30 | ft/day |  | dV | 10 | ft/d
Penetration actual rate | 20 | ft/day
delta | -10 | ft/day
|  |  |  | V2 | 40 | ft/day
Feet not realized | -300 | ft |  | t2 | 15 | day
Ft realized, | 900 | ft |  | v1 | 30 | ft/day
|  |  |  | t1 | 20 | day
|  |  |  | dt | -5 | days
|  |  |  | z | 600 | ft
|  |  |  | Avg act | 1 | days
|  |  |  | dDays | 15%
|  |  |  | Expc days | 0.85 | days

## Sheet4
Data returned for Sum of Actual Cost USD, Well Cost - Services - Directional Drilling & Surveys, MBD-8 (First 1000 rows).
Table18[#] | Table18[Asset] | Table18[Campaign] | Table18[Level 2] | Table18[Level 3] | Table18[Level 4] | Table18[Level 5] | Table18[Well] | Table18[Actual Cost USD]
47 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-8 | 1977239.44

## Sheet3
Asset | All
Sum of Actual Cost USD | Column Labels
Row Labels | MBA-6 | MBA-7 | MBD-7 | MBD-8
Well Cost
Drilling Operation Water Support
Drilling Operation Water Support | 12864.21
Material - LL
Casing | 395838.88 | 325171.97 | 299595.79 | 304089.61 | mbd 7 8 shallower (??)
Equipment Rental | 457313.66
Fuel & Lubricants | 133859.92 | 217969.05 | 397730.2 | 432393.83 | problem well for mbd 7 & 8(??)
Well Equipment Surface | 76817.64 | 73907.16 | 57089.09 | 64532.62
Services
API non API Machine Shop Service | 103071.13 | 129993.89 | 131706.28 | 152464.29
Bits, Reamer and Core heads | -12705 | 88611 | 84413 | 76948.75
Casing Installation | 75718.2 | 76816.73 | 55441.94 | 75380.46
Cement, Cementing & Pump Fees | 439716.99 | 402650.92 | 450613.83 | 644909.26
Contract Rig | 1543621.9 | 1455536.41 | 1675768.33 | 2358033.98 | why mbd 7 8 (?)
Directional Drilling & Surveys | 334786.2 | 341813.33 | 416441.82 | 1977239.44 | mbd 8 kenapa lebih tinggi 3x lipat
Drilling Safety, Health & Environment | 71177 | 66339.49 | 94771.95 | 93867.15
Equipment Rental | -141778.44 | 329171.23 | 829062.51 | 626075.37 | why mbd 7 8 (?)
Land Transportation | 117550.47 | 76205.36 | 150677.1 | 185244.79
Mud Logging Service | 68207.7 | 61220.32 | 88856.75 | 104010.01
Mud, Chemical and Engineering Service | 417750.09 | 688367.79 | 1827224.33 | 1762720.88 | why mbd 7 8 (?)
Open Hole Electrical Logging Service |  | 0 | 0 | 154684.52
Other Transportation | 200544.73 | 7081.19 | 7103.95 | 14360.42
Others | 17890.25
Service Lines & Communication | 1752.74 | 1785.73 | 2140.73 | 2421.73
Supervision | 185132.24 | 80443.65 | 127652.64 | 151322.99
whats the story with WW 2018

## Structured.Cost (2)
# | Asset | Campaign | Level 2 | Level 3 | Level 4 | Level 5 | Well | Actual Cost USD
1 | Wayang Windu | WW - 2018 | Drilling Cost | LIH | LIH | LIH | General | -105457.27
2 | Wayang Windu | WW - 2018 | Drilling Cost | Logging Cost | Logging Cost | Logging Cost | General | 160573.24
3 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | General | 0
4 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-6 | 11935.55
5 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-7 | 325171.97
6 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-7 | 299595.79
7 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-8 | 304089.61
8 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | -149146.03
9 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBA-6 | 133859.92
10 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBA-7 | 217969.05
11 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-7 | 397730.2
12 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-8 | 432393.83
13 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | General | 0
14 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-6 | -321.15
15 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-7 | 73907.16
16 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBD-7 | 57089.09
17 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBD-8 | 64532.62
18 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | General | -228196.52
19 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBA-6 | 103071.13
20 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBA-7 | 129993.89
21 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBD-7 | 131706.28
22 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | MBD-8 | 152464.29
23 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | General | 0
24 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-6 | -45705
25 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-7 | 88611
26 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-7 | 84413
27 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-8 | 76948.75
28 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | General | -10421.91
29 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-6 | 2844.22
30 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-7 | 76816.73
31 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-7 | 55441.94
32 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-8 | 75380.46
33 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | -174558.94
34 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-6 | -26298.11
35 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-7 | 402650.92
36 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-7 | 450613.83
37 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-8 | 644909.26
38 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | General | -1867545.5
39 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-6 | 566893.34
40 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-7 | 1455536.41
41 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-7 | 1675768.33
42 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-8 | 2358033.98
43 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | General | 0
44 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-6 | -141925.8
45 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-7 | 341813.33
46 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-7 | 416441.82
47 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-8 | 1977239.44
48 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | -16482.32
49 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-6 | 39109.49
50 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-7 | 66339.49
51 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-7 | 94771.95
52 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-8 | 93867.15
53 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | General | 0
54 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBA-6 | -141778.44
55 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBA-7 | 329171.23
56 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBD-7 | 829062.51
57 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Equipment Rental | MBD-8 | 626075.37
58 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | General | -38611.47
59 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-6 | 10230.16
60 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-7 | 76205.36
61 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-7 | 150677.1
62 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-8 | 185244.79
63 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | -32083.35
64 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-6 | -5105.34
65 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-7 | 61220.32
66 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-7 | 88856.75
67 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-8 | 104010.01
68 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | General | 0
69 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-6 | -668928.96
70 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-7 | 688367.79
71 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-7 | 1827224.33
72 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-8 | 1762720.88
73 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | General | 0
74 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBA-7 | 0
75 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBD-7 | 0
76 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBD-8 | 154684.52
77 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | General | -16983.19
78 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 11550.1
79 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-7 | 7081.19
80 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-7 | 7103.95
81 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-8 | 14360.42
82 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | -3010.93
83 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-6 | -247.26
84 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-7 | 1785.73
85 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-7 | 2140.73
86 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-8 | 2421.73
87 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | General | -111731.14
88 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-6 | 116332.5
89 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-7 | 80443.65
90 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBD-7 | 127652.64
91 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBD-8 | 151322.99
92 | Wayang Windu | WW - 2018 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 112.34
93 | Wayang Windu | WW - 2018 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 71133.41
94 | Wayang Windu | WW - 2018 | Support Cost | Permitting (IPPKH/IPJLPB) | Hardware Supply | Permitting | General | 0
95 | Wayang Windu | WW - 2018 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 72283.43
96 | Wayang Windu | WW - 2018 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 117507.88
97 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 0
98 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Tie-in | Procurement | Installation, Hook Up & Pre-Commisioning | General | 552424.06
99 | Wayang Windu | WW - 2018 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 313780.66
100 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Casing | MBA-6 | 383903.33
101 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBA-6 | 77138.79
102 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBA-6 | 2000
103 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | MBA-6 | 12864.21
104 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | MBA-6 | 976728.56
105 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBA-6 | 1086679.05
106 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBA-6 | 33000
107 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBA-6 | 457313.66
108 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBA-6 | 476712
109 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | MBA-6 | 72873.98
110 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBA-6 | 466015.1
111 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBA-6 | 73313.04
112 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | MBA-6 | 68799.74
113 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | MBA-6 | 107320.31
114 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 5871.45
115 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | MBA-6 | 183123.18
116 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBA-6 | 32067.51
117 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | MBA-6 | 10359.49
118 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | MBA-6 | 7530.76
119 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 476192.46
120 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | 3010.93
121 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Drilling Operation Water Support | Drilling Operation Water Support | General | 4904.05
122 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Contract Rig | General | 1866987.58
123 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Casing Installation | General | 10421.91
124 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | 174558.94
125 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | 16400
126 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Supervision | General | 111731.14
127 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Land Transportation | General | 32683.58
128 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Other Transportation | General | 16983.19
129 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | 149146.03
130 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 69.37
131 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | 16365.77
132 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 175153.08
133 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 580963.37
134 | Wayang Windu | WW - 2018 | Drilling Cost | Well Cost | Services | Others | General | 18635.98
136 | Darajat | DRJ - 2019 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 3136274.38
137 | Darajat | DRJ - 2019 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1337803.55
138 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-44OH | 367853.72
139 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-45OH | 571988.4
140 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-46OH | 532507.52
141 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-47OH | 454605.79
142 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-48 | 359868.91
143 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-44OH | 370208.79
144 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-45OH | 862920.21
145 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-46OH | 567110.31
146 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-47OH | 428314.23
147 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-48 | 332831.74
148 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-44OH | 318467.05
149 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-45OH | 580748.72
150 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-46OH | 368892.76
151 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-47OH | 298311.87
152 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-48 | 281753.9
153 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-44OH | 42261.87
154 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-45OH | 46684.52
155 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-46OH | 44139.04
156 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-47OH | 43094.75
157 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-48 | 43465.68
158 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-44OH | 135360
159 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-45OH | 321941.79
160 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-46OH | 168825.17
161 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-47OH | 105736.8
162 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-48 | 128882.5
163 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-44OH | 53399.65
164 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-45OH | 147905.11
165 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-46OH | 22398.73
166 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-47OH | 43200.12
167 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-48 | 111988.49
168 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-44OH | 395083.1
169 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-45OH | 929785.71
170 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-46OH | 808531.89
171 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-47OH | 567957.4
172 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-48 | 418783.86
173 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-44OH | 1319224
174 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-45OH | 2233613.7
175 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-46OH | 1308448.96
176 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-47OH | 1045526.44
177 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-48 | 728159.42
178 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-44OH | 358007.9
179 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-46OH | 624076.94
180 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-47OH | 756550.79
181 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-48 | 1096259.06
182 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-44OH | 41904.02
183 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-45OH | 128749.16
184 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-46OH | 75023.2
185 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-47OH | 57579.6
186 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-48 | 29319.96
187 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-44OH | 93305.44
188 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-45OH | 225633.72
189 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-46OH | 130265.36
190 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-47OH | 100633.48
191 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-48 | 170960.95
192 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-44OH | 35453.82
193 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-45OH | 84843.99
194 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-46OH | 50328.8
195 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-47OH | 37982.98
196 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-48 | 30672.16
197 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-44OH | 401556.19
198 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-46OH | 824197.43
199 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-47OH | 626372.53
200 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-48 | 1445756.12
201 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-48 | 109856.93
202 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-44OH | 171589.2
203 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-45OH | 204629.65
204 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-46OH | 326157.76
205 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-47OH | 135804.1
206 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | DRJ-48 | 193295.66
207 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Others | General | 6141.57
208 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-44OH | 1142
209 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-46OH | 1582
210 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-47OH | 1156
211 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-48 | 3575
212 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-44OH | 110802.99
213 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-45OH | 216667.32
214 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-46OH | 116665.88
215 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-47OH | 100968.1
216 | Darajat | DRJ - 2019 | Drilling Cost | Well Cost | Services | Supervision | DRJ-48 | 93671.47
217 | Darajat | DRJ - 2019 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 1009443.94
218 | Darajat | DRJ - 2019 | Support Cost | PGPA & Security | PGPA | PGPA | General | 602913.71
219 | Darajat | DRJ - 2019 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 232821.26
220 | Darajat | DRJ - 2019 | Support Cost | Well Testing | Well Testing | Well Testing | General | 333273.87
221 | Darajat | DRJ - 2019 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 141985.79
222 | Darajat | DRJ - 2019 | Surface Facilities Cost | Conductor Casing Installation & Material | Services | Service | General | 570474.38
223 | Darajat | DRJ - 2019 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 1183965.08
224 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 2589388.68
225 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 3295100.56
226 | Darajat | DRJ - 2019 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 440017.11
227 | Wayang Windu | WW - 2021 | Drilling Cost | Explosive | Explosive | Explosive | General | 129531.42
228 | Wayang Windu | WW - 2021 | Drilling Cost | LIH | LIH | LIH | General | 330865.54
229 | Wayang Windu | WW - 2021 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 3981170.51
230 | Wayang Windu | WW - 2021 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 201214.07
231 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBD-8WO | 72987.9
232 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBE-6 | 409317.86
233 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBE-7 | 593931.6
234 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | MBI-1 | 368289.74
235 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | WWA-8 | 513871.54
236 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | WWA-9 | 585870.55
237 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBD-8WO | 533496.04
238 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBE-6 | 231136.99
239 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBE-7 | 344832.62
240 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | MBI-1 | 179334.32
241 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | WWA-8 | 762026.33
242 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | WWA-9 | 270273.02
243 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBD-8WO | 200286.6
244 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBE-6 | 169951.07
245 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBE-7 | 91084.43
246 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | MBI-1 | 88905.15
247 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | WWA-8 | 226206.2
248 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | WWA-9 | 218216.73
249 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBE-6 | 80177.45
250 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBE-7 | 64124.49
251 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | MBI-1 | 66560.99
252 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | WWA-8 | 56105.44
253 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | WWA-9 | 52653.32
254 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBD-8WO | 15385.86
255 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBE-6 | 71817.63
256 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBE-7 | 110547.29
257 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | MBI-1 | 90817.65
258 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | WWA-8 | 171407.29
259 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | WWA-9 | 110547.28
260 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBD-8WO | 55337.05
261 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBE-6 | 55253.68
262 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBE-7 | 100305.64
263 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | MBI-1 | 55580.6
264 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | WWA-8 | 53894.8
265 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | WWA-9 | 72409.5
266 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBD-8WO | 187723.47
267 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBE-6 | 276242.39
268 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBE-7 | 400466.91
269 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | MBI-1 | 236423.66
270 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | WWA-8 | 532362.28
271 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | WWA-9 | 305944.7
272 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBD-8WO | 880156.96
273 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBE-6 | 436456.53
274 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBE-7 | 680370.68
275 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | MBI-1 | 348332.76
276 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | WWA-8 | 1229036.48
277 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | WWA-9 | 518644.75
278 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBD-8WO | 315268.62
279 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBE-6 | 239924.36
280 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBE-7 | 324820.26
281 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | MBI-1 | 208122.09
282 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | WWA-8 | 706179.17
283 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | WWA-9 | 265095.09
284 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBD-8WO | 12392.45
285 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBE-6 | 6832.05
286 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBE-7 | 10737.34
287 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | MBI-1 | 5366
288 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | WWA-8 | 18858.51
289 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | WWA-9 | 7931.09
290 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBD-8WO | 68781.39
291 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBE-6 | 46472.28
292 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBE-7 | 54339.75
293 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | MBI-1 | 23515.42
294 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | WWA-8 | 114753.8
295 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | WWA-9 | 56610.35
296 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBD-8WO | 24494.27
297 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBE-6 | 11480
298 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBE-7 | 548.81
299 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | MBI-1 | 15831.29
300 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | WWA-8 | 59638.95
301 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | WWA-9 | 24464.01
302 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBD-8WO | 277995.3
303 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBE-6 | 277107.12
304 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBE-7 | 404978.12
305 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | MBI-1 | 71653.58
306 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | WWA-8 | 493805.9
307 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | WWA-9 | 179630.72
308 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBE-6 | 29400
309 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | MBE-7 | 41823.45
310 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | General | 22300.88
311 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBD-8WO | 3095.42
312 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBE-6 | 4562.38
313 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | MBE-7 | 4428.19
314 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBD-8WO | 84302.59
315 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBE-6 | 145881.28
316 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBE-7 | 178521.37
317 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | MBI-1 | 112596.93
318 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | WWA-8 | 241638.46
319 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Others | WWA-9 | 180531.16
320 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBD-8WO | 941
321 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBE-6 | 1115
322 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBE-7 | 3429.54
323 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | MBI-1 | 363
324 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | WWA-8 | 900
325 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | WWA-9 | 615
326 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBD-8WO | 83861.36
327 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBE-6 | 46711.72
328 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBE-7 | 72937.18
329 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | MBI-1 | 45980.56
330 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | WWA-8 | 125279.46
331 | Wayang Windu | WW - 2021 | Drilling Cost | Well Cost | Services | Supervision | WWA-9 | 53695.39
332 | Wayang Windu | WW - 2021 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 129437.17
333 | Wayang Windu | WW - 2021 | Support Cost | IT & Communication | Drilling Facilities Support | Hardware Supply | General | 15984.04
334 | Wayang Windu | WW - 2021 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 18015.03
335 | Wayang Windu | WW - 2021 | Support Cost | PGPA & Security | PGPA | PGPA | General | 4156.68
336 | Wayang Windu | WW - 2021 | Support Cost | PGPA & Security | Security | Security | General | 65091.26
337 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 36778.03
338 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBD-8WO | 5802.67
339 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBE-6 | 17944.21
340 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBE-7 | 21184.52
341 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | MBI-1 | 3034.21
342 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | WWA-8 | 3034.21
343 | Wayang Windu | WW - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | WWA-9 | 3034.21
344 | Wayang Windu | WW - 2021 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 135591.23
345 | Wayang Windu | WW - 2021 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 8336.88
346 | Wayang Windu | WW - 2021 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 16051.55
347 | Wayang Windu | WW - 2021 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 271686
348 | Wayang Windu | WW - 2021 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 73078.09
349 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | MBE-6 | 113533.87
350 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | MBE-7 | 131575.61
351 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | WWA-8 | 103755.9
352 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | WWA-9 | 101119.67
353 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 339765.29
354 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBD-8WO | 43316.39
355 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBE-6 | 40570.57
356 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBE-7 | 32466.06
357 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | MBI-1 | 24941.43
358 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | WWA-8 | 11509.15
359 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | WWA-9 | 24870.39
360 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 160032.47
361 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBD-8WO | 127823.74
362 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBE-6 | 150242.22
363 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBE-7 | 163175.01
364 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | MBI-1 | 151195.77
365 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | WWA-8 | 30995.67
366 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | WWA-9 | 145307.49
367 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 4339.44
368 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | WWA-8 | 6424.63
369 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Engineering | Engineering | WWA-9 | 6424.61
370 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 208653.62
371 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBD-8WO | 10090.5
372 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBE-6 | 47330.47
373 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBE-7 | 52316.65
374 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | MBI-1 | 101977.03
375 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | WWA-8 | 72676.01
376 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | WWA-9 | 83379.7
377 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 59483.98
378 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBE-6 | 12494.31
379 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBE-7 | 11463.18
380 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | MBI-1 | 19141.45
381 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | WWA-8 | 11660.59
382 | Wayang Windu | WW - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | WWA-9 | 12278.16
383 | Salak | SLK - 2021 | Drilling Cost | LIH | LIH | LIH | General | 1531986.77
384 | Salak | SLK - 2021 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2089596.15
385 | Salak | SLK - 2021 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1721630.85
386 | Salak | SLK - 2021 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 240894.27
387 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 16-08 | 425099.43
388 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 16-09 | 402339.51
389 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | Awi 21-05 | 472745.02
390 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | Awi 21-06 | 356852.49
391 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-10 | 527713.81
392 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 16-08 | 467276.53
393 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 16-09 | 164541.09
394 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | Awi 21-05 | 215162.26
395 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | Awi 21-06 | 91365.62
396 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-10 | 267325.16
397 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Others | Awi 21-05 | 20805.02
398 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Others | AWI 9-10 | 4044.28
399 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 16-08 | 153306.91
400 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 16-09 | 138386.43
401 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | Awi 21-05 | 1777.1
402 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | Awi 21-06 | 1017.84
403 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-10 | 91686.64
404 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 16-08 | 152674
405 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 16-09 | 96387
406 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | Awi 21-05 | 107327
407 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | Awi 21-06 | 96387
408 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-10 | 96387
409 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 16-08 | 91320.71
410 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 16-09 | 73700.11
411 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | Awi 21-05 | 54026.09
412 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | Awi 21-06 | 54473.34
413 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-10 | 72940.53
414 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 16-08 | 901112.84
415 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 16-09 | 436221.84
416 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | Awi 21-05 | 337535.81
417 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | Awi 21-06 | 355841.12
418 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-10 | 480970.12
419 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 16-08 | 1120266.73
420 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 16-09 | 529448.46
421 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | Awi 21-05 | 610958.48
422 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | Awi 21-06 | 353180.05
423 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-10 | 625984.53
424 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 16-08 | 437427.53
425 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 16-09 | 224302.69
426 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | Awi 21-05 | 261948.12
427 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | Awi 21-06 | 166333.3
428 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-10 | 260085.35
429 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 16-08 | 18622.03
430 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 16-09 | 8683.85
431 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | Awi 21-05 | 9585.31
432 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-10 | 9709.76
433 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 16-08 | 488997.36
434 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 16-09 | 248812.25
435 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | Awi 21-05 | 459144.39
436 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | Awi 21-06 | 176541.56
437 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-10 | 304583.66
438 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 16-08 | 124815.55
439 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 16-09 | 37123.29
440 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | Awi 21-05 | 64079.18
441 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | Awi 21-06 | 479.69
442 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-10 | 59122.98
443 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 16-08 | 38542
444 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 16-09 | 18270
445 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | Awi 21-05 | 22062
446 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | Awi 21-06 | 12500
447 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-10 | 21991
448 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 16-08 | 553955.47
449 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 16-09 | 380369.19
450 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | Awi 21-05 | 215916.4
451 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | Awi 21-06 | 163342.31
452 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-10 | 389865.09
453 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 16-08 | 9633.44
454 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 16-09 | 13578.53
455 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | Awi 21-05 | 12218
456 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | Awi 21-06 | 13875.08
457 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-10 | 14359.78
458 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 16-08 | 339463.67
459 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 16-09 | 234866.72
460 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | Awi 21-05 | 181353.4
461 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | Awi 21-06 | 275766.02
462 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Others | AWI 9-10 | 321789.39
463 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 16-08 | 1000
464 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 16-09 | 608
465 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | Awi 21-05 | 662
466 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | Awi 21-06 | 416
467 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-10 | 1877.11
468 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 16-08 | 136509.33
469 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 16-09 | 51266.89
470 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | Awi 21-05 | 64507.2
471 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | Awi 21-06 | 31377.29
472 | Salak | SLK - 2021 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-10 | 55436.83
473 | Salak | SLK - 2021 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Other | General | 73309.31
474 | Salak | SLK - 2021 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 115695.83
475 | Salak | SLK - 2021 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 194.66
476 | Salak | SLK - 2021 | Support Cost | PGPA & Security | PGPA & Security | Other | General | 4042.69
477 | Salak | SLK - 2021 | Support Cost | PGPA & Security | PGPA & Security | PGPA & Security | General | 106038.43
478 | Salak | SLK - 2021 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 56448.66
479 | Salak | SLK - 2021 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 296189.13
480 | Salak | SLK - 2021 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 1154.8
481 | Salak | SLK - 2021 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 14769.16
482 | Salak | SLK - 2021 | Support Cost | SHE | SHE Permit | Environment Permit | General | 5318.4
483 | Salak | SLK - 2021 | Support Cost | SHE | SHE Permit | Others | General | 143.34
484 | Salak | SLK - 2021 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 281675.05
485 | Salak | SLK - 2021 | Support Cost | Well Testing | Well Testing | Well Testing | General | 339981.58
486 | Salak | SLK - 2021 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 88740.03
487 | Salak | SLK - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Others | General | 73521.98
488 | Salak | SLK - 2021 | Surface Facilities Cost | Conductor Casing Installation & Material | Service | Service | General | 844257.09
489 | Salak | SLK - 2021 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 703912.78
490 | Salak | SLK - 2021 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 15826.09
491 | Salak | SLK - 2021 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 102042.51
492 | Salak | SLK - 2021 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 894047.32
493 | Salak | SLK - 2021 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 1063466.97
494 | Darajat | DRJ - 2022 | Drilling Cost | Explosive | Explosive | Explosive | General | 119099.02
495 | Darajat | DRJ - 2022 | Drilling Cost | LIH | LIH | LIH | General | 0
496 | Darajat | DRJ - 2022 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2658145.82
497 | Darajat | DRJ - 2022 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1615754.88
498 | Darajat | DRJ - 2022 | Drilling Cost | Rig Skid | Skid Moving | Rig Skid | General | 169380.89
499 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-38RD | 13514.56
500 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-49OH | 31535.17
501 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-50OH | 22400.72
502 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-51OH | 19432.99
503 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-52OH | 21580.53
504 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-38RD | 198087.95
505 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-49OH | 414603.22
506 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-50OH | 419472.97
507 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-51OH | 532953.13
508 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-52OH | 319725.93
509 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-38RD | 332119.15
510 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-49OH | 473986.83
511 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-50OH | 433704.53
512 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-51OH | 337680.73
513 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-52OH | 587193.81
514 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-38RD | 678.26
515 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-49OH | 52635.16
516 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-50OH | 67957.22
517 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-51OH | 51443.06
518 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | DRJ-52OH | 55296.04
519 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-38RD | 7653.56
520 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-49OH | 26370.44
521 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-50OH | 26370.44
522 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-51OH | 26370.44
523 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-52OH | 26370.44
524 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-38RD | 53020.16
525 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-49OH | 88305.13
526 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-50OH | 78769.12
527 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-51OH | 54349.72
528 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-52OH | 55784.64
529 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-38RD | 60128
530 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-49OH | 231601
531 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-50OH | 151482.5
532 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-51OH | 120098.5
533 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-52OH | 105762.5
534 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-38RD | 34670.49
535 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-49OH | 66375.81
536 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-50OH | 53644.74
537 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-51OH | 51885.17
538 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-52OH | 67979.2
539 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-38RD | 431610.05
540 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-49OH | 728386.4
541 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-50OH | 415221.41
542 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-51OH | 634852.06
543 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-52OH | 476892.74
544 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-38RD | 867517.38
545 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-49OH | 1033044.74
546 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-50OH | 838855.14
547 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-51OH | 821879
548 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-52OH | 577880
549 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-38RD | 0
550 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-49OH | 0
551 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-50OH | 0
552 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-51OH | 0
553 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Coring | DRJ-52OH | 0
554 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-38RD | 348618.99
555 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-49OH | 426500.84
556 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-50OH | 415437.95
557 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-51OH | 401366.06
558 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-52OH | 271966.42
559 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-38RD | 13026.14
560 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-49OH | 15440.29
561 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-50OH | 12880.89
562 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-51OH | 0
563 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-52OH | 8354.05
564 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-38RD | 798979.46
565 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-49OH | 430103.37
566 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-50OH | 475803.33
567 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-51OH | 438722.44
568 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-52OH | 269816.43
569 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-38RD | 36907.27
570 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-49OH | 40807.21
571 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-50OH | 41017.02
572 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-51OH | 40772.11
573 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-52OH | 51925.49
574 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-38RD | 78091.96
575 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-49OH | 89256.93
576 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-50OH | 66927.07
577 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-51OH | 74087.43
578 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-52OH | 80498.53
579 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-38RD | 30000
580 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-49OH | 34905
581 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-50OH | 29229
582 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-51OH | 29312
583 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-52OH | 67575
584 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-38RD | 319451.08
585 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-49OH | 443856.33
586 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-50OH | 305156.59
587 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-51OH | 369513.61
588 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-52OH | 345656.38
589 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-38RD | 56043.99
590 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-49OH | 33042.43
591 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-50OH | 62912.89
592 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-51OH | 14136.94
593 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-52OH | 32029.56
594 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-38RD | 127992
595 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-49OH | 0
596 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-50OH | 35818.98
597 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-51OH | 64482.04
598 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-52OH | 0
599 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-38RD | 0
600 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-49OH | 12170.25
601 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-50OH | 16468.12
602 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-51OH | 20360.22
603 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-52OH | 16329.48
604 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-38RD | 0
605 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-49OH | 0
606 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-50OH | 0
607 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-51OH | 0
608 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-52OH | 0
609 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-38RD | 999
610 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-49OH | 1311
611 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-50OH | 974
612 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-51OH | 980
613 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-52OH | 679
614 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-38RD | 90519.15
615 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-49OH | 92633.31
616 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-50OH | 85446.68
617 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-51OH | 86100.33
618 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Supervision | DRJ-52OH | 60329.68
619 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-38RD | 173.86
620 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-49OH | 0
621 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-50OH | 0
622 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-51OH | 0
623 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-52OH | 0
624 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-38RD | 12413.28
625 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-49OH | 16005.34
626 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-50OH | 10851.89
627 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-51OH | 7705.26
628 | Darajat | DRJ - 2022 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-52OH | 7619.82
629 | Darajat | DRJ - 2022 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 111242.84
630 | Darajat | DRJ - 2022 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 383588.08
631 | Darajat | DRJ - 2022 | Support Cost | IT & Communication | Hardware Supply | Hardware Supply | General | 5049.74
632 | Darajat | DRJ - 2022 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 0
633 | Darajat | DRJ - 2022 | Support Cost | PGPA & Security | PGPA | PGPA | General | 32221.37
634 | Darajat | DRJ - 2022 | Support Cost | PGPA & Security | Security | Security | General | 29263.28
635 | Darajat | DRJ - 2022 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 14086.9
636 | Darajat | DRJ - 2022 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 431181.96
637 | Darajat | DRJ - 2022 | Support Cost | SHE | Drill Cutting | Heavy Equipment for Drill Cutting | General | 55128.71
638 | Darajat | DRJ - 2022 | Support Cost | SHE | Environmental Monitoring | Environmental Monitoring | General | 11182
639 | Darajat | DRJ - 2022 | Support Cost | SHE | Environmental Monitoring | IPAL | General | 0
640 | Darajat | DRJ - 2022 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 74043.23
641 | Darajat | DRJ - 2022 | Support Cost | SHE | SHE Permit | Andalalin | General | 0
642 | Darajat | DRJ - 2022 | Support Cost | SHE | SHE Permit | Environment Permit | General | 18968.04
643 | Darajat | DRJ - 2022 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 298156.75
644 | Darajat | DRJ - 2022 | Support Cost | Well Testing | Well Testing | Well Testing | General | 397045.52
645 | Darajat | DRJ - 2022 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 84508.19
646 | Darajat | DRJ - 2022 | Surface Facilities Cost | Conductor Casing Installation & Material | Material | Material | General | 361333.57
647 | Darajat | DRJ - 2022 | Surface Facilities Cost | Conductor Casing Installation & Material | Services | Service | General | 610128.96
648 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 784372.53
649 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 11467.04
650 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 0
651 | Darajat | DRJ - 2022 | Surface Facilities Cost | Road & Pad | Procurement | Material - Non LL | General | 62393.78
652 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 217964.53
653 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 0
654 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - LL | General | 60098.57
655 | Darajat | DRJ - 2022 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - Non LL | General | 49110.91
656 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 801479.81
657 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 33004.1
658 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 18900.82
659 | Darajat | DRJ - 2022 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 683599.01
660 | Darajat | DRJ - 2024 | Drilling Cost | Explosive | Explosive | Explosive | General | 22676.26
661 | Darajat | DRJ - 2024 | Drilling Cost | LIH | LIH | LIH | General | 0
662 | Darajat | DRJ - 2024 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 3485865.57
663 | Darajat | DRJ - 2024 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 1557867.01
664 | Darajat | DRJ - 2024 | Drilling Cost | Rig Skid | Rig Skid | Rig Skid | General | 103749.54
665 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-53 | 6771.23
666 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-54 | 0
667 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-55 | 0
668 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-56 | 0
669 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | DRJ-57 | 6042.02
670 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | General | 0
671 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-53 | 51344.18
672 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-54 | 555950.62
673 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-55 | 889177.81
674 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-56 | 710970.27
675 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | DRJ-57 | 892680.61
676 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing | General | 0
677 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-53 | 0
678 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-54 | 212268.85
679 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-55 | 0
680 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-56 | 0
681 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | DRJ-57 | 0
682 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | General | 0
683 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-53 | 0
684 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-54 | 79581.86
685 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-55 | 81369.12
686 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-56 | 78767.68
687 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | DRJ-57 | 81618.21
688 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Equipment Rental | General | 0
689 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-53 | 179613.75
690 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-54 | 491709.18
691 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-55 | 312598.37
692 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-56 | 432977.03
693 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | DRJ-57 | 560934.25
694 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | General | 0
695 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-53 | 14897.57
696 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-54 | 17937.45
697 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-55 | 21260.21
698 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-56 | 19820.82
699 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | DRJ-57 | 12009.27
700 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Material - Non LL | Consumables | General | 0
701 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-53 | 58943.01
702 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-54 | 45923.6
703 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-55 | 41026.32
704 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-56 | 56654.67
705 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | DRJ-57 | 41595.77
706 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | General | 0
707 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-53 | 247456
708 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-54 | 116360
709 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-55 | 258054
710 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-56 | 272200
711 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | DRJ-57 | 263648
712 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | General | 0
713 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-53 | 50444.7
714 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-54 | 67671.8
715 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-55 | 66983.46
716 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-56 | 89528.22
717 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | DRJ-57 | 52451.98
718 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Casing Installation | General | 0
719 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-53 | 462888.41
720 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-54 | 472474.63
721 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-55 | 531994.69
722 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-56 | 747394.5
723 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | DRJ-57 | 542203.17
724 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | General | 0
725 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-53 | 970902.29
726 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-54 | 977166.3
727 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-55 | 783052.64
728 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-56 | 1174500.15
729 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | DRJ-57 | 617565.9
730 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Contract Rig | General | 0
731 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-53 | 0
732 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-54 | 0
733 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-55 | 0
734 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-56 | 0
735 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | DRJ-57 | 0
736 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Coring | General | 0
737 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-53 | 282292.41
738 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-54 | 566232.97
739 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-55 | 270682.54
740 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-56 | 432060.8
741 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | DRJ-57 | 282841.5
742 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | General | 0
743 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-53 | 10285.62
744 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-54 | 12486.36
745 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-55 | 7271.73
746 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-56 | 20712.73
747 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | DRJ-57 | 7720.67
748 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | General | 0
749 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-53 | 318237.95
750 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-54 | 582091.74
751 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-55 | 475623.6
752 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-56 | 1167015.34
753 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | DRJ-57 | 665835.97
754 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Equipment Rental | General | 0
755 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-53 | 24972.38
756 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-54 | 10541.25
757 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-55 | 26590.89
758 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-56 | 20014.65
759 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | DRJ-57 | 29044.52
760 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | General | 0
761 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-53 | 74275.07
762 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-54 | 38209.46
763 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-55 | 93130.32
764 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-56 | 108360.54
765 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | DRJ-57 | 53406.26
766 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Land Transportation | General | 0
767 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-53 | 71350
768 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-54 | 70250
769 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-55 | 49750
770 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-56 | 110100
771 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | DRJ-57 | 48700
772 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud Logging Service | General | 0
773 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-53 | 637251.5
774 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-54 | 444820.5
775 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-55 | 336707.5
776 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-56 | 697896.5
777 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | DRJ-57 | 315167.5
778 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | General | 0
779 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-53 | 34146.57
780 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-54 | 40556.83
781 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-55 | 21811.64
782 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-56 | 61439.88
783 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | DRJ-57 | 17509.14
784 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | NDT Inspection | General | 0
785 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-53 | 0
786 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-54 | 249600
787 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-55 | 0
788 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-56 | 571655.2
789 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | DRJ-57 | 0
790 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | General | 0
791 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-53 | 0
792 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-54 | 18849.94
793 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-55 | 11385.84
794 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-56 | 15491.37
795 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | DRJ-57 | 7701.69
796 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Other Transportation | General | 0
797 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-53 | 0
798 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-54 | 0
799 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-55 | 0
800 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-56 | 0
801 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | DRJ-57 | 0
802 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Rig Inspection | General | 0
803 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-53 | 1500
804 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-54 | 1500
805 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-55 | 1500
806 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-56 | 1500
807 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | DRJ-57 | 1500
808 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Service Lines & Communication | General | 0
809 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-53 | 100381.75
810 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-54 | 100847.09
811 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-55 | 68405.98
812 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-56 | 116299.85
813 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | DRJ-57 | 53151.03
814 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Supervision | General | 0
815 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-53 | 0
816 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-54 | 0
817 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-55 | 0
818 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-56 | 0
819 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | DRJ-57 | 0
820 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Vehicle Inspection | General | 0
821 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-53 | 11619.22
822 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-54 | 16524.2
823 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-55 | 11566.43
824 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-56 | 20618.01
825 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | DRJ-57 | 9670.59
826 | Darajat | DRJ - 2024 | Drilling Cost | Well Cost | Services | Welding Service | General | 0
827 | Darajat | DRJ - 2024 | Support Cost | Drilling Facilities Support | Drilling Operation Water Support | Drilling Facilities Support | General | 188116.74
828 | Darajat | DRJ - 2024 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 132251.66
829 | Darajat | DRJ - 2024 | Support Cost | IT & Communication | Drilling Facilities Support | Hardware Supply | General | 20405.19
830 | Darajat | DRJ - 2024 | Support Cost | Permitting (IPPKH/IPJLPB) | Hardware Supply | Permitting | General | 156205.65
831 | Darajat | DRJ - 2024 | Support Cost | PGPA & Security | PGPA | PGPA | General | 82973.05
832 | Darajat | DRJ - 2024 | Support Cost | PGPA & Security | Security | Security | General | 37958.17
833 | Darajat | DRJ - 2024 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 443299.87
834 | Darajat | DRJ - 2024 | Support Cost | SHE | Drill Cutting | Heavy Equipment for Drill Cutting | General | 22092.53
835 | Darajat | DRJ - 2024 | Support Cost | SHE | Environmental Monitoring | Environmental Monitoring | General | 20422.64
836 | Darajat | DRJ - 2024 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 18729.87
837 | Darajat | DRJ - 2024 | Support Cost | SHE | SHE Permit | Environment Permit | General | 19289.67
838 | Darajat | DRJ - 2024 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 196078.03
839 | Darajat | DRJ - 2024 | Support Cost | Well Testing | Well Testing | Well Testing | General | 494955.41
840 | Darajat | DRJ - 2024 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 110325.8
841 | Darajat | DRJ - 2024 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Material | General | 579209.1
842 | Darajat | DRJ - 2024 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 810634.08
843 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 1514304.52
844 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 55525.52
845 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Procurement | Material - LL | General | 0
846 | Darajat | DRJ - 2024 | Surface Facilities Cost | Road & Pad | Procurement | Material - Non LL | General | 106778.84
847 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 122872.65
848 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 11687.08
849 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - LL | General | 465218.82
850 | Darajat | DRJ - 2024 | Surface Facilities Cost | Special Requirement Existing Pad | Procurement | Material - Non LL | General | 114836.25
851 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 908012.89
852 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 55781.32
853 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 266811.29
854 | Darajat | DRJ - 2024 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 594127.03
855 | Salak | SLK - 2025 | Contingency | Contingency | Contingency | Contingency | General | 0
856 | Salak | SLK - 2025 | Drilling Cost | Explosive | Explosive | Explosive | General | 142754.25
857 | Salak | SLK - 2025 | Drilling Cost | LIH | LIH | LIH | General | 0
858 | Salak | SLK - 2025 | Drilling Cost | Logging Cost | Logging Cost | Logging Cost | General | 0
859 | Salak | SLK - 2025 | Drilling Cost | Rig Mobilization | Rig Mobilization | Rig Mobilization | General | 2472778.98
860 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Interpad Move | Rig Move | General | 985714.21
861 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Services | Rig Move | General | 709217.51
862 | Salak | SLK - 2025 | Drilling Cost | Rig Move | Skid Moving | Rig Move | General | 830091.9
863 | Salak | SLK - 2025 | Drilling Cost | Rig Skid | Skid Moving | Rig Skid | General | 274554.31
864 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 21-7 | 0
865 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 21-8 | 0
866 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 23-1 | 0
867 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 23-2 | 0
868 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 2-6 | 0
869 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 2-7 ML | 0
870 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 3-9 | 0
871 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 9-10 RD | 0
872 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Asset Transfer | AWI 9-11 | 0
873 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 21-7 | 429505.88
874 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 21-8 | 435335.47
875 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 23-1 | 1054232.96
876 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 23-2 | 965451.4
877 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 2-6 | 575229.74
878 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 2-7 ML | 725447.72
879 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 3-9 | 592905.89
880 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-10 RD | 16239.59
881 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing | AWI 9-11 | 3831.42
882 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 21-7 | 38422.66
883 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 21-8 | 0
884 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 23-1 | 0
885 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 23-2 | 0
886 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 2-6 | 45349.48
887 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 2-7 ML | 33522.6
888 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 3-9 | 0
889 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 9-10 RD | 0
890 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Casing Repair & Modif | AWI 9-11 | 0
891 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 21-7 | 126062.42
892 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 21-8 | 100429.12
893 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 23-1 | 329002.18
894 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 23-2 | 199759.8
895 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 2-6 | 95453.76
896 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 2-7 ML | 295020.14
897 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 3-9 | 239039.65
898 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-10 RD | 0
899 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Fuel & Lubricants | AWI 9-11 | 32866.56
900 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 21-7 | 71550.58
901 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 21-8 | 71550.58
902 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 23-1 | 79719.94
903 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 23-2 | 76400.29
904 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 2-6 | 55714.09
905 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 2-7 ML | 111558.08
906 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 3-9 | 56322.38
907 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-10 RD | 0
908 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - LL | Well Equipment Surface | AWI 9-11 | 0
909 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 21-7 | 13955.48
910 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 21-8 | 589.92
911 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 23-1 | 14250.42
912 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 23-2 | 576.42
913 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 2-6 | 26254.71
914 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 2-7 ML | 43003.2
915 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 3-9 | 6555.58
916 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 9-10 RD | 3627.98
917 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Material - Non LL | Consumables | AWI 9-11 | 27548.57
918 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 21-7 | 1072.77
919 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 21-8 | 42179.35
920 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 23-1 | 16080.49
921 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 23-2 | 34147.78
922 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 2-6 | 9498.84
923 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 2-7 ML | 13606.35
924 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 3-9 | 15034.32
925 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 9-10 RD | 6359.84
926 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | API non API Machine Shop Service | AWI 9-11 | 9621.15
927 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 21-7 | 94068
928 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 21-8 | 172456
929 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 23-1 | 226776
930 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 23-2 | 241956
931 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 2-6 | 226776
932 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 2-7 ML | 129276
933 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 3-9 | 76071
934 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-10 RD | 0
935 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Bits, Reamer and Core heads | AWI 9-11 | 0
936 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 21-7 | 47835.3
937 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 21-8 | 48247.53
938 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 23-1 | 48609.99
939 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 23-2 | 65679.52
940 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 2-6 | 64407.34
941 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 2-7 ML | 80541.2
942 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 3-9 | 47547.44
943 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-10 RD | 0
944 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Casing Installation | AWI 9-11 | 0
945 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 21-7 | 439155.86
946 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 21-8 | 485092.21
947 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 23-1 | 687821.17
948 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 23-2 | 556572.63
949 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 2-6 | 257054.57
950 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 2-7 ML | 452778.44
951 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 3-9 | 484916.72
952 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-10 RD | 0
953 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Cement, Cementing & Pump Fees | AWI 9-11 | 0
954 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 21-7 | 555095.7
955 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 21-8 | 337932.78
956 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 23-1 | 408535.21
957 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 23-2 | 441013.53
958 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 2-6 | 0
959 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 2-7 ML | 202739.53
960 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 3-9 | 586102.57
961 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-10 RD | 0
962 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Contract Rig | AWI 9-11 | 0
963 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 21-7 | 0
964 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 21-8 | 0
965 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 23-1 | 0
966 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 23-2 | 0
967 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 2-6 | 0
968 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 2-7 ML | 0
969 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 3-9 | 0
970 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 9-10 RD | 0
971 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Coring | AWI 9-11 | 0
972 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 21-7 | 208104.94
973 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 21-8 | 276141.51
974 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 23-1 | 330360.01
975 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 23-2 | 305864.51
976 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 2-6 | 383225.5
977 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 2-7 ML | 539568.66
978 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 3-9 | 280036.51
979 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-10 RD | 0
980 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Directional Drilling & Surveys | AWI 9-11 | 17280
981 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 21-7 | 415673.72
982 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 21-8 | 395934.56
983 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 23-1 | 658713.31
984 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 23-2 | 535788.29
985 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 2-6 | 219911.21
986 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 2-7 ML | 636198.74
987 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 3-9 | 553353.44
988 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 9-10 RD | 0
989 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Rig O&M | AWI 9-11 | 0
990 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 21-7 | 6569.31
991 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 21-8 | 7386.96
992 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 23-1 | 9010.76
993 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 23-2 | 9851.29
994 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 2-6 | 4450.16
995 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 2-7 ML | 10083.5
996 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 3-9 | 6928.95
997 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-10 RD | 0
998 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Drilling Safety, Health & Environment | AWI 9-11 | 0
999 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 21-7 | 294408.35
1000 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 21-8 | 236707.6
1001 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 23-1 | 299466.1
1002 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 23-2 | 286869.75
1003 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 2-6 | 0
1004 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 2-7 ML | 569931.8
1005 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 3-9 | 251905.6
1006 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-10 RD | 0
1007 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Equipment Rental | AWI 9-11 | 0
1008 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 21-7 | 6459.45
1009 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 21-8 | 5235.62
1010 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 23-1 | 9269.86
1011 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 23-2 | 5090.54
1012 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 2-6 | 7572.76
1013 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 2-7 ML | 14521.32
1014 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 3-9 | 5122.93
1015 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 9-10 RD | 3114.37
1016 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Explosive Handling & Permitting | AWI 9-11 | 4367.5
1017 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 21-7 | 33177.69
1018 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 21-8 | 138436.38
1019 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 23-1 | 127600.61
1020 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 23-2 | 74352.56
1021 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 2-6 | 58439.03
1022 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 2-7 ML | 211145.09
1023 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 3-9 | 112627.87
1024 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-10 RD | 15785.96
1025 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Land Transportation | AWI 9-11 | 15786.07
1026 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 21-7 | 49600
1027 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 21-8 | 31400
1028 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 23-1 | 42637.5
1029 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 23-2 | 45900
1030 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 2-6 | 23525
1031 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 2-7 ML | 53900
1032 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 3-9 | 43000
1033 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-10 RD | 0
1034 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud Logging Service | AWI 9-11 | 0
1035 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 21-7 | 299496
1036 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 21-8 | 297688.5
1037 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 23-1 | 254115
1038 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 23-2 | 410447
1039 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 2-6 | 218933
1040 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 2-7 ML | 330676
1041 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 3-9 | 258317
1042 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-10 RD | 0
1043 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Mud, Chemical and Engineering Service | AWI 9-11 | 0
1044 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 21-7 | 12977.87
1045 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 21-8 | 32818.09
1046 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 23-1 | 17992.77
1047 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 23-2 | 12618.12
1048 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 2-6 | 11942.24
1049 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 2-7 ML | 27067.6
1050 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 3-9 | 19673.31
1051 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 9-10 RD | 0
1052 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | NDT Inspection | AWI 9-11 | 0.04
1053 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 21-7 | 0
1054 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 21-8 | 0
1055 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 23-1 | 199400
1056 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 23-2 | 0
1057 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 2-6 | 0
1058 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 2-7 ML | 183600
1059 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 3-9 | 0
1060 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 9-10 RD | 0
1061 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Open Hole Electrical Logging Service | AWI 9-11 | 0
1062 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 21-7 | 0
1063 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 21-8 | 0
1064 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 23-1 | 0
1065 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 23-2 | 0
1066 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 2-6 | 0
1067 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 2-7 ML | 0
1068 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 3-9 | 0
1069 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-10 RD | 0
1070 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Other Transportation | AWI 9-11 | 0
1071 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 21-7 | 0
1072 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 21-8 | 0
1073 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 23-1 | 0
1074 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 23-2 | 0
1075 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 2-6 | 0
1076 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 2-7 ML | 0
1077 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 3-9 | 0
1078 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 9-10 RD | 0
1079 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Rig Inspection | AWI 9-11 | 0
1080 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 21-7 | 825
1081 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 21-8 | 795
1082 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 23-1 | 1050
1083 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 23-2 | 1095
1084 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 2-6 | 0
1085 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 2-7 ML | 1350
1086 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 3-9 | 850.5
1087 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-10 RD | 0
1088 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Service Lines & Communication | AWI 9-11 | 0
1089 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 21-7 | 39787.77
1090 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 21-8 | 70968.66
1091 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 23-1 | 65296.11
1092 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 23-2 | 56306.36
1093 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 2-6 | 45711.43
1094 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 2-7 ML | 55185.55
1095 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 3-9 | 33542.53
1096 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-10 RD | 0
1097 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Supervision | AWI 9-11 | 0
1098 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 21-7 | 0
1099 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 21-8 | 0
1100 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 23-1 | 0
1101 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 23-2 | 0
1102 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 2-6 | 0
1103 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 2-7 ML | 0
1104 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 3-9 | 0
1105 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 9-10 RD | 0
1106 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Vehicle Inspection | AWI 9-11 | 0
1107 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 21-7 | 0
1108 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 21-8 | 0
1109 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 23-1 | 0
1110 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 23-2 | 0
1111 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 2-6 | 0
1112 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 2-7 ML | 0
1113 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 3-9 | 0
1114 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 9-10 RD | 0
1115 | Salak | SLK - 2025 | Drilling Cost | Well Cost | Services | Welding Service | AWI 9-11 | 0
1116 | Salak | SLK - 2025 | Support Cost | Drilling Facilities Support | Drilling Facilities Support | Drilling Facilities Support | General | 475455.58
1117 | Salak | SLK - 2025 | Support Cost | Drilling Operation Water Support | Drilling Operation Water Support | Drilling Operation Water Support | General | 320332
1118 | Salak | SLK - 2025 | Support Cost | IT & Communication | Hardware Supply | Hardware Supply | General | 4000.06
1119 | Salak | SLK - 2025 | Support Cost | IT & Communication | Internet and IT Support Service | Internet and IT Support Service | General | 5138.14
1120 | Salak | SLK - 2025 | Support Cost | PGPA & Security | PGPA | PGPA | General | 113196.24
1121 | Salak | SLK - 2025 | Support Cost | PGPA & Security | Security | Security | General | 23682.08
1122 | Salak | SLK - 2025 | Support Cost | Project Management Cost | Project Management Cost | Project Management Cost | General | 13129.99
1123 | Salak | SLK - 2025 | Support Cost | SHE | Drill Cutting | Drill Cutting - Transport & Process | General | 373275.99
1124 | Salak | SLK - 2025 | Support Cost | SHE | Environmental Monitoring | Sampling and Lab Analysis | General | 6855.03
1125 | Salak | SLK - 2025 | Support Cost | SHE | Hazardous Waste | Hazardous Waste | General | 951.75
1126 | Salak | SLK - 2025 | Support Cost | Well Insurance | Well Insurance | Insurance | General | 131647.73
1127 | Salak | SLK - 2025 | Support Cost | Well Testing | Well Testing | Well Testing | General | 417018.49
1128 | Salak | SLK - 2025 | Support Cost | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | Wellsite Geologist (WSG) | General | 147941.46
1129 | Salak | SLK - 2025 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Material | General | 677988.38
1130 | Salak | SLK - 2025 | Surface Facilities Cost | Conductor Casing Installation & Material | Conductor Casing Installation & Material | Service | General | 1165594.54
1131 | Salak | SLK - 2025 | Surface Facilities Cost | New Rig Pavement | Construction | New Rig Pavement | General | 0
1132 | Salak | SLK - 2025 | Surface Facilities Cost | Road & Pad | Construction | Construction | General | 737235.37
1133 | Salak | SLK - 2025 | Surface Facilities Cost | Road & Pad | Engineering | Engineering | General | 67334.7
1134 | Salak | SLK - 2025 | Surface Facilities Cost | Special Requirement Existing Pad | Construction | Construction | General | 0
1135 | Salak | SLK - 2025 | Surface Facilities Cost | Special Requirement Existing Pad | Engineering | Engineering | General | 43417.87
1136 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Construction | Installation, Hook Up & Pre-Commisioning | General | 377631.68
1137 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Engineering | Engineering | General | 292017.33
1138 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Procurement | Material - LL | General | 1051404.93
1139 | Salak | SLK - 2025 | Surface Facilities Cost | Tie-in | Procurement | Material - Non LL | General | 208699.68